## E_Gov Godišnji izveštaj o sprov
Annex 3: Table from UIS system, contribution of specific institutions on E-Government Development Programme of the Republic of Serbia 2020−2022 for the year 2020
Annual Report on the Implementation of the 2020 Action Plan for the: |  |  |  |  | Implementation of the e-Government Development Programme of the Republic of Serbia 2020−2022
Institution responsible for coordination and reporting: |  |  |  |  | MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Public policy document elaborated by the Action Plan: |  |  |  |  | e-Government Development Programme of the Republic of Serbia 2020−2022
Overall objective 1: Development of an efficient and user-centric administration in a digital environment
Document proponent: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT (MPALSG)
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
EU benchmark for e-Government |  |  | 37 (2019) |  | 43 | 43.75 | The latest 2020 eGovernment Benchmark report (https://ec.europa.eu/digital-single-market/en/news/egovernment-benchmark-2020-egovernment-works-people) published the performance by 36 European countries in four areas / benchmarks in delivery of electronic services (user centricity, transparency, citizens cross border mobility/business cross border mobility, key enablers) measured over the past two years 2018/2019, based on eight life events. The Republic of Serbia has made a 7% progress compared to the previous report, and the best results were achieved in the area of user-centered eGovernment. The 2021 eGovernment Benchmark report will include the results in the field of eGovernment for year the 2019/2020.
Specific objective 1: Development of e-Government infrastructure and ensuring interoperability
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of public authorities using centres for storing and managing data in production and/or in operational use |  |  | 37 (2019) |  | 60 | 71
Number of LSGUs using centres for storing and managing data in production, i.e. in operational use |  |  | 0 (2019) |  | 5 | 168
Number of services downloading data from the Central Population Register |  |  | 0 (2019) |  | 1 | 1 | All receiving bodies will use the same service for downloading data. The e-Government Portal is currently using this service.
Measure 1.1.1: Establishing State Data Management and Storage Centre in Kragujevac − Data Centre Kragujevac and Improvement of the State Data Management and Storage Centre in Belgrade − Data Centre Belgrade
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of registers migrated to data centres |  |  | 0 (2019) |  | 20 | 55 | One of the registers kept in the State Data Management and Storage Centre is the Central Population Register, which contains centralised data on citizens from 13 official records and five databases. Some registries have a confidentiality status and therefore cannot be published.
Number of software solutions migrated to data centres |  |  | 0 (2019) |  | 15 | 100
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.1.1.1: Adoption of by-laws to regulate the data management and storage infrastructure; | Q3 2020 –> Q4 2021 | MPALSG | Not commenced yet | – | . |  | The COVID-19 pandemic caused the postponement of work on the drafting of the by-law that should regulate the data management and storage infrastructure (pursuant to Article 29 of the Law on Electronic Administration, The Official Gazette of the Republic of Serbia, No. 27/18). Also, the issue of operational management of infrastructure of the newly built secondary Data Centre in Kragujevac should have been resolved. In mid-November 2020, the Office for Information Technologies and eGovernment submitted a request to the MPALSG seeking opinion on the Government's decision proposal on the establishment of the “Data Cloud Technology” Limited Liability Company.” | It is planned to establish the Working group for the adoption of by-laws regulating the data management and storage infrastructure will in the Q1 2021.
1.1.1.2: Drafting an Analysis of options for the operational management of Data Centre Kragujevac and adoption of the best option; | Q1 2020 | ITE Office | Completed | – | Analysis of options for the operational management of the Data Centre in Kragujevac has been prepared. . |  | . | .
1.1.1.3: Drafting the initial plan of migration and assessment of the readiness of applications to be migrated to the cloud; Improvement of the migration plan and assessment of the readiness of applications to be migrated to the cloud; ; | Q4 2020 –> Q4 2021 | ITE Office | In progress | – | Activity has been initiated. |  | The COVID-19 pandemic has slowed down the activities on developing a migration plan. The activities will be intensified in the upcoming period. | A new deadline for the completion of activities has been defined – Q4 2021.
1.1.1.4: Construction of facilities 1 and 2 of Data Centre Kragujevac and furnishing up to the level of IT equipment racks; | Q2 2020 –> Q4 2022 | ITE Office | In progress | 100% | Facility 1 was completed and ceremoniously put into trial operation. The construction of facility 2 has begun. |  | There are no deviations, the deadline for the construction of Facility 1 is 2020 and the construction of Facility 2 is proceeding according to the planned dynamics, with the deadline in Q4 2022. | There are no deviations, the deadline for the construction of Facility 1 was 2020 and the construction of Facility 2 is proceeding according to the planned dynamics. The project is expected to be completed in Q4t 2022.
1.1.1.5: Initial furnishing of facility 1 of Data Centre Kragujevac with ICT equipment; | Q3 2020 –> Q4 2021 | ITE Office | In progress | – | The activity has not been completed because the WB loan foreign currency funds have not been converted. . |  | The COVID-19 pandemic. The conversion of the WB loan foreign currency funds will be pushed forward. | A new deadline for the completion of activities has been defined – Q4 2021.
1.1.1.6: Installing a cloud platform at Data Centre Kragujevac with a cloud management solution. | Q4 2020 –> Q1 2022 | ITE Office | In progress | – | The activity has not been completed because the WB loan foreign currency funds have not been converted. |  | The COVID-19 pandemic affected the implementation of activities and plans. The activity has not been completed because the WB loan foreign currency funds have not been converted. | A new deadline for the completion of activities has been defined – Q1 2022.
Measure 1.1.2: Improving the Unified Information-Communication Network of e-Government
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Percentage of LSGUs connected to the UIC network |  |  | 0 (2019) |  | 40 | 96.55 | Connection of bodies to the Unified Information and Communication e-Government Network is performed in accordance with the Decree on Organisational and Technical Standards for Maintenance and Improvement of the Unified Information and Communication Network of e-Government and connection of bodies to that network (The Official Gazette of the Republic of Serbia, No. 104, 28 December 2018)
Number of established redundant nodes in Belgrade |  |  | 0 (2019) |  | 2 | 12
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.1.2.1: Drafting a concept and technical solution with the aim of initial improvements to UIC network management (procedures, supervision, configuration, information security aspect); | Q4 2020 | ITE Office | Completed | 100% | A conceptual and technical solution has been developed which has improved the UIC network management, which has enabled greater accessibility, availability and faster resolution of challenges. The development of the UIC network of state bodies was performed with the aim to ensure secure communication and data exchange between public administration bodies. |  | . | Provide adequate inspection of the UIC network (network traffic flow and monitoring of network devices), as well as the establishment of NOC (Network Operation Centre). This is foreseen by the following activity with the deadline in Q4 2021.
1.1.2.3: Establishing redundant nodes in Belgrade; | Q4 2020 –> Q4 2021 | ITE Office | In progress | – | The activity has not been completed because the WB loan foreign currency funds have not been converted. |  | One of the main challenges concerning the public administration ICT infrastructure is the lack of redundant hubs. The building of redundant hubs was slowed down by the COVID-19 pandemic, as well as due to procedures concerning the WB loan foreign currency funds conversion. | A new deadline for the completion of activities has been defined, which is the Q4 2021. Тhe conversion of the WB loan foreign currency funds will be pushed forward.
1.1.2.4: Improvement of domain infrastructure in all bodies that are part of e-Government. | Q4 2020 | ITE Office | Completed | 100% | The domain infrastructure has been improved, achieving greater accessibility and availability of Microsoft collaboration services (mail, teams, SharePoint), which were especially important during the pandemic and large number of employees working remotely. . |  | . | .
Measure 1.1.3: Establishing a unified Register Office, e-Archive and integration with existing systems
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of institutions using the Register Office as a primary tool |  |  | 0 (2019) |  | 2 | 0 | Unified Register Office implementation deadline is end 2021.
Number of institutions which have integrated the existing software solutions into the e-Register Office and e-Archive |  |  | 0 (2019) |  | 0 | 0 | e-Register Office implementation deadline is end 2021.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.1.3.1: Adoption of regulations on office operations. | Q3 2020 | MPALSG | Completed | – | The Decree on Office Operations of State Administration Bodies regulates the field of modern office operations, following the application of new information and communication technologies and systems (software solutions for e-Register Offices, DMS and e-Archives) in order to improve the operations of RS bodies with citizens and economy. The Decree on Office Operations of State Administration Bodies (The Official Gazette of the Republic of Serbia, No. 21, 6 March 2020) shall apply from 1 April 2021. The Decree is available at https://www.pravno-informacioni-sistem.rs/SlGlasnikPortal/eli/rep/sgrs/vlada/uredba/2020/21/7/reg . |  | . | .
Measure 1.1.4: Development of other joint (shared) IT services for public administration purposes
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of state bodies integrated into the collaboration system |  |  | 5 (2019) |  | 10 | 12 | The integration of state bodies continued in 2020 aimed at greater use of collaboration services. Two more state bodies are currently being integrated into the system, and they will be able to share e-Government services and facilitate some of the tasks.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.1.4.1: Improvement of the e-Payment+ function on the e-Government Portal (collection of all fees and/or unified collection of fees for one service, with one fee payment transaction and elimination of the need to submit the proof of payment (identification by reference number and derecognition); | Q1 2020 | ITE Office | Completed | 100% | The functionality has been improved and the system is now being tested for possible errors or bugs, after which it will be put into operation. . |  | . | .
1.1.4.2: Implementation of the mandatory use of gov.rs and упр.срб domains for all public administration bodies; | Q4 2020 –> Q4 2021 | ITE Office | In progress | – | Implementation activities are in progress. |  | The pandemic caused a delay in the start of this activity. Implementation will be intensified in line with pandemic protection and precautionary measures. | New deadline for the completion is Q4 2021.
1.1.4.3: Improvement of the service for the use of e-mail accounts for authorised officials (technological improvement). | Q3 2020 –> Q4 2021 | ITE Office | In progress | – | Implementation activities are in progress. |  | The COVID-19 pandemic. Implementation of activities will continue in accordance with pandemic protection and precautionary measures. | New deadline for the completion is Q4 2021.
Measure 1.1.5: Development of architecture and implementation of a Platform supporting the development and use of e-Government services
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of implemented e-Government services |  |  | 5 (2019) |  | 75 | 0 | Data will be available after the establishment of the Metaregister, aimed at ensuring interoperability in e-Government. Deadline for this activity is set for Q2 2021.
Measure 1.1.6: Establishing new and improving existing registers and records in electronic form to support the development of e-Government services
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Percentage of established registers compared to the total number of registers covered under this measure |  |  | 10 (2019) |  | 35 | 35 | Registers covered by this measure: 1. Central Population Register; 2. Address register; 3. Social Welfare IS; 4. Unified Social Card IS; 5. Improvement of the Property Register – Real-Estate Cadastre; 6. Improvement of the Business Registers; 7. Digitalisation of the Register of Agricultural Farms (e-Agrar); 8. Improvement of the veteran-disability protection IS; 9. Improvement of the child and family protection IS;
Number of institutions using data from the Register |  |  | 300 (2019) |  | 1500 | 320 | Number of bodies that electronically exchange data via the service bus on daily basis.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.1.6.1: Development of a software solution and establishment of a Central Population Register (data migration); | Q3 2020 | ITE Office | Completed | 100% | The software solution is developed and the system is being prepared. Citizens are invited to check their data. . |  | On 20 November 2020, the Central Population Register was put into operation. The ITE Office completed the public procurement, a software solution was developed and data migration was completed. The office is in charge of storing and keeping citizens' database. The citizens' database is located in the State Data Centre and is kept according to the highest technical and security standards. Pursuant on the Law on the Central Population Register, it is defined that MPALSG approves access to the Central Population Register, and IT and data security operations are performed by the Office for IT and eGovernment. Starting from April 2021, the MPALSG will begin the process of approving access to the CRS. | .
1.1.6.2: Establishment of an up-to-date Address register (improvement of the software solution and entry of missing data) and Register of Spatial Units; | Q2 2020 | RGA | Completed | 100% | Central AR database was established on 2 December 2019. |  | . | .
1.1.6.4: Establishment of the unified Social Card IS (development of a software solution, connection, taking over and unification of data from the records of state authorities and their putting into use). | Q4 2020 –> Q1 2022 | MLEVSA | Not commenced yet | – | No progress was made. |  | The condition for the establishment of the register is the adoption of the Law on Social Cards, which was not passed as planned in 2019. | Adoption of the Law on the Social Cards at the beginning of 2021, followed by public procurement for the establishment of the register.
1.1.6.9: Improvement of the child and family protection IS. | Q4 2020 –> Q1 2022 | MLEVSA | Not commenced yet | – | No progress was made. |  | The expected amendments to the Law on Financial Support for Families with Children were not passed, which would be a reason for improving the system. | The competence in the area of amending the Law on Financial Support for Families with Children now falls under the newly formed Ministry of Family Care and Demography. Having in mind the Decisions of the Constitutional Court of December 2020, by which certain paragraphs of provisions of the Law on Financial Support to Families with Children were declared unconstitutional, and the fact that the publication of Decisions in the The Official Gazette of the Republic of Serbia were postponed by six months, it is necessary to start drafting the Amendments to the Law on Financial Support for Families with Children. The draft Amendments are expected to be completed in February 2021 and sent for further procedure to the National Assembly so that they could be adopted by the end of May 2021. The change of legal solutions will require appropriate changes to by-laws, as well as appropriate changes in the application software for calculation and payment.
Measure 1.1.7: Establishing a unified Public Register of Procedures
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA (PPS)
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Public Register of Administrative Procedures up and running |  |  | 0 (2019) |  | 1 | 0 | The Register was prepared within the set deadline, but was not released because 86 bodies and organisations must update the data entered in the Register, which refer to 2,618 procedures implemented at the national and provincial level. These activities will be completed during the Q1 2021 and after that the Register will be released.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.1.7.1: Preparation of a draft Law that would regulate the establishment and functionality of the Register; | Q4 2020 | PPS | Completed | 100% | A draft law on the Register of Administrative Procedures was drafted and a public discussion was held. The adopted objections received in the public discussion were included in the draft Law. |  | There were no deviations. | According to the plan, the draft law will be put into the procedure for obtaining opinion by the end of January 2021.
1.1.7.2: Adoption of by-laws based on the Law that would regulate the establishment and functioning of the Register; | Q4 2020 –> Q3 2021 | PPS | Not commenced yet | – | . |  | . | A request was sent for the appointment of members of the working group for the development of by-laws based on the Law on the Register. The working group will be formed by the end of January 2021 at the latest, with a task to prepare drafts of relevant regulations by April 2021, which should be adopted by June 2021 at the latest.
1.1.7.3: Development of the software solution of a portal for the Register of Administrative Procedures; | Q2 2020 | ITE Office | Completed | 100% | Software solution has been developed and is now in the test phase. After the noted errors have been fixed it will be put into production. |  | . | .
1.1.7.4: Mapping and entry into the Register of administrative procedures for citizens at the national level; | Q2 2020 –> Q1 2022 | ITE Office | Not commenced yet | – | The activity has not been completed because the WB loan foreign currency funds have not been converted. |  | The COVID-19 pandemic. The conversion of the WB loan foreign currency funds will be pushed forward. | A new deadline for the completion of activities has been defined – Q1 2022.
1.1.7.5: Detailed list of 150 administrative procedures for citizens at the national level; | Q2 2020 –> Q2 2022 | ITE Office | Not commenced yet | – | The activity has not been completed because the WB loan foreign currency funds have not been converted. |  | The COVID-19 pandemic. The conversion of the WB loan foreign currency funds will be pushed forward. | A new deadline for the completion of activities has been defined – Q2 2022.
1.1.7.6: 50 simplified selected administrative procedures for citizens at the national level. | Q3 2020 –> Q2 2022 | ITE Office | Not commenced yet | – | The activity has not been completed because the WB loan foreign currency funds have not been converted. |  | The COVID-19 pandemic. The conversion of the WB loan foreign currency funds will be pushed forward. | A new deadline for the completion of activities has been defined – Q2 2022.
Measure 1.1.8: Improving public administration human resources to establish and apply information technologies in e-Government
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of public administration staff certified for ITIL |  |  | 0 (2019) |  | 30 | 0
Number of systematised and filled jobs for IT officers in the public administration |  |  | 0 (2019) |  | 1 | 595 | Source of verification: Human Resources Management Service. Note: The stated data refers to the number of systematized jobs, and it doesn't include the jobs of IT officers in the Ministry of Defense, the Ministry of Interior and the Directorate for Execution of Criminal Sanctions, because the Regulations on Internal Organization and Systematization of Jobs of these bodies are confidential at certain level. The Human Resources Management Service planned to put into production an information system by the end of 2021, from which statistics on the number of vacancies can be obtained.
Number of systematised and filled jobs for IT officers in LSGUs |  |  | 0 |  | 1 | 210 | The Ministry of Public Administration and Local Self-Government has sent a request to the all local self-government units and the data are in the collection phase. According to the received data 98 local self-government units have 210 systematized jobs for IT officers, and most of the systematized jobs have been filled. Thirteen out of 98 local self-governments do not have systematized IT jobs at all (Arandjelovac, Golubac, Bela Crkva, Titel, Ljig, Knić, Gadžin Han, Sremski Karlovci, Ada, Arilje, Kuršumlija, Veliko Gradište and Beočin), while some local governments are in the lead in the number of IT experts: Beograd (22), Zrenjanin (13), Subotica (8), Inđija (7), Novi Pazar (6), Loznica (6) and Kruševac (5). Some local self-government units have signed service contracts with private companies in the field of information and communication technologies or employed IT workers on determinate period.
Number of civil servants trained to work in a digital environment compared to the total number of civil servants employed by the public administration authority, i.e. LSGUs |  |  | 50 (2019) |  | 60 | 600
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.1.8.2: Implementation of training for IT staff; | Q4 2022 | NAPA | In progress | – | NAPA continuously conducts training intended for IT staff. During 2020, the following training was conducted: Use of ECDL databases – 3 training sessions – 54 participants; Using the National infrastructure of geospatial data towards more efficient administration and better public services – 1 online training – 20 participants; Information security – ICT systems of special importance – 1 online training – 40 participants; e-Government in the service of citizens – 1 training – 44 participants; Electronic document, electronic identification and trust services in electronic business – 2 training sessions – 266 participants; IT security – 1 training – 111 participants; Data opening and visualisation – 1 training – 25 participants; Application of guidelines for the production of internet presentations and visibility of internet presentations – 1 training – 40 participants; Total: 11 training sessions and 600 participants. |  | . | Additional donor funds are needed in order to expand the scope of training, which were not provided in 2020. NAPA plans to conduct these training sessions in the next period using funds from the RS budget.
1.1.8.3: Drafting pilot online courses in the field of e-Government for civil servants on the NAPA platform; | Q2 2020 | ITE Office | Completed | – | Pilot online courses in the field of e-Government for civil servants have been developed on the NAPA platform. NAPA makes training plans, schedules and conducts training, keeps records, issues certificates, etc. |  | . | .
1.1.8.7: Strengthening ITE Office capacities (management, development and control role). | Q4 2020 | ITE Office | Completed | – | The capacity of the ITE Office is strengthened in the segment of customer support, infrastructure improvement, establishment of new IS, services, information security, etc. |  | . | .
Measure 1.1.9: Improving information security and standards
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Share of institutions which have an established and functional information security system and which meet information security standards (adopted Regulation on information security and adopted disaster recovery plan) compared to the implemented regular and extraordinary inspections on annual level. |  |  | 10 (2019) |  | 70 | 100 | According to the data from the regular and extraordinary inspection supervision in 2020, supervision inspection was performed in 17 bodies and all of them have a safety act in place. Source of verification: Ministry of Trade, Tourism and Telecommunications
Number of implemented information security tests for ICT in public administration and local self-government |  |  | 15 (2019) |  | 30 | 0 | Source RATEL: Bearing in mind that the competence of the National CERT is prescribed by the Law on Information Security (The Official Gazette of the Republic of Serbia, Nos. 6/2016, 94/2017 and 77/2019) and that the competence of testing ICT information security in state administration and local self-government is not prescribed by this Law, no testing has been performed. No report on the testing of the information security of the ICT system of state administration and local self-government has been submitted to the National CERT.
Number of civil servants that have completed cyber exercises |  |  | 50 (2019) |  | 100 | 32 | Verification sourceе: RATEL.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.1.9.1: Issuing expert recommendations for the protection of ICT systems of public administration bodies, which include the application of standards for disaster recovery and business continuity. | Q4 2020 –> Q4 2021 | ITE Office | In progress | – | Activity is in progress, and recommendations for system security are being prepared. |  | COVID-19 pandemic. Continued implementation. | A new deadline for the completion of activities has been defined – Q4 2021.
Specific objective 1.2: Improvement of legal certainty in the use of e-Government
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of court acts and documents concerning or stemming from proceedings before judicial organs which have been delivered to businesses and natural persons through the unique electronic mailbox |  |  | 0 (2019) |  | 100 | 0 | The e-Justice uses the e-Court application in which registered users have their own unique e-Mailbox. As far as electronic delivery is concerned, analysis and work on changes in the legal framework are in progress.
Number of regulations by inspection authorities sent to the unique electronic mailbox of businesses and natural persons |  |  | 0 (2019) |  | 1500 | 1700
Measure 1.2.1: Harmonising the legal framework with the regulations governing e-Government and e-Commerce
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Percentage of the legislation harmonised with general regulations on e-Government and e-Commerce compared to the previously identified number of regulations that need to be harmonised |  |  | 0 (2019) |  | 10 | 0
Measure 1.2.2: Establishing inspection control of the electronic service delivery quality
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of implemented supervision controls by competent inspections through the use of e-tools (AI and ISI) |  |  | 0 (2019) |  | 20 | 315 | The administrative inspection applies the software solution e-Inspector when performing inspection control, (or when performing the inspection procedure as a special administrative procedure by applying the specified software solution).
Number of state administration, APs, and LSG bodies implementing electronic administrative procedures whose electronic systems are open for supervision by the Administrative Inspection |  |  | 0 (2019) |  | 200 | 350 | For the purposes of conducting inspections of the application of regulations on the unified electoral roll and registers, the administrative inspection was able to inspect two special software solutions used by the Ministry of State Administration and Local Self-Government and all local self-government units for the purposes of updating the unified electoral roll and maintaining registers.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.2.2.1: Drafting checklists for control over the implementation of regulations in e-Government (AI and ISI); | Q2 2020 –> Q4 2021 | MPALSG | In progress | – | Work on production of checklists has been initiated. . |  | A checklist was prepared for the needs of inspection supervision over the application of the LAP as a general, umbrella regulation regulating the administrative procedure, and there is continued work on the development of checklists for the needs of inspection supervision over the application of regulations governing the use of information and communication technologies and office operations. The new Regulation on office operations shall come into force as of 1 April 2021, and it is necessary to issue instructions on the implementation of this regulation and have normative regulation of the electronic seal of state bodies. | Continued work on the development of checklists for monitoring the implementation of regulations in the field of e-Government.
1.2.2.2: Ensuring access to information systems of state bodies to inspections competent for supervision through the use of the e-Inspector software tool. | Q4 2020 –> Q4 2021 | ITE Office | In progress | – | The activity is in progress and half of the planned functionalities are provided. Further implementation is ongoing. |  | The pandemic caused a delay in this activity, but implementation continues. | New completion deadline has been defined – Q4 2021.
Measure 1.2.3: Establishing a mechanism for correcting and updating data entered into the registers and monitoring the use of personal data
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of official records available in electronic form on the service bus (for citizens to be able to check whether their personal data is current and accurate) |  |  | 0 (2020) |  | 25 | 13 | Pursuant to Article 10 of the Law on the Central Population Register (The Official Gazette of the Republic of Serbia, No. 17, 14 March 2019), the Central Register is kept on the basis of data from 13 original official records, specifically: 1) records on personal identification numbers of citizens – unique personal identification number of citizens; 2) records on citizenship – citizenship of the Republic of Serbia; 3) registry books (births, marriages, deaths); 4) records of permanent and temporary residence and temporary residence abroad; 5) records on identity cards; 6) records on travel documents; 7) Central Register of Compulsory Social Insurance; 8) records of taxpayers; 9) records on foreigners/aliens; 10) records on asylum seekers, aliens who have been granted asylum, aliens who have been granted subsidiary protection...; 11) records on foreigners who do not have a permit for permanent residence or temporary residence in the Republic of Serbia, and have acquired property or rights and obligations on the basis of pension and disability insurance or the status of a taxpayer; 12) records on refugees from the former Yugoslav republics; 13) Address register.
Number of requests for the correction of data kept in the official records which are available electronically, submitted through the e-Government Portal |  |  | 0 (2020) |  | 200 | 394 | These are electronic requests for correction of inaccurate data within the Central Population Register
Number of requests for the correction of data kept in the official records which are available electronically, submitted to the authorities |  |  | 0 (2020) |  | 50 | 394 | Submitted electronically within the Central Population Register
Number of requests for reports on the use of electronically available personal data by authorities [in their regular course of business] |  |  | 0 (2020) |  | 20 | 0
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.2.3.1: Development of a functional–technical specification and implementation of a technical solution that will enable a user of the e-Government Portal to review all data kept on them, monitor its processing, and submit electronic requests for correcting data. | Q1 2020 | ITE Office | Completed | – | The development of the Central Population Register (CPR) and its implementation allows the users of the e-Government Portal to review all data kept about them and submit electronic requests for their correction. |  | . | .
Measure 1.2.4: Ensuring effective protection of the rights of e-Government users in court proceedings
Institution in charge: MINISTRY OF JUSTICE (MoJ)
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of court proceedings which can be initiated electronically |  |  | 4 (2019) |  | 10 | 6 | Three types of electronic public sale (movables, real estate and joint sale of goods). Issuance of data from the Criminal Records of Legal Entities (CRLE) for special departments of higher courts for combating corruption, special department of the High Court in Belgrade for organised crime, CRLE for higher courts and CRLE for basic courts.
Percentage of courts which accept writs and evidence submitted electronically compared to the total number of courts |  |  | 2.6 (2019) |  | 20 | 3.1 | Administrative and Appellate Courts receive submissions and evidence electronically, and due to the pandemic, the digitalisation of Commercial Courts has been postponed, which also requires necessary legal changes.
Percentage of courts which access, ex officio, data in electronic records required for conducting the proceedings and issuing decisions compared to the total number of courts |  |  | 90 (2019) |  | 100 | 100 | Judicial Information System is accessible to all.
Number of judges trained to work in a digital environment compared to the total number of judges |  |  | 0 |  | 150 | 173 | A total of 58 judges were trained in the field of human rights within the Council of Europe Programme on Human Rights Education for Legal Professionals (HELP), on the topic of fight against human trafficking (using a distance learning software), within the subject “Use of databases of case law of the European Court of Human Rights”, and a total of 20 judges were trained in the use of available databases of case law of the European Court of Human Rights. In the field of special knowledge and skills within the training in the use of electronic database of case law, 95 judges were trained in the use of software.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.2.4.5: Determining educational needs of holders of judicial office and employees in judiciary; | Q2 2020 | JA | Completed | – | The Judicial Academy conducts annual analysis of training needs assessments in November and December of the current year for the following year. In December 2020, the Department for Research and Improvement of Education of the Judicial Academy conducted a training needs analysis, which is the basis for the planning of the Annual Training Program and is an important source of data for developing a list of priorities for improving the quality of the existing and new training, and budget planning related to organisation and implementation. |  | . | .
1.2.4.6: Development and adoption of training programme for 2021. | Q4 2020 | JA | Completed | – | The Annual Training Program for 2021 has been prepared. The training program of the Judicial Academy is available through the following link https://www.pars.rs/sr/strucno-usavrsavanje. |  | . | .
Measure 1.2.5: Improving the legal framework and practice of using e-Signatures and e-Seals within public administration
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of issued qualified electronic seals (target 10,000), first year 10%, second year 30%, third year 60%) |  |  | 0 (2019) |  | 200 | 15 | Verification source: Ministry of Trade, Tourism and Telecommunications
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.2.5.1: Adoption of a by-law on office operations that will regulate the method of using e-Signature and e-Seal. | Q3 2020 | MPALSG | Activity was abandoned | – | . |  | The development of the e-Registry Office software should enable the implementation of the new Regulation on office operations. This requires the use of qualified electronic seal in the performance of the activities, which is currently regulated by regulations relating to electronic business and electronic administration. The appearance and content of the seal are regulated by the Law on the Seal of State and Other Bodies (The Official Gazette of the Republic of Serbia, No. 101/2007), which does not currently recognise the use of electronic seals. | The procedure of enacting the Amendments to the Law on the Seal of State and Other Bodies has been initiated. This will regulate the purpose, content, appearance and use of qualified electronic seals when state and other bodies use electronic exchange of document materials prepared or created in work of these bodies.
Measure 1.2.6: Improving delivery in e-Government
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of activated electronic mailboxes for companies and legal persons |  |  | 0 (2019) |  | 20000 | 12931
Number of activated electronic mailboxes for natural persons |  |  | 0 (2019) |  | 80000 | 320000
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.2.6.2: Enactment of a Rulebook on terms and conditions for services of verified electronic delivery. | Q1 2020 | MTTT | Completed | – | The Rulebook on terms and conditions for services of verified electronic delivery and the content of the receipt has been adopted. |  | . | .
Specific objective 1.3: Increase of e-Government accessibility to citizens and businesses by improving client service
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
EU e-Government Benchmark – Key enablers |  |  | 24 (2018) |  | 35 | 28 | The RS has made progress compared to the previous eGovernment Benchmark Report in the field of “key enablers, i.e. e-Government enablers”, which assesses the availability of e-documents, e-identification and electronic delivery of documents to citizens and businesses through established electronic mailboxes. Since the national identification portal for the use of e-government services was established in 2020 (https://eid.gov.rs/) and the connection of other portals and web presentations to the Single Sign On system is in progress, as well as the electronic delivery via the Single Electronic Mailbox of Citizens is growing, it is necessary to wait for the next comparable year, which is 2021. The EU Benchmark report is comparable only at a 2-year level.
EU e-Government Benchmark – User centricity |  |  | 68 (2018) |  | 73 | 70 | The Republic of Serbia has made the greatest progress in the field of user-centred e-Government. RS is recording constant growth in this segment, which determines the extent to which services are provided online, how much customer support is available, and the extent to which services and official presentations of bodies are mobile friendly. The EU Benchmark report is comparable at a 2-year level, so the 2020 is compared to 2018 and 2021 to 2019. It is necessary to wait for the eGovernment Benchmark report 2021.
Measure 1.3.1: Improving the e-Government Portal and other software solutions
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of services on the e-Government Portal |  |  | 20 (2019) |  | 50 | 140 | The source of data is the statistics from the e-Government Portal (submitted by the administrator of the e-Government Portal). The largest number of established services are those intended for citizens, and among them are current services related to the COVID-19 pandemic. The latest services on the Portal (https://euprava.gov.rs/) include: • Expression of interest for vaccination against COVID-19 • e-Schedule for the SARS-CoV-2 test (traveling to Germany) • e-Schedule for PCR testing • Tobacco products – Tobacco Administration • Notify me if the PCR test on COVID-19 is complete
Number of active e-Government Portal service-users |  |  | 300,000 (2019) |  | 500000 | 320000 | Data refers to active users. The source is the statistics of the e-Government Portal and the Portal administrator generates data from the system. According to official data, 1,026,347 citizens use the e-Government Portal, about 48,000 children are enrolled in preschool institutions through the established e-Kindergarten service, and in January 2020 alone, the number of realised services was close to 80,000.
Share of level-four sophistication services available on the Portal compared to the total number of electronic services on the e-Government Portal |  |  | 0 (2019) |  | 20 | 26 | The level of sophistication of the service starts from the basic level, which implies only providing information; the second level is one-way interaction (simple download form); the third level is a two-way communication and interaction with users; the fourth level are transactions (service is completely available online); the fifth level of sophistication is the personalisation of services, which includes proactive services. The source is the statistics of the e-Government Portal and the Portal administrator generates data from the system.
Percentage of users with positive experience using services through the e-Government Portal |  |  | 0 (2020) |  | 50 | 93 | The source is the statistics of the e-Government Portal, and the Portal administrator generates data from the system.
e-Government Portal’s functionality harmonised with accessibility standards |  |  | 0 (2020) |  | 60 | 70 | 1) Validation in terms of e-Accessibility – 0 points, 46 HTML and 15 CSS errors 2) Navigation through the whole presentation is available with the help of the <Tab> key, and a partial, half point is visually noticeable – 3 points out of 5 3) All documents on the website offered for download are in a readable format. There are no scanned documents in the form image. Maximum number of points – 5 out of 5 4) The content on the site is adapted for the use of tools such as text-to-speech or screen reader. Maximum number of points – 5 out of 5 5) Documents available for download are offered in several formats: text (pdf, docx, odt) and tabular (xlsx, ods) in one format, half points, 3 out of 5 6) Images and photographs on the web presentation have alternative text. Maximum number of points – 5 out of 5 Exact estimate – total of 21 points out of possible 30. Compliance 70%
Number of services provided annually through the e-Government Portal |  |  | 0 (2019) |  | 1100000 | 1500000 | The source is the statistics of the e-Government Portal, and the Portal administrator generates data from the system.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.3.1.1: Establishing a mechanism for measuring the user experience on the e-Government Portal (drafting a methodology for analysing the user experience on the e-Government Portal, drafting the analysis and establishing the mechanism); | Q2 2020 –> Q1 2021 | ITE Office | In progress | – | The methodology is in the final stage of development and its completion is expected in early 2021. |  | COVID-19 pandemic. Continued implementation. | New completion deadline has been defined for this activity – Q1 2021.
1.3.1.2: Establishment of e-Signature and e-Seal in the cloud, e-IDs and two-factor (multifactor) identification of the users of e-Government services (and inclusion of bodies). | Q4 2022 | ITE Office | In progress | 100% | Two-factor identification is in production. The deadline for the implementation of e-signatures and e-seals in the cloud is Q4 2022. |  | Activity is implemented as planned. See AP. | Deadline for the completion of the second part of the activity is Q4 2022.
Measure 1.3.2: Standardisation and optimisation of electronic services to improve client services
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Percentage of standardised and optimised services among the 100 selected |  |  | 0 (2019) |  | 10 | 27 | With the introduction of new electronic services for businesses on the e-Government Portal through the e-Paper Programme, the first 27 fully digitised procedures for issuance of permits, licences and consent forms are now available to businesses in Serbia. This innovation is part of a three-year project for the improvement of business environment in Serbia, implemented by the Public Policy Secretariat, Office for IT and eGovernment of the Government of the Republic of Serbia and the International Finance Corporation (IFC), a member of the World Bank Group, with financial support from the United Kingdom Good Governance Fund and the British Embassy in Belgrade. The first digitised procedures include, but are not limited to, entry in the register of distributors and importers of plant nutrition products, recognition of registration of plant protection products, entry in the register of producers of seeds, seedlings, mycelium of edible and medicinal mushrooms, entry in the register of plant nutritionists and soil enhancers, and many others.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.3.2.1: Drafting functional specifications of draft amendments to regulations with the aim of optimising procedures related to life events; | Q4 2020 | ITE Office | Activity was abandoned | – | Activity was not implemented because no funds were provided. |  | Activity was not implemented because no funds were provided. | .
1.3.2.2: Digitalise 100 selected procedures for businesses at the national level and set them up on the e-Government Portal (creation of electronic services). | Q2 2021 | ITE Office | In progress | 30% | 27 procedures have been digitalised. Implementation of other procedures is going as planned. |  | Activities are proceeding according to the planned dynamics. For some reason, the deadline stated in the AP is wrong, because the planned deadline for the realisation of this activity is 2021. | Digitisation of the remaining procedures will be completed by the beginning of Q2 2021.
Measure 1.3.3: Providing support to e-Government users
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Percentage of services that provide support through a helpdesk |  |  | 5 (2019) |  | 65 | 0 | The period of implementation of the measure within which the indicator is specified, which implies the provision of support to e-Government users, is planned for 2021, and therefore there are no data for 2020.
Percentage of resolved help-desk user requests compared to the number of submitted requests |  |  | 80 (2019) |  | 85 | 0 | The period of implementation of the measure within which the indicator is specified, which implies the provision of support to e-Government users, is planned for 2021, and therefore there are no data for 2020.
Percentage of services with data on user satisfaction |  |  | 0 (2019) |  | 65 | 0 | The period of implementation of the measure within which the indicator is specified, which implies the provision of support to e-Government users, is planned for 2021, and therefore there are no data for 2020.
Percentage of services positively assessed by the users |  |  | 0 (2019) |  | 50 | 0 | The period of implementation of the measure within which the indicator is specified, which implies the provision of support to e-Government users, is planned for 2021, and therefore there are no data for 2020.
Percentage of users who positively assessed the e-Government services |  |  | 0 (2019) |  | 65 | 0 | The period of implementation of the measure within which the indicator is specified, which implies the provision of support to e-Government users, is planned for 2021, and therefore there are no data for 2020.
Percentage of services for which it is possible to follow case progress/status |  |  | 0 (2019) |  | 65 | 0 | The period of implementation of the measure within which the indicator is specified, which implies the provision of support to e-Government users, is planned for 2021, and therefore there are no data for 2020.
Measure 1.3.4: Affirmation of e-Government (raising awareness of civil servants and citizens about the importance of digitalisation and strengthening trust in electronic services)
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of civil servants using the e-Government infrastructure |  |  | 100 (2019) |  | 400 | 0
Number of citizens using the unified mailboxes |  |  | 0 (2019) |  | 5000 | 224000
Number of video instructions compared to the number of new electronic services, and/or IS |  |  | 1 (2019) |  | 10 | 10
Number of businesses using the unique mailboxes compared to the total number of businesses |  |  | 0 (2019) |  | 400 | 10
Number of announcements on social media accounts posted annually |  |  | 500 (2019) |  | 600 | 862
Number of announcements posted annually on the internet portals |  |  | 300 (2019) |  | 360 | 363
Number of articles in the most popular daily newspapers and weekly magazines published annually |  |  | 200 (2019) |  | 240 | 244
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.3.4.2: Development of ITE Office communication strategy to promote electronic services; | Q3 2020 –> Q4 2021 | ITE Office | Not initiated | – | . |  | COVID-19. | New completion deadline has been defined for this activity – Q4 2021.
1.3.4.3: Implementation of ITE Office communication strategy to promote electronic services. | Q4 2020 –> Q4 2021 | ITE Office | Not initiated | – | . |  | COVID-19. | New completion deadline has been defined for this activity – Q1 2021.
Measure 1.3.5: Implementing a one-stop shop
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of services which have an established one-stop shop |  |  | 0 (2019) |  | 1 | 5 | The number of services is different, because it is a pilot project. The most frequently provided services at the one-stop shop counters are in the field of social protection, property relations and services provided by public companies.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.3.5.1: Drafting a study on the methods of establishing a one-stop-shop at the national and local level with recommendations on the criteria for the selection of services it applies to; | Q4 2020 –> Q4 2021 | MPALSG | Activity was abandoned | – | . |  | No funds were provided. | A by-law regulating the establishment of a one-stop shop should be passed in Q4 2021.
1.3.5.2: Implementation of a pilot one-stop-shop for LSGUs in accordance with the recommendations of the study from activity 3.5.1. | Q4 2020 | MPALSG | In progress | 100% | Contracts on the implementation of one-stop shops were signed in 3 local government units: Paraćin, Kosjerić and Topola. So far 14 one-stop shops have been opened in RS, specifically in the following municipalities: Lazarevac, Šabac, Zitište, Smederevska Palanka, Bela Palanka, Sombor, Kruševac, Vlasotince, Užice, Gornji Milanovac, Rača, Pirot, Kuršumlija and Stara Pazova. |  | . | .
Specific objective 1.4: Open data in public administration
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of data bases available on the Open Data Portal |  |  | 250 (2019) |  | 350 | 306 | The National Open Data Portal is available at https://data.gov.rs/sr. Bodies/institutions with the largest number of data sets introduced include the City Administration of the City of Niš (35), Statistical Office of the Republic of Serbia (25), Environmental Protection Agency (23), Medicines and Medical Devices Agency of Serbia (19) and the Commissioner for Information of Public Importance and Personal Data Protection (16). The total number of data sets/resources is 306/2,194.
Number of users of the Open Data Portal |  |  | 500 (2019) |  | 800 | 1051
Measure 1.4.1: Securing the implementation of the open data legal framework
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of public administration bodies and other holders of public authority which share/publish open data on the Open Data Portal |  |  | 33 (2019) |  | 60 | 62 | Number of public administration bodies and other holders of public authority which share/publish open data on the Open Data Portal compared to the previous year has doubled. There is a growing awareness in RS of the importance of open data in institutions in order to increase transparency and accountability, as well as economic growth, because the potential of the open data market is exceptional.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.4.1.1: Establishing a special organisational unit in ITE Office for open data and the Open Data Portal with the aim of providing support to institutions to open data in a machine-readable format, to ensure the sustainability of the open data initiative; | Q1 2020 –> Q4 2021 | ITE Office | Not initiated. | – | . |  | COVID-19 pandemic. Implementation will be pushed forward. | New completion deadline has been defined for this activity – Q4 2021.
1.4.1.2: Drafting a methodology and standards for opening data with defined priority data sets. | Q4 2020 | ITE Office | Activity was abandoned | – | . |  | The activity was not implemented because no funds were provided, and due to circumstances related to the COVID-19 pandemic. | .
Measure 1.4.2: Improving the Open Data Portal
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of machine-readable datasets published on the Open Data Portal and regularly updated |  |  | 0 (2019) |  | 2400 | 2194 | Examples of the use of open data are highlighted on the central Open Data Portal of the Republic of Serbia (go to: https://data.gov.rs/sr). In order to improve transparency in the field of public finances, the citizens have access the visualisation of more than 90 budgets of cities and municipalities in RS through the platform budzeti.data.gov.rs. Open data of the Office for IT and eGovernment made available statistics on the number of citizens in self-isolation, infected with the COVID-19 virus, tested, hospitalised and deceased in the territory of the Republic of Serbia, https://covid19.data.gov.rs/
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.4.2.1: Development and publishing of guidelines and tools to raise the quality of open data; | Q3 2020 | ITE Office | Activity was abandoned | – | . |  | Activity was not implemented because no funds were provided. | .
1.4.2.2: Improving the software solution for the Open Data Portal: – Automated data downloads; – Use of tools for maintaining quality of the data sets with the aim of achieving optimum functionality; – Establishing access to records produced through the work of public administration bodies by way of an API and other models and entry of statistical data (indicators, codebooks, classifications, geospatial data, etc.). | Q4 2020 | ITE Office | Activity was abandoned | – | . |  | Activity was not implemented because no funds were provided. | .
Measure 1.4.3: Supporting the use of open data
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of organised hackathons, datathons and Open Data Weeks |  |  | 0 (2020) |  | 6 | 1 | On 2 March 2020, a conference entitled “Spark for the Future” was held in cooperation with ITE Office, UNDP and donors (https://www.ite.gov.rs/vest/4740/podaci-i-euprava -iskra-za-buducnost.php)
Number of applications and software solutions launched owing to the use of open data |  |  | 8 (2019) |  | 11 | 26 | Examples of use can be found on the Open Data Portal, at the following address: https://data.gov.rs/sr/reuses/
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.4.3.1: Analysis of the methods for including the private sector in the open data initiative; | Q2 2020 | ITE Office | Activity was abandoned | – | . |  | The activity was not implemented because no funds were provided, and due to circumstances related to the COVID-19 pandemic. | .
1.4.3.2: Providing support to civil society organisations and higher education institutions for projects based on the reuse and promotion of open data; | Q3 2020 | ITE Office | Activity was abandoned | – | . |  | The activity was not implemented because no funds were provided. | .
Measure 1.4.4: Introducing the concept of "smart city"/e-City
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Note
Number of cities that have piloted “e-City” projects |  |  | 0 (2019) |  | – | 0 | The implementation of smart cities requires significant financial investments. The goal for the end of 2022 is to have two cities in RS with pilot “smart city” projects. Donor funds were not provided in this reporting period.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.4.4.1: Create a joint platform for collecting and publishing data of relevance for economic development at the local level in cooperation with LSGUs. | Q3 2020 | Statistical Office of RS | Activity was abandoned | – | . |  | Given that the development of the platform requires close cooperation with local governments, and that this requires conducting several surveys and engagement of interviewers in all local government units, all without any funds provided, it was impossible to initiate platform development. Additional aggravating circumstance was the COVID-19 pandemic. | Under the current circumstances, there are no plans to continue the activity.