## Sve aktivnosti export_1
Annual Report on the Implementation of the 2021 Action Plan for the: |  |  |  |  | Action Plan 2021–2023 for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia
Institution responsible for coordination and reporting: |  |  |  |  | MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Public policy document elaborated by the Action Plan: |  |  |  |  | Programme for the Reform of the Local Self-Government System in the Republic of Serbia for the 2021–2025 period
Overall objective 1: Establishing a local self-government system that enables efficient and sustainable exercise of citizens’ rights to local self-government
Document proponent: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Compliance of the local self-government system with the key principles of the European Charter of Local Self-Government (Composite scale (1–5)) |  |  | 3 (2020) |  | 2–3 | 3 |  |  | –
Share of LSG expenditures in consolidated public expenditures in the Republic of Serbia (%) |  |  | 14.75 (2019) |  | 14–15 | 12
LSGU capacity to apply the principles of good governance (%) |  |  | 39 (2018) |  | 40–43 | 47 | The achieved value entered is the result of measuring whether the SCTM Index for 2021 has been met.
Availability and quality of providing the priority public services of local self-government (Composite scale (1–10)) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Specific objective 1.1: Improving the position and responsibilities of the local self-government
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Level of the European Charter of Local Self-Government ratification (Composite scale (1–5)) |  |  | 3 (2020) |  | 2–3 | 3
Average value of the Good Governance Index in selected areas: 1) accountability; 2) transparency, openness and participation (%) |  |  | 43 (2018) |  | 45 | 53 | The achieved value entered is the result of measuring whether the SCTM Index for 2021 has been met.
Share of adopted laws in relation to the total number of adopted laws which largely relate to LSG, in the preparation of which the LSGUs participated (Composite scale (1–5)) |  |  | 3 (2020) |  | 2–3 | 3 | The achieved value was entered on the basis of data submitted by the SCTM.
Measure 1.1.1: Continuing harmonisation of the legal framework of the Republic of Serbia for local self-government with the principles of the European Charter of Local Self-Government
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Amendments to the Law on Ratification of the ECLSG adopted, and level of accepting ECLSG by the RS increased (0 – No, 1 – Yes) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.1.1: Developing an ex ante assessment of the impact of continuing the ECLSG ratification on the legal framework of the Republic of Serbia | 4Q 2021 -> 1Q 2022 | MPALSG | In progress | - | The assessment is currently being prepared, and it is to be completed at the end of Q1 2022. |  | The development of the assessment has been postponed until Q1 2022, as agreed with the activity implementation partner (SCTM). | The assessment is to be completed by the end of Q1 2022.
Measure 1.1.2: Improving the electoral system and strengthening the capacity of local administration to conduct local elections
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
A new legal framework for conducting local elections adopted (0 – No, 1 – Yes) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Proportion of MEC/CEC presidents and secretaries certified to conduct local election procedures (%) |  |  | 0 (2020) |  | 0 | 0 | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.2.1: Developing an ex ante impact assessment of the new Law on Local Elections, and a simulation of its possible effects (primarily related to ensuring equal territorial representation, representation of minority communities, etc.) and organising consultations with political parties, community of experts, and CSOs. | Q3 2021 -> Q1 2023 | MPALSG | Has not commenced | - | . |  | The activity has not been implemented, and it will have to be revised because the Government has begun preparing a proposal for a new Law on Local Elections. Also given the organisational and staffing changes in the MPALSG, for a long time nobody was being appointed as the project manager who would be responsible for project implementation. Consequently, the implementation of this activity was delayed. | The activity will change to being an ex post impact assessment of application of the new Law on Local Elections. Depending on the conclusions in the assessment [report], potential additional improvements to the local elections system will be recommended..
1.1.2.2: Preparing a draft Law on Local Elections | Q4 2021 | MPALSG | Completed | - | In 2021, the draft Law on Local Elections was being drawn up. In its session on 23 November 2021, the Committee on the Judiciary, Public Administration and Local Self-Government confirmed the programme of the public hearing for the draft text of the new Law on Local Elections (hereinafter: the Bill), at the initiative of the Ministry of Public Administration and Local Self-Government in accordance with Article 41(3) of the Rules of Procedure of the Government. The public hearing of the Bill was conducted in accordance with the adopted public hearing programme, from 24 November to 13 December 2021. The Bill was officially available on the website of the Ministry of Public Administration and Local Self-Government. |  | . | .
1.1.2.3: Submitting the draft Law on Local Elections to Government for review and approval of the legislative proposal (Bill) | Q3 2021 | MPALSG | Completed | - | During the public hearing of the draft Law on Local Elections, proposals and suggestions from associations and citizens were being received. After the public hearing, opinions of the state administration bodies were collected during the month of December which were then submitted to the Government for review and approval in the first half of January. At the Government session held on 17 January 2022, the Bill was confirmed and then submitted to the National Assembly of the Republic of Serbia for decision. |  | . | .
Measure 1.1.3: Improving the legal framework and procedures for direct participation of citizens in local self-government management
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
A new legal framework for conducting referendum and people’s initiative adopted (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 1 | 1 | Amendments to the Law on Referendum and People's Initiative (The Official Gazette of the Republic of Serbia, No. 119/21)
Share of towns, municipalities, and urban municipalities in the total number of towns, municipalities, and urban municipalities whose employees are trained to apply the new legal framework in the field of referendum and people’s initiative (%) |  |  | 0 (2020) |  | 0 | 0 | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.3.1: Preparing a draft Law on Referendum and People’s Initiative, and submitting it to the Government for approving the legislative proposal (Bill) | Q2 2021 | MPALSG | Completed | - | In 2021, the draft Law on Referendum and People’s Initiative was drawn up. The public hearing about the draft Law was conducted between 8 July and 29 July, in accordance with the public hearing programme previously adopted by the Committee on the Judiciary, Public Administration and Local Self-Government. In the course of the public hearing, proposals and suggestions for the draft Law were being received from associations and citizens. Once the public hearing was over, opinions on the draft Law of the state administration bodies as well as the Venice Commission were collected, so that the [consolidated text of the] draft Law could be submitted to the Government for review and approval. In its session on 9 November 2021, the Government reviewed and approved the Bill. The Law on Referendum and People’s Initiative (The Official Gazette of the Republic of Serbia, No. 111/21) was adopted at the end of 2021. Following the adoption, Amendments to the Law on Referendum and People's Initiative were passed (The Official Gazette of the Republic of Serbia, No. 119/21). |  | . | .
1.1.3.2: Preparing a guide/handbook for conducting a referendum and people’s initiative (with forms of legal acts and documents to be used) | Q4 2021 -> Q4 2022 | MPALSG | In progress | 34.37% | A draft Guide for Conducting a Referendum and a People's Initiative was developed. . |  | The final version of the Guide for Conducting a Referendum and a People's Initiative was completed following the referendum on 16 January 2022, so that it reflects the experiences of the process and aligns with the new version of the Law. Also, in light of the organisational and staffing changes in the MPALSG, for a long time nobody was being appointed as the project manager who would be responsible for project implementation. Consequently, the implementation of this activity has been delayed. | The procedure of appointing a new manager on the project is on-going. Once the procedure is completed, it will be possible to start implementing the project activities according to the timeline.
Measure 1.1.4: Improving the participation of local self-government in the process of developing national regulations and public policies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Improved legal framework towards greater participation of local authorities in the process of preparation of public policies and general acts governing local self-government issues (0 – No, 1 – Yes) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Share of laws related to LSGUs on which information was submitted through the SCTM system for informing the LSG, in relation to the total number of laws related to LSGUs (%) |  |  | 65 (2020) |  | 70 | 95
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.4.2: Continually and regularly informing the local authorities about the adopted amendments to the legal framework (Law Alert system of the SCTM) | Q4 2023 | MPALSG | In progress | - | By the end of 2021, LSGUs were informed through the Law Alert service in a succinct manner about 16 of the 17 laws largely (95%) concerning LSGs which were adopted that year. |  | . | .
Measure 1.1.5: Further development of local self-government capacity for applying the principles of good governance
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Number of local officers trained to apply the principles of good governance (cumulative) (Number) |  |  | 831 (2020) |  | 1200 | 1350
Percentage of the total number of towns, municipalities and urban municipalities which have adopted the new SCTM Code of Ethics (%) |  |  | 7 (2020) |  | 10 | 16.5
Number of towns, municipalities and urban municipalities which have received an award for applying the principles of good governance (cumulative) (Number) |  |  | 8 (2020) |  | 12 | 12
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.5.1: Providing capacity-building support packages for improving administrative efficiency and effectiveness, as well as a package for enhancing anti-corruption policies at the local level | Q4 2021 | MPALSG | Completed | 100% | The SCTM began providing packages of support to 10 LSGUs in improving administrative efficiency and effectiveness in October 2020, and finished in December 2021. The support packages included advisory support in the drafting of internal acts for the purpose of improving efficiency, consolidating the legal practice, informing citizens about the changes to regulations as well as introducing models of administrative procedures. At the same time, support was given in establishing one-stop shops, developing capacity analysis and formulating recommendations on how to meet legal obligations related to e-Government and how to conduct activities in situations caused by the pandemic — all towards sustainable business continuity of the LSGUs and them being able to conduct administrative procedures. As part of these support packages, 20 general and 50 special acts were adopted towards improving the administrative procedure. Out of those, 24 related to the establishment of one- stop shops for certain administrative services. 36 training sessions were held; total attendance: 383 representatives of LSGUs. Also, 9 anti-corruption support packages were provided in 2021, and 2 additional support packages were initiated — these are expected to go on until mid-February 2022. Through these packages, if necessary, the LSGUs receive support in drafting and adopting entirely new Local Anti-Corruption Plan (LAP) or revising an existing one, and in forming a body to monitor the LAP application in line with the Chapter 23 Action Plan and the model developed by the Anti-Corruption Agency with the SCTM's support. Additionally, these packages include support in the implementation of LAPs for 5–7 selected risk areas, in the form of passing acts which are developed based on the SCTM models and giving training to employees who would be applying the acts [as part of their work] in the local self-government. In 2021, as a result of these support packages, 3 LAPs, and 41 general and 11 individual acts were adopted – all of which reduce the risk of corruption. There were 64 training sessions on applying the acts, and a total of 396 attendees. |  | . | .
1.1.5.2: Coordinating the implementation of the training programme on good governance from the Sectoral Programme of Continuous Professional Development of employees in LSGUs | Q4 2023 | NAPA | In progress | 100% | During 2021, the SCTM implemented several accredited training session on good governance from the Sectoral Programme of Continuous Professional Development of employees in LSGUs: four one-day webinars entitled Exercising the right of access to public information, four one-day webinars entitled Electronic Government, three 2-day regional training sessions plus two 2-day webinars about Introducing and Implementing the Principle of Good Governance in the work of Local Self-Government Units, four webinars entitled Cooperation with Civil Society Organisations and Funding Projects of Public Interest Implemented by Associations, as well as one 7-day online training entitled Good Governance at the Local Level. A total of 519 (369 women) representatives of units of local self-government who attended the sessions were entitled to a certificate. . |  | . | .
1.1.5.3: Promoting the Code of Ethics of local self-government officials (online conferences, organising workshops, distributing a guide and posters with quotes from the Code of Ethics, etc.) | Q4 2021 -> Q4 2022 | MPALSG | In progress | 100% | On 21 March, the SCTM in cooperation with the OSCE Mission to Serbia, and with the participation of the MPALSG and the Council of Europe Congress of Local and Regional Authorities, held an online conference entitled Code of Ethics for Local Self-Government Officials. Over 150 high representatives of towns and municipalities across Serbia were in attendance. The first three editions of the Guide to the Code of Ethics for Local self-Government Officials (total print-runs: 25,000 copies) were distributed to 120 LSGUs, towns and municipalities. They were distributed with posters with quotes from the Code of Ethics in the Serbian language and the minority languages in official use in specific LSGUs. Distribution to the remaining LSGUs, towns and municipalities, as well as the printing of the fourth edition of the Guide will take place in 2022. |  | Due to the pandemic, presentations of the Code of Ethics for Local Self-Government regionally were postponed until 2022. | To complete all the planned activities, the pandemic permitting.
1.1.5.4: Е-training for officials on the application of the Code of Ethics of local self-government officials | Q4 2021 | MPALSG | Completed | 100% | From 22 September to 3 November, the SCTM held an online training on the Code of Ethics for Local Self-Government Officials, which 130 local officials from 52 LSGUs and towns and municipalities completed successfully. |  | . | .
1.1.5.5: Pilot–implementation of the training programme for members of the council responsible for monitoring the application of the Code of Ethics of local self-government officials | Q4 2021 -> Q4 2022 | MPALSG | In progress | - | Preparation for the training are on-going, whereas the actual delivery will depend on the epidemiological situation. |  | Due to the epidemiological situation in autumn 2021, this activity was moved to 2022. | To complete all the planned activities, the pandemic permitting.
1.1.5.6: Developing the second analysis of the local self-government performance assessment pertaining to good governance, based on the SCTM Good Governance Index (on a sample of 60 LSGUs) | Q4 2021 | MPALSG | Completed | 100% | Following the 2018 initial estimate of the LSGUs' capacities to apply the principle of good governance, the SCTM conducted a second analysis of the local self-government performance assessment pertaining to good governance ,the purpose of which was to measure the progress towns and municipalities had made in the field of good governance during the 4-year period. The analysis was done on a sample of 60 LSGUs, based on the SCTM Good Governance Index, between October and December 2021. The results will help separate procedures and processes with an established good practice in applying the principles of accountability, transparency, participation, efficiency, effectiveness, equality, and corruption prevention, from those procedures which require additional work at the LSGU level. . |  | . | .
1.1.5.8: Organising a public call for annual awards for the best municipal/town administration in applying the principle of good governance | Q4 2023 | MPALSG | In progress | 100% | As part of the Programme of Support to the Development and Functioning of the Local Self-Government System (MPALSGU Budget Fund), a public call for the annual award for the best municipal/town(city) administration was announced. Winners in each of the four categories (areas) were awarded with 2,300,000.00 dinars. The Efficiency and Effectiveness Award went to the Municipality of Knić, the Transparency and Public Participation in the Work of the Local Self-Government Award went to the Municipality of Veliko Gradište, the Accountability and Rule of Law Award went to the City of Kragujevac, and the Equality and Anti-discrimination Award went to the City of Kruševac. By the Decision on the Allocation of the Budget Fund for the Annual 2020 Award for the Best Municipal/City Administration (The Official Gazette of the Republic of Serbia, No. 23/21), a total of 9,200,000.00 dinars was awarded. |  | . | .
1.1.5.9: Implementing the package of support to local self-government (for developing / revising and implementing multiannual action plans for the implementation of participatory process for making decisions about spending LSG’s own revenues; support to local communities in applying participatory mechanisms being developed and in applying their own development programmes and financial plans) | Q4 2023 | MPALSG | In progress | - | The programme is at the earliest stage of implementation. At the end of 2021, a Memorandum of Understanding between the Government of the Republic of Serbia and the Swiss Embassy was prepared and signed. A public call for the provision of LSGU-support package was published, which would help LSGUs improve in the area of citizen participation in the decision-making process at the local level. |  | Minor delays in the preparatory work for the project implementation as well as the postponed signing of the Memorandum of Understanding between the Government of the Republic of Serbia and the Swiss Embassy (November 2021) which was the condition for launching the project. | Selecting partner LSGUs, meeting with the selected LSGUs to set the plan and the dynamic of the technical support to be provided. Continuing the implementation of project activities in line with the project timeline.
Measure 1.1.6: Improvement of vertical and horizontal supervision in performing original and entrusted tasks of LSGUs
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Improved legal framework governing the supervisory function of the municipal/town (city) assembly (reporting by executive bodies to the assembly, councillor issues – interpellations, strengthening the position of working bodies – proposing acts, etc.) (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 1 | 0 | The indicator was not met because the plan was to initiate a more comprehensive process of amending the Law on Local Self-Government in 2022, which would encompass the topics in question.
Improved legal framework governing the functioning of administrative districts (strengthening the coordination role of administrative districts and their supervisory function regarding the execution of local self-government activities) (0 – No, 1 – Yes) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.6.1: Analysis of the possibilities for redefining decision-making competencies in the second instance administrative procedure in the field of LSGUs’ original tasks, and for the introduction of a special local authority or the establishment of intermunicipal bodies (primarily for fewer LSGUs) for this purpose | Q4 2021 -> Q4 2022 | MPALSG | Has not commenced | - | It has been moved to 2022. . |  | Given the organisational and staffing changes in the MPALSG, for a long time nobody was being appointed as the project manager who would be responsible for project implementation. Consequently, the implementation of this activity has been delayed. | The procedure of appointing a new manager on the project is on-going. Once the procedure is completed, it will be possible to start implementing the project activities according to the timeline.
Specific objective 1.2: Improving the local self-government financing system
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Share of LSG tax revenues in the total tax revenues in the Republic of Serbia (%) |  |  | 10.12 (2020) |  | 10.35–10.4 | 10.1
Share of capital expenditures in total expenditures of local self-government (%) |  |  | 15.54 (2019) |  | 15–16 | 17.3
Share of LSGUs which have adopted a medium-term plan (%) |  |  | 0 (2020) |  | 0 | 0
Measure 1.2.1: Reform of the local self-government financing system and support for the development of fiscal decentralisation
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Systemic legal framework reformed (0 – No, 1 – Yes) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned..
Share of property tax revenues in total budget revenues of the LSG (%) |  |  | 15.8 (2019) |  | 16.2–16.1 | 16.1 | The share of realised property tax revenues includes transfers from other levels of the government
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.1.1: Initiating and continuing the work of the Commission for Financing Local Self-Government within its purview as defined in the Law on Financing Local Self-Government | Q3 2021 -> Q4 2022 | MoF | In progress | - | The Commission begun working during this reporting period. It convened for the first time on 18 November 2021, when it adopted its own Rules of Procedure and agreed on the tasks ahead. . |  | There was a delay in forming the Commission because not all ministries had timely proposed their candidate members. | [For the Commission] to develop the Commission Work Plan and to perform within its purview, as prescribed under the Law on Local Self-Government Financing.
1.2.1.2: Improving the financing system in line with the findings of the local self-government financing system analysis (application and effects of the systemic legal framework, LSGU revenues/income and expenditures/expenses structure; planning and generation of revenues, and execution of expenditure and expenses; LSGUs’ aligning with the MoF instructions) | Q2 2022 | MoF | In progress | - | The structures of local government revenues and expenditures, as well as the criteria for financing, are being analysed. |  | . | To present the analysis findings to the Commission for Financing Local Self-Government so that it may suggest changes to the way financing is done.
1.2.1.3: Supporting further capacity building of local tax administrations (LTAs) (inter-connecting/networking and knowledge sharing between LTAs, implementing annual training programmes and workshops, advisory support, direct technical assistance to specific LSGUs, etc.) | Q4 2023 | MoF | In progress | 81.54% | Two workshops on the given topic were held for employees of local tax administrations. I – 39 LSGUs, 80 participants, II – 35 LSGUs, 73 participants, Technical support. |  | The MoU between the Government of the Republic of Serbia and the Swiss Embassy was signed in November 2021 which is when the activities could be and were started. Part of the planned activities and funds were carried over to 2022 (5.3 million RDS were planned, 4.35 million RSD were spent). | To develop a 2022 plan of support to LSGUs for further capacity building of local tax administrations.
Measure 1.2.2: Support to LSGUs to improve the budget planning process
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Share of LSGUs which have aligned the medium-term plan with the programme budget in the total number of LSGUs which have adopted the medium-term plan (%) |  |  | 0 (2020) |  | 0 | 0 | There were no adopted LSGU medium-term plans in the 2021–2024 planning cycle.
Average capacity of LSGUs to apply the principles of good governance in accordance with the Good Governance Index in LSGUs in the field of accountability (%) |  |  | 45 (2018) |  | 55 | 48 | The achieved value entered is the result of measuring whether the SCTM Index for 2021 has been met. The value achieved in 2021 is below the target value owing to LSGUs' obligations prescribed under the Law on the Planning System which have affected how indicators related to LSGU planning are formulated, making those indicators more difficult to meet compared to the indicators from 2018.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.2.1: Establishing and providing a general support to LSGs for the development of medium-term plans (advisory support to all LSGs, developing models and instructions, and information exchange with all LSGs) | Q4 2023 | PPS | In progress | 54% | The tasks of providing general and advisory support to LSGUs in developing their medium-term plans (MTPs) has been added to the PPP's scope of work. Providing this support in 2021 meant providing answers to LSGUs, which had adopted their development plans, about the process of developing their MTPs. In cooperation with NAPA, one training in medium-term planning was held, which was also open to LSGUs representatives (....). The SCTM also organised four other training sessions which were accredited by NAPA. As part of the EU Exchange 6 Programme, a series of webinars on how to prepare the 2022 budget was held in October 2021 for all LSGU. One of the webinars covered specially the topic of MTP development. |  | SCTM was to organise eight accredited training sessions in 2021, but fewer were held in the end due to the pandemic. | Support to LSGs in developing MTPs will continue to be provided. Also, the plan is to draft the Handbook for Developing Medium-Term Plans at the Local Level.
1.2.2.2: Implementing 25 support packages to municipalities for developing LSGU medium-term plans | Q4 2023 | PPS | In progress | 92% | In 2021, there was continued support for the development of medium-term plans in 5 LSGUs which were the beneficiaries of direct technical support under a project funded by SlovakAid, and implemented by the UNDP and the SCTM in coordination with the PPS. The 5 LSGUs were: Bački Petrovac, Mali Zvornik, Petrovac na Mlavi, Sjenica, and Kuršumlija. As part of that support, workshops on MTP-development were held for each of the named LSGUs. By the end of 2021, complete MTPs were developed for Bački Petrovac, Kuršumlija, and Petrovac na Mlavi, and MTP drafts were developed for Sjenica and Mali Zvornik. |  | . | Direct support to 10 new LSGUs to develop their MTPs will be continued under the EU Exchange 6 Project. A public call [for applications] for support in developing 10 LSGUs' MTPs will be announced in Q1 2022. Support to another 10 LSGUs is planned for 2023. The exact allocation of the support will depend on the number of LSGUs interested in receiving it, i.e. their dynamic of adopting own development plans.
1.2.2.3: Implementing 20 support packages to municipalities for preparing capital budget | Q4 2023 | MoF | Has not commenced | - | Direct support to LSGUs for preparing capital budget, under the EU Exchange 6 Project, has not been initiated yet. The public call [for applications for direct support] is currently being prepared, but once completed, the support will be provided to the LSGUs selected in that procedure. |  | . | Support for 10 LSGUs will be available through this public call. But there will be another public call at the start of 2023, during the second half the Programme implementation, which will be for support to another 10 LSGUs for preparing their capital budgets (depending on the LSGUs' interest, it may be that fewer LSGUs than the average 10 receive support in the first round of public calls but more in the second round).
1.2.2.4: Annual updating, accreditation, and coordination of the implementation of the professional development programme for LSG employees, focused on programme and capital budgeting and their alignment with the local development planning (developing an LSGU’s medium-term plan and linking it to the LSGU’s programme and capital budget), gender and participatory budgeting | Q4 2023 | NAPA | In progress | 100% | Over the summer months of 2021, at the invitation of colleagues from NAPA and in cooperation with them, the SCTM reviewed the 2022 plan for the programme of professional development of LSGU employees working in the domain of programme and capital budgeting, and medium-term planning. Compared to the 2021 programme, there were no key changes to the agenda and the content of the training in programme and capital budgeting. When it comes to the implementation of the professional development programme in LSGUs, as per the adopted 2021 programme, a series of accredited training sessions on medium-term planning in LSGUs (4 webinars to be exact) were held in early November, as part of the EU Exchange 6 Project. The main objective of those webinars was to get the attendees familiar with the process of medium-term planning and the implementation of LSGU medium-term plans in line with the laws regulating the planning and budget system. Other objectives included learning how to link public policies to the LSGUs medium-term expenditure framework. The webinars were intended for employees in LSGUs who perform tasks related to development planning and financial planning and budgeting as well as any other tasks relevant for managing public policies within the LSG's purview. A total of 191 participants from 66 LSGUs and city municipalities attended the webinars. There were also other accredited training sessions held, as part of a support project for 10 LSGUs to develop their medium-term plans. This project is funded by SlovakAid/UNDP but implemented by the SCTM. The sessions focused on a given topic, depending on the activity in question (for LSGUs which are [project] beneficiaries only). Specifically, one accredited training (in a form of a webinar) entitled Medium-term Planning in Local Self-Government was held in March 2021. Then in June 2021, 2 more accredited training sessions were held: a 2-day one entitled Local Self-Government Programme Budget, and a full-day one entitled Capital Budgeting in Units of Local Self-Government. |  | . | .
1.2.2.5: Developing annual reviews of the alignment of LSGUs’ programme budgets with their medium-terms plans | Q4 2023 | PPS | Has not commenced | - | . |  | The development of the first annual review in accordance with the subject activity is planned for 2022. At the moment this present Report was drafted, the SCTM begun collecting programme budget submissions for 2022 from all LSGUs, which will serve as a basis for the first annual review (with mapped medium-term plans of LSGUs) which itself is planned for later in the year (2022). | .
Measure 1.2.3: Improving transparency of the local finance system
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
A public electronic display has been established for displaying and monitoring the state of local budgets (0 – No, 1 – Yes) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned..
Share of LSGs which have publicly available budget portals (%) |  |  | 1.7 (2020) |  | 12 | 8.82 | The target value for 2021 has not been fully achieved but the expectation is that it will be by Q2 2022. When the target value was being projected, the expectation was that by the end of 2021 all LSGU beneficiaries of the current project (implemented by UNDP and SCTM but funded by SIDA) would have public budget portals — this project is, in fact, supporting the launch of this application, i.e. the budget portals. Due to the COVID-19 pandemic, the project duration has been extended into Q1 2022. Accordingly, about one half of the beneficiary LSGUs had launched budget portals by the end of 2021. The remaining ones are expected to do so in early 2022, when the target value of the subject indicator will be achieved.
Share of LSGs which publish monthly reports (or cumulative monthly reports) on budget execution on their website (%) |  |  | 9.4 (2020) |  | 12 | 7.6 | Data from the Transparency Serbia's Local Transparency Index (LTI) suggests a 7.6% value for 2021 (https://www.transparentnost.org.rs/index.php/sr/istraivanja-o-korupciji/lti). The data are based on the 2021 report which, as a source, suggests a lower value than in 2020 (baseline value). In the explanation of the LTI results, it was said that a lower value in a budget category generally had to do with the pandemic, meaning that the administration was slower, and the fact that LSGUs faced challenges at the end of 2020 and in early 2021, when their employees were either on sick leave or were unable to collect data because they were working remotely from home.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.3.1: Forming a public electronic display of the local authorities’ budget (planning and the execution of each LSG’s budget revenues and expenditure) | Q4 2023 | MoF | Has not commenced | - | . |  | . | .
1.2.3.2: Developing 40 LSG budget portals | Q4 2023 | MoF | In progress | 100% | 2021 marked a continuation of activities under phase 2 of an on-going project which is funded by SIDA but implemented by the UNDP and the SCTM. In the first phase of the project, 10 LSGUs had been supported. Following a public call in 2019, the decision was made to support 21 LSGUs. The 2021 support covered two additional LSGUs as a result of cooperation with the Property Tax Reform Programme (funded by the Swiss Confederation, but implemented by Helvetas), making the grand total of 23 LSGUs. During the reporting period, particularly Q1 and Q2 2021, reports on the budget process were finalised and consolidated [in cooperation] with the representatives of the finance departments of the project-beneficiary LSGUs. Afterwards, the budget portal software was installed and updated in 33 local self-governments (23 new LSGUs supported by the project + 10 LSGUs from the pilot phase (2016–2018 period)), and procurement and delivery of computer equipment for 21 beneficiary LSGUs completed. Since July 2021, the focus has been on field visits and training IT administrators, finance departments and other competent representatives to use the budget portal. Then in November and December 2021, board members of the beneficiary LSGUs were given presentations on the(ir) budget portal(s). The budget portals are to be fully operational and their effectiveness will start being monitored in early 2022. |  | . | To launch the EU Exchange 6 project support for launching budget portals by mid-2022, by which time the first round of package support (for capital budgeting, development plans, and medium-term planning) will have ended. The possibility of launching budget portals will primarily be offered to the LSGUs which had been selected through the earlier public call for [receiving support in] capital budgeting. That means that there will be no separate or additional public call for budget portals.
Measure 1.2.4: Intensive development of the public internal financial control system (PIFC) at the local level
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
% of certified internal auditors in local self-government units (%) |  |  | 64 (2019) |  | 63 | - | The Central Harmonisation Unit still has no data for 2021. Data is processed for the 2021 Consolidated Annual Report on the PIFC on the basis of individual BPFs' reports submitted.
% of LSGUs included in the system of reporting on their FMC systems (%) |  |  | 55.86 (2019) |  | 75 | - | The Central Harmonisation Unit still has no data for 2021. Data is processed for the 2021 Consolidated Annual Report on the PIFC on the basis of individual BPFs' reports submitted.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.4.1: Supporting the establishment/advancement of an adequate PIFC system in 8 indirect budget users (IBUs) from 3 LSGUs (training, direct technical support onsite, mentoring, and networking) as part of creating a system of managerial accountability at the LSGU level | Q1 2022 | Selected LSGUs | In progress | 100% | Work on developing supervision over the IBUs' work continued. Business processes were defined, and business process mapping for 8 IBUs in 3 LSGUs was completed. For those IBUs, all the system documentation was prepared. The project [team] held two regional conferences Supervision over the work of IBUs for a total of 65 participants. IBUs Annual Work Programmes were developed on the basis of a new model in 12 IBUs in 3 LSGU. In cooperation with the CHU, the final draft of the Manual for establishing a FIA system with IBUs, which includes a practical Excel tool, was completed. |  | . | .
1.2.4.2: Creating an online video training for IA users (video tutorials, text materials, testing questions) in cooperation with CHU and NAPA, which will become part of NAPA’s curriculum and platform for training employees and managers in state administration and LSGUs | Q4 2022 | MoF | In progress | 100% | Over the summer months of 2021, at the invitation of colleagues from NAPA and the Central Harmonisation Unit (CHU) of the Ministry of Finance, and in cooperation with them, the SCTM reviewed the 2022 plan for the programme of professional development of LSGU employees who work in the PIFC domain. A new one-day support programme for financial management and control (FMC) in LSGUs was agreed and developed within the 2022 Professional Development Programme. Consultations with the CHU were held throughout the year, as part of the overall process of developing the Programme for Reform of the Local Self-Government System. The CHU is responsible for implementing the formal internal audit (IA) training programme, but the general instructions for LSGUs (to be delivered in cooperation with the SCTM) will be planned once the changes to the Handbook for Internal Audit Standards and Criteria (i.e. IA certification) have been consolidated. The first iteration of these changes was the subject of review and comments in December 2021, when the specialised unit of the SCTM (1) categorised the comments and suggestions received from LSGUs via the various networks for IA, local finance, and administration, and (2) took part in the work dialogue with the MoF. CHU input: The draft versions of the online training lessons have been delivered to the CHU, and they are currently being perfected. It is expected that the final lessons, which are to become part of the NAPA curriculum and platform for the training of employees and managers in the civil service and LSGUs, will be developed by the end of January 2022. |  | . | Considering the scope of proposed modifications (for users at all levels of administration), to continue working on the handbooks in the first half of 2022. The SCTM is actively providing advisory support to LSGUs by responding to their IA-related enquiries, whereas cooperation including the monitoring of direct support to selected LSGUs are continuing within the RELOF2 Project supported by the Swiss Confederation.
1.2.4.3: Introducing/advancing the IA function in 5 LSGUs (training, direct technical support onsite, mentoring) and connecting internal auditors at the local level through support in improving risk control | Q2 2022 | Selected LSGUs | In progress | 100% | The IA function has been advanced in 4 LSGUs. Support to internal auditors was provided by way of mentoring and direct onsite support. During this process of supporting LSGUs in advancing their IA function, internal auditors benefitted from shared professional development training sessions which created opportunities for networking and further sharing of experiences. In order to contribute to improving the system as much as possible and through a very successful cooperation with the RELOF2 Project [team] and joint support, the CHU mentors helped internal auditors in the process of [obtaining] certifications. |  | . | .
1.2.4.4: Improving the capacity to establish/advance an adequate PIFC system in 14 LSGUs (training, direct technical support onsite, mentoring, and networking) | Q4 2022 | Selected LSGUs | In progress | 100% | The RELOF2 Project has supported 13 LSGUs in the process of setting up/advancing the FIC system (one LSGU voluntary had left the project). In 2021, 2 training sessions were held in all LSGUs: 1) Introduction to setting up an FIC system (total of 76 attendees), and 2) Risk management (total of 129 attendees). Business processes were defined, lists of business processes were made, and business processed mapped. The remaining steps in setting up/advancing the FIC system are planned for 2022. |  | . | .
1.2.4.5: Implementing the previously developed model of joint internal audit in a single LSGU; drafting a report on the model implementation, with lessons learnt and an improved model of joint internal audit with attachments/appendices which other LSGUs can apply | Q4 2022 | Selected LSGUs | In progress | 100% | Implementation of the model of joint internal audit is in progress. Due to the unforeseen consequences of the pandemic (staff absences) as well as the organisational changes within the municipal administration, the original deadlines have been moved forward. Despite these challenges, a [cooperation] agreement was drafted, then approved by the CHU, and finally signed by LSGUs and public companies. This activity is expected to complete mid-2022. |  | . | .
1.2.4.6: Improving the capacity of the local self-government to establish and apply the FIC and the PIFC (developing a practical Manual for establishing a FIA system with IBUs at the local level, organising two two-day events for women presidents of municipalities/lady mayors about the introduction of FIC and IA, organising a conference on the importance of PIFC as an integral part of local strategic and operations processes) | Q4 2022 | Selected LSGUs | In progress | 100% | The FIC system has been set up in 3 LSGUs (institutes for culture, sports, libraries, and preschools). Based on that experience, it was possible to develop a practical guide on how to set up a FIC system with IBUs at the local level using FIC tools, which included a proposal for defining the business processes for all local IBUs, expect schools. At the end of 2021, a pilot project for setting up a FIC system in schools was launched. The expected outcomes of this pilot project for 2022 are [1] that primary and secondary schools in 2 LSGUs would have a running FIC system, and [2] a developed Practical guide for setting up a FIC system in schools (primary and secondary) using FIC tools, with proposed businesses processes and revised video lessons for the NAPA platform. The other activities have been postponed until Q1 2022 when it could make more sense to hold them given the legal deadline for FIC-system reporting. The conference on the importance of the PIFC has been scheduled for 1 March 2022, and two 2-day events about introducing FIC and IA, intended for women presidents of municipalities/lady mayors, were made into a single event now planed for early March 2022. Activities 2.4.1., 2.4.2., 2.4.3., 2.4.4., 2.4.5., 2.4.6. are being implemented with donor support: (SECO–RELOF2). Activities 2.4.7. and 2.4.8. fall under the EU Exchange 6–SCTM project, and are yet to be implemented because the project is in its initial phase. |  | . | .
1.2.4.7: Establishing and/or further developing the functions of internal audit, financial management and control, and managerial accountability at the local level, with LSGUs reporting on the PIFC (advisory support, training, (inter-)connecting the LSG) | Q4 2023 | Selected LSGUs | Has not commenced | - | Activities 2.4.7. and 2.4.8. fall under the EU Exchange 6–SCTM project, and are yet to be implemented because the project is in its initial phase. SCTM input: Over the summer months of 2021, at the invitation of colleagues from NAPA and the Central Harmonisation Unit (CHU) of the Ministry of Finance, and in cooperation with them, the SCTM reviewed the 2022 plan for the programme of professional development of LSGU employees who work in the PIFC domain. A new one-day support programme for financial management and control (FMC) in LSGUs was agreed and developed within the 2022 Professional Development Programme. Consultations with the CHU were held throughout the year, as part of the overall process of developing the Programme for Reform of the Local Self-Government System. The CHU is responsible for implementing the formal internal audit (IA) training programme, but the general instructions for LSGUs (to be delivered in cooperation with the SCTM) will be planned once the changes to the Handbook for Internal Audit Standards and Criteria (i.e. IA certification) have been consolidated. The first iteration of these changes was the subject of review and comments in December 2021, when the specialised unit of the SCTM (1) categorised the comments and suggestions received from LSGUs via the various networks for IA, local finance, and administration, and (2) took part in the work dialogue with the MoF. Considering the scope of proposed modifications (for users at all levels of administration), the work on the handbooks will continue in the first half of 2022. The SCTM is actively providing advisory support to LSGUs by responding to their IA-related enquiries, whereas cooperation including the monitoring of direct support to selected LSGUs are continuing within the RELOF2 Project supported by the Swiss Confederation. |  |  | .
1.2.4.8: Direct support to LSGUs for establishing and/or further developing the functions of internal audit and financial management and control. | Q4 2023 | Selected LSGUs | Has not commenced | - | Activities 2.4.7. and 2.4.8. fall under the EU Exchange 6–SCTM project, and are yet to be implemented because the project is in its initial phase. |  | . | .
Specific objective 1.3: Improved organisation and capacities of local self-government
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
LSGU capacity for management of human resources in the local government (%) |  |  | 51 (2020) |  | 53–56 | 59.3 | The last survey was conducted in Q2 2021, using the SCTM's HRM questionnaire. The survey was done on a sample of 70 LSGUs.
Share of LSGUs which have established inter-municipal cooperation in the total number of LSGUs (%) |  |  | 27 (2020) |  | 31 | 36
Measure 1.3.1: Improving the human resource management function in local government
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
LSGU capacity for human resource management in local government (average value of the SCTM index for HRM in selected areas: organisation and planning of human resources; filling vacancies; employee evaluation, disciplinary responsibility and appeal procedure; communication, ethics, values and culture of the organisation) (Index–composite indicators) |  |  | 58 (2020) |  | 60 | 63.7
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.1.1: Support the building of overall capacities of LSGUs for human resource management (implementing technical support to LSGUs in human resource management, building capacities for the application of the new legal framework for local officers’ salaries, support packages to LSGUs, organisational transformation in 15 LSGUs) | Q2 2022 -> Q4 2023 | MPALSG | In progress | 30% | In 2021, the SCTM answered over 140 questions about human resource management, submitted by city and municipal [administrations], and it received no requests for support. Fifteen LSGUs were selected to receive organisational municipal support packages (OMSP) to help improve their administration in a functional and organisational sense. A functional and organisational analysis was conducted in all 15 LSGUs and reports on the findings were submitted. Also, action plans for the implementation of recommendations for improving the functioning and the organisation of the LSG were developed. In December 2021, all 15 LSGs submitted their project proposals for receiving the Council of Europe OMSP grants. Between May and July 2021, several 3-day Train-the-Trainer training sessions for HRM officers were held. There were also seven regional training sessions which 76 participants from 57 LSGs attended. With the application of the Law on Salaries of Employees in [APs and] LSGUs postponed until 2025, no activities on this matter were held. |  | The Human Resource Management in Local Self-Government – phase 2 Project has been extended until June 2022. Accordingly, the awarding of OMSP grants by the Council of Europe was moved to early 2022 (originally, it was to be done in 2021). Project proposals are under evaluation at the moment. The total allocated funds to be given as OMSP grants are €450,000 (≈RSD 52,875,000). With the application of the Law on Salaries of Employees in [APs and] LSGUs postponed until 2025, no activities on this matter were held. | To award the grants and perform monitoring by May 2022. To provide advisory support continuously to LSGs throughout 2022, as planned.
Measure 1.3.2: Improving the process of professional development of employees in LSGUs
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
LSGU capacity for professional development in local government (average value of the SCTM index for HRM in selected areas: professional development and training of employees) (Index–composite indicators ) |  |  | 30 (2020) |  | 45 | 47
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.2.1: Organising and funding the implementation of special professional development programmes and training programme from the Sectoral Programme of Continuous Professional Development in at least 50 LSGUs | Q4 2021 -> Q2 2022 | MPALSG | In progress | 100% | In 2021, the SCTM continued providing technical support for the development of 2022 Professional Development Programmes (PDP), through the Human Resource Management in LSGs – phase 2 Project which is implemented by the Council of Europe and the SCTM in cooperation with the MPALSG. All 42 municipalities which had prepared PDPs have accepted to continue receiving technical support in 2021 for the development of a special programme for 2022. Out of the total number of supported LSGUs, 41 have completed the full round of preparation of the 2022 special programmes, whereas 26 LSGUs published a call for the implementation of the 2021 special programme. In addition, the Council of Europe had approved 24 grants through the Project, which would support the implementation of the 2021 special programmes. Of the 24 awarded grants, 20 LSGUs have successfully completed all their activities as per their project proposals. Through this Project, a total of 15 webinars were held from the Sectoral Programme of Continuous Professional Development of employees in LSGUs who perform inspection supervision tasks (the line ministries of sports, education, and construction, each had 5 webinars per field). |  | The Human Resource Management in LSGs – phase 2 Project was extended until June 2022. The Ministry of Education, Science and Technological Development has written to the Council of Europe requesting 5 additional webinars. Given the approved Project extension and the request for webinars, the implementation of the Sectoral special programmes by the Council of Europe has been extended until Q2 2022. | By May 2022, to conduct the additional training in education inspection.
1.3.2.11: Supporting LSGU bodies in the process of assessing the needs for professional development, development, designing and implementation of special training programmes in LSGU bodies and of the annual plan of professional development of employees in LSGU bodies | Q4 2021 | NAPA | Completed | - | Professional support has been given to [LSGU] bodies so that they could conduct an assessment of the organisational needs for professional development of employees, by means of consultations on the needs assessment, developing and posting an online survey to help identify employees' individual needs, as well as data processing. Professional support has been given to [LSGU] bodies in preparing proposals of their special programme of professional development. on 16 June 2021, NAPA held a webinar for 21 participants on how to develop the special programmes. The target group were NAPA contact persons/officers who in their place of work take part in the development of the special programmes. |  | . | .
Measure 1.3.3: Support to the organisational and functional transformation of local self-government and to unification of organisational forms established by LSGU for implementation of their competencies and tasks
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Harmonisation of the organisational structure of local government (average ratio of basic and supporting functions in local government) (%) |  |  | 40 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Harmonisation of the organisational forms of LSGUs with basic typology of organisational forms which can be established by LSGUs (%) |  |  | 0 (2020) |  | 0 | 0 | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.3.1: Preparing functional and organisational models of local government | Q3 2021 | MPALSG | Completed | 100% | Four functional and organisational models have been developed on the basis of 6 criteria (1. size of the local self-government, 2. number of organisational units, 3. competence/jurisdiction, 4. prescribed limitations, 5. control range, and 6. number of employees). The models are: MODEL 1 for LSGUs with up to 20,000 inhabitants, MODEL 2 for LSGUs with 20,001 to 50,000 inhabitants, MODEL 3 for LSGUs with 50,001 to 100,000 inhabitants , and MODEL 4 for cities with over 100,000 inhabitants. |  | . | .
1.3.3.2: Developing an analysis of existing organisational forms established by LSGUs for meeting their mandates and performing their tasks (legal basis and status, organisational form, internal structure and governance, status and relationship with the founder, process of managing the organisational form, management, etc.) | Q4 2021 -> Q4 2022 | MPALSG | Has not commenced | - | . |  | Given the organisational and staffing changes in the MPALSG, for a long time nobody was being appointed as the project manager who would be responsible for project implementation. Consequently, the implementation of this activity has been delayed. | The procedure of appointing a new manager on the project is on-going. Once the procedure is completed, it will be possible to start implementing the project activities according to the timeline.
1.3.3.5: Implementing financial support (fund) for the application of functional and organisational models in local government, and technical support in applying the model | Q4 2022 | MPALSG | In progress | 57.85% | The first public call has been conducted for project proposals for the application of functional and organisational models in units of local self-government in the Republic of Serbia. Four projects (four LSGUs) have been selected for funding and technical assistance during the application of the functional and organisational model. |  | The finalisation of the first funding round and the application of the model in four LSGUs were delayed owing to the organisational and staffing changes in the MPALSG. Corrective measures taken entailed forming a new commission, selecting [new] projects for the application of functional and organisational models, and effecting payments of the allocated funds by the end of 2021. The application of the model(s) in the four selected LSGUs is expected to complete by 30 June 2022. | To conduct the second round of funding for the application of functional and organisational models ain units of local self-government and of technical assistance in the application of the model, through the second public call for project proposals for the application of functional and organisational models in units of local self-government in the Republic of Serbia, and to select at least four projects (four LSGUs) for the application of the model.
Measure 1.3.4: Continuing development of inter-municipal cooperation in the implementation of local self-government competencies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
The national financial mechanism for support to inter-municipal cooperation established and functional (Number) |  |  | 4 (2020) |  | 10 | 10
Basic and sectoral legal framework improved for the purpose of developing inter-municipal cooperation (0 – No, 1 – Yes) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.4.2: Funding of inter-municipal cooperation projects | Q4 2023 | MPALSG | In progress | 99.86% | In 2021, six projects were funded following the first public call for projects for establishing and advancing inter-municipal cooperation, two of which aimed to advance an existing inter-municipal cooperation, and four of which aimed to establish new inter-municipal cooperation. Areas in which advancement of existing inter-municipal cooperation was supported were social services (OSI) and emergencies. Areas in which establishment of new inter-municipal cooperation was supported were environmental protection, zoohygiene, and public prosecution services. |  | The original start and end [date] of the first public call has been pushed to 2022 because of the organisational and staffing changes in the MPALSG as well as the late implementation of the funded projects, i.e. activities, caused by the COVID-19 pandemic. The exception has been the established IMC in environmental protection and public prosecution services. That is, two of the four projects have been implemented. The implementation period of the other two projects related to zoohygiene and environmental protection has been extended because the LSGUs were themselves late in implementing project activities. | To run the second and the third round of grants for advancing/establishing inter-municipal cooperation in 2022 and 2023.
Measure 1.3.5: Improving the local self-government development planning system
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Share of LSGUs which have adopted development plans in total number of LSGUs (%) |  |  | 4.1 (2020) |  | 15 | 21.4
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.5.1: Screening/analysis of the Law on the Planning System of the Republic of Serbia and special laws regulating the development of sectoral planning documents at the local level, identifying the needs for reviewing the deadlines for [1] aligning the process of developing local planning documents per special regulations with the systemic Law, and [2] initiating amendments to regulations. | Q4 2022 | PPS | Has not commenced | - | . |  | . | This activity will be implemented during 2022.
1.3.5.2: Establishing and implementing support to LSGUs in drafting Development Plans (advisory support, instructions, and ensuring coordination and exchange of experiences, etc.) | Q4 2023 | PPS | In progress | - | The tasks of providing general and advisory support to LSGUs in preparing their development plans (DPs) has been added to the PPP's scope of work. That support in 2021 included responding to LSGUs' questions about the process of drafting their DPs and applying the Guidelines for Drafting LSGU Development Plans, https://rsjp.gov.rs/wp-content/uploads/Prirucnik-za-lokalnu-samoupravu-web_final-19.8.pdf. The PPS and the SCTM established cooperation in coordinating the support to LSGUs to establish the new planning system. The training in medium-term planning at the local level, which NAPA had organised with the SCTM, provided LSGUs with information about the relevant DP-planning methodology. |  | . | To continue supporting LSGUs in preparing their development plans into 2022 and 2023.
1.3.5.3: Providing mentoring to 15 LSGUs for drafting Development Plans | Q1 2022 -> Q3 2023 | PPS | In progress | 20% | Direct donor support for drafting 15 LSGUs' development plans is being provided in coordination with the PPS, and through three specific projects: 1. Project Local Self-Government of the 21st century (SDC) supports the preparation of 3 LSGUs' development plans. Criteria and a points system for selecting the 3 LSGUs have been developed and confirmed. The winning or selected municipalities were Opovo, Prijepolje, and Sokobanja, each of which has concluded a business cooperation agreement with the Tentative Timeline of Activities involving the process of drafting a development plan. A stakeholder analysis, an analysis of institutional capacities, and a situation analysis per area, are all being conducted at the moment. 2. Project Public Financial Reform – Agenda 2030 (GIZ) supports the preparation of 2 LSGUs' development plans: the Municipality of Užice, and the Municipality of Sremski Karlovci. Both municipalities have concluded a business cooperation agreement with the Tentative Timeline of Activities involving the process of drafting a development plan. A stakeholder analysis, an analysis of institutional capacities, and a situation analysis per area, are all being conducted at the moment. 3. Project Public Financial Reform (GIZ), supports the preparation of 10 LSGUs' development plans. The LSGU-selection criteria is being defined, after which a public call for applications will be announced. A full coordination with the SCTM has been achieved to prevent overlaps in support to LSGUs (Activity 1.3.5.4). |  | The pandemic has slowed down the project activities related to the preparation of draft development plans for 5 municipalities (projects Local Self-Government of the 21st century, SDC and Public Financial Reform – Agenda 2030, GIZ). | Deadline for the drafting of three development plans has been extended until August 2022 (the SDC Project Local Self-Government of the 21st century). Activities will be implemented in accordance with the Tentative Timeline of Activities in the process of drafting development plans. It is expected that the public call within the GIZ Project Public Financial Reform will be announced in Q1 2022.
1.3.5.4: Supporting LSGUs in drafting/revising their Development Plans (direct technical support for a minimum of 25 LSGUs). | Q4 2023 | PPS | In progress | 80.65% | In 2021, 5 LSGUs continued receiving support for drafting their development plans. The 5 LSGUs in question are beneficiaries of direct technical support under the project funded by SlovakAid but implemented by UNDP and SCTM in coordination with the PPS. They are: Tutin, Blace, Prokuplje, Nova Varoš, and Bač. As part of that support, partner forums were held in the LSGUs to encourage a wider circle of local community stakeholders to participate in the process of drafting the DPs, there was a coordinated development of a socio-economic analysis as well as an analysis of administrative and financial capacities, and a 2-day workshop for municipal teams. In order for the subject LSGUs to prepare for the operationalisation of their DPs through project funding, an accredited training entitled Preparing Project Proposals Following EU Procedures was organised for them in September 2021. Additionally, UNDP begun supporting the development of Raška Municipality's DP. |  | Due to the pandemic, there were certain delays in the implementation of activities which had to do with supporting the development of supported LSGUs' DPs, while other activities were done online. Consequently, the duration of the project support for the development of 5 DPs has been extended until June 2022. | In 2022, to continue with the activities, i.e. to complete the 5 DPs of the supported LSGUs by the deadline of June 2022. In 2022 and 2023, to continue the direct support for the design of development plans of 10 new LSGUs under the EU Exchange 6 Project. The public call for the selection of the 10 new LSGUs to receive support is planned for Q1 2022, and of another 10 LSGUs for early 2023. Direct support to 10 new LSGUs to develop their MTPs will be continued under the EU Exchange 6 Project.
1.3.5.6: Maintenance and development of an analytics services for LSGUs in order to support LSGUs in designing [their] Development Plans | Q4 2021 | PPS | Completed | - | The LSGUs' analytics service is updated, filled with 2020 data and expanded to include data and indicators (broken down by gender, where applicable) for areas of education and healthcare. Reporting tables for LSGUs' development plans have been created inside their analytics-reporting system (Kyubit Business Intelligence software) for all the available areas, necessary for the development of an evidence-based situation analysis, i.e. for identifying and describing key obstacles to a sustainable development in the given LSGU (one of the main and first steps in the process of drafting LSGU development plans in accordance with the Law on the Planning System of the Republic of Serbia). |  | . | Continue to upgrade the LSGUs' service to ensure evidence-based decision making.
Specific objective 1.4: Improving the quality and availability of services of local government bodies, utilities and services of public institutions
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Index for measuring the availability and quality of LSGU services has been developed (0 – No, 1 – Yes) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Index for measuring users’ satisfaction with LSG services has been developed (0 – No, 1 – Yes) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Measure 1.4.1: Development and improvement of the basic methodology and tools for monitoring the implementation
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Basic methodology for calculating the necessary financial, human and technical capacities for the implementation of local self-government tasks has been determined (0 – No, 1 – Yes) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
An analysis of the degree of established tasks in the priority areas of local self-government has been performed (0 – No, 1 – Yes) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Percentage of administrative tasks from the Unified List of LSGU Tasks (tasks of administrative bodies) performed by LSGUs (%) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.1.6: Updating the list of competencies and tasks at all levels of government and updating the Unified List of Tasks at the Local Level | Q4 2023 | MPALSG | In progress | 100% | Completed update of the list of tasks in 34 fields (healthcare, social policy, economy, agriculture, regional development, urbanism, spatial planning, youth, sports, culture, information, veterinary, plants, education, environmental protection, energy, mining, civil status, property relations, general administration, construction, infrastructure, science, technological development, labour relations, employment, veteran affairs, transportation, finance, trade, commerce, tourism, telecommunications, utility activities, housing,at all levels of government) in accordance with the methodology for analysing lists of tasks in all fields in the Republic of Serbia, for the central, provincial, and local levels of government, for the 2019–2020–2021 period. Updated 2020–2021 Unified List of Tasks at the Local Level in 49 fields (finance, construction, infrastructure, spatial planning, public informing, public transportation, utility activity, culture, science, technological development, education, youth, general administration, agriculture, water management, forestry, economy, regional development, labour relations, employment, veteran affairs, mining, geological research, transportation, local self-government, citizens' civil status, management of citizen registers, suffrage, social protection, sports, housing, trade, tourism, hospitality, telecommunications, veterinary, plants, healthcare, environmental protection, energy, inspectoral supervision, administrative inspections, defence, emergencies, data secrecy, public procurement, public property) in accordance with the Law on Local Self-Government. |  | . | .
1.4.1.7: Developing an analysis/verifying the degree of instituted tasks in priority areas from the Unified List of Tasks on a sample of 45 LSGUs | Q4 2023 | MPALSG | In progress | 35.48% | The draft analysis has been completed using the special methodology applied on a sample of 45 LSGUs in 6 fields (environmental protection, agriculture, social protection, education, culture, housing) which are relevant in LSGUs' performance of key competencies. |  | . | .
Measure 1.4.2: Improving the capacity of local self-government to provide administrative services
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Number of LSGUs with established OSS (Number) |  |  | 14 (2020) |  | 19 | 19
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.2.2: Improving and aligning the models of administrative procedures for performing tasks entrusted to LSGUs | Q4 2023 | MPALSG | In progress | 100% | The SCTM has established cooperation with the Ministry of Labour, Employment, Veteran and Social Affairs, when it comes to veteran disability protection-related procedures. A total of 22 draft new procedures have been prepared in accordance with the new Law on Veteran Protection. These procedures are currently in the phase of preparation for entry into the Register of Administrative Procedures. |  | . | .
Measure 1.4.3: Initiation of systemic reforms of utility activities and services
Institution in charge: MINISTRY OF CONSTRUCTION, TRANSPORT AND INFRASTRUCTURE
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Basic legal framework in the area of performing utility activities and delivery of utility services has been improved (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 1 | 0 | The necessary adoption of the new Law on Utility Activities which is to define more clearly and more transparently the procedure of conferring the performance of utility activities, which will enable the necessary investments into the utility infrastructure. The target value for 2021 has not been envisaged.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.3.1: Drafting a situation analysis in the area of utility activities | Q4 2021 | MCTI | Completed | 100% | Considering that the Government Work Plan for 2021 envisaged amendments to the Law on Utility Activities, at the Standing Conference of Towns and Municipalities' proposal and with the support from the Ministry of Public Administration and Local Self-Government, the Ministry of Construction, Transport and Infrastructure had agreed to develop an ex-post impact assessment of that Law. The development of the assessment had begun in Q2 [2021]. |  | . | .
1.4.3.2: Preparing a draft Law on Utility Activities | Q4 2021 -> Q4 2022 | MCTI | In progress | - | A questionnaire about the implementation of the Law on Utility Activities was made for units of local self-government and public utility companies, and send to them through the STCM communication channels (networks) on 31 May. Responses from 56 units of local self-governments were received. In the meantime, a database of documents relevant for the impact assessment was created. |  | . | .
1.4.3.3: Submitting the draft Law on Utility Activities to the Government for review and approval of the legislative proposal (Bill) | Q4 2021 -> Q4 2022 | MCTI | In progress | - | On the basis of the ex-post impact assessment of the Law on Utility Activities, the Ministry of Construction, Transport and Infrastructure began drafting the new Law on Utility Activities. To that end, a national working group was created. |  | . | .
Measure 1.4.4: Improvement of local public services through local economic development and implementation of public-private partnership models
Institution in charge: MINISTRY OF ECONOMY
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
The legal framework governing LSGU action in LED field has been improved (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 1 | 0 | The [text of the] Law on Investments is being prepared.
Percentage of total number of LSGUs which have adopted LED programme (%) |  |  | 5 (2019) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Percentage of LSGUs which have PPP projects (%) |  |  | 48 (2020) |  | 50 | 50 | The number of PPP projects has been constantly rising, year to year, making the set target fully achieved.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.4.1: Preparing the proposed amendments to provisions of the Law on Investments relating to the adoption of programmes for LED, which would define a set of LSGU activities in the area of LED and LSGU services for businesses | Q4 2021 -> Q3 2022 | Ministry of Economy | In progress | - | The procedure of amending the Law on Investments was completed in Q4 2021. During that same quarter, the draft text was sent to a total of 18 addresses, including ministries and other relevant bodies and organisations, professional associations, and occupational associations. The following terms were defined: investment of local importance, actions of the local unit for support to the local economic development programme, contents of the local economic development programme, records of investments of local importance, etc. The draft Law will be submitted to the Government, immediately after it is formed following the April elections. Once the Government has confirmed the draft Law, it will submit it [now as a Bill] to the National Assembly of the Republic Serbia for adoption. |  | . | .
1.4.4.2: Support to LSGUs in implementing LED activities (advisory and mentoring support, networking and knowledge sharing, regional workshops, drafting instructional materials, expert support for drafting a programme for LED, etc.) | Q3 2022 | Ministry of Economy | In progress | 100% | In 2021, the SCTM used multiple mechanisms to support units of local self-government in carrying out their LED-related competencies. Those mechanisms included advisory support through expert advice in response to LSGUs' questions, developing a handbook (the Handbook for attracting and realising investments at the local level has been revised and aligned with the Law on the Planning System), developing and distributing the Handbook for Planning the Development of Tourism in LSGUs, and developing a handbook – now in its final stage – for LSGUs' control and monitoring of investments of local importance (investments which are supported with incentive funds out of the LSGU budgets). The planned revision and improvement of the Handbook for Developing LED Programmes was postponed until 2022 due to the planned adoption of the Amendments to the Law on Investments, i.e. the planned changes to the section(s) [of the Law] specifically referring to the LSG's obligations in the process of developing and adopting LED programmes. A meeting of the SCTM network was held during which the Minister of Economy spoke about the importance of the incentive policy on the local economy. In Q4 2021, three online workshops were held where LSGUs were presented the Central Information System e-Tourist (e-Turista) in detail and shown by experts how to use it – all in line with the applicable Rulebook on the Mode of Entry, Operation and Use of the Central Information System and its Content and Data Type. In that same period, a comprehensive support in preparing a LED programme for the City of Loznica was initiated. This support is to result in a fully developed LED programme and a finalised concept of package support which the SCTM will leave at all other LSGUs' disposal. |  | . | .
1.4.4.3: Building the capacities of LED units’ employees (enhancing the existing and defining new sectoral continual and special training programmes and coordinating the implementation of accredited training programmes) | Q4 2023 | NAPA | In progress | 100% | Over the summer months of 2021, at the invitation of colleagues from NAPA and in cooperation with them, the SCTM reviewed the 2022 plan for professional development of LSGU employees working in the field of local economic development. Compared to the 2021 programme, there were no key changes to the contents of the training in this field. The SCTM implemented an accredited training entitled Application of the Law on Tourism and the Law on Hospitality in accordance with the 2021 Sectoral Programme of Continuous Professional Development of employees in LSGUs. The purpose of this intervention was to expand the participants' existing knowledge [of those laws] and to familiarise them with the new legal solutions concerning tourism and hospitality, to resolve LSGUs' most frequently faced dilemmas about the application of regulations governing the field of tourism and hospitality, to enable employees in local administration to apply regulations and perform the LSGU tasks accurately, especially supervisory tasks in the field of hospitality which are within the purview of LSGUs. |  | . | .
1.4.4.4: Situation analysis and analysing the capacities of LSGUs in Serbia to prepare and implement PPP projects and to apply the Law on PPPs | Q3 2021 -> Q2 2022 | Ministry of Economy | In progress | - | The conducting of analysis begun in October 2021, and it will last until January 2022. The objective of the analysis is to determine the real situation or reality of the process of preparing and implementing PPP projects in LSGs, and to identify potential system flaws, so that the SCTM could prepare adequate support in this area to LSGs. Also, the analysis is meant to indicate potential changes and improvements to the legislative framework which relate to PPP implementation. To ensure a good quality analysis and that the most relevant data is collected, a portion of this activity is being implemented in the field, i.e. in 30 LSGs with prior experience implementing PPP projects. |  | Due to the pandemic, the start of the development of the analysis was pushed forward slightly. The plan is to have the analysis completed in early 2022. | Activity implementation at the start of 2022.
1.4.4.5: Drafting amendments to the Law on PPP (based on the needs and the findings of the situation analysis) | Q4 2021 -> Q4 2022 | Ministry of Economy | In progress | - | In accordance with the Government Work Plan, the following period will see completed amendments to the Law on Public-Private Partnerships and Concessionsе, which will enable a full harmonisation of this important part of the legislature with the EU acquis (Directive 23/2014, and Directive 24/2014). A Working Group has been formed and tasked to draft the amendments. |  | Due to the pandemic, the project proponents were delayed in developing the analysis and collecting field data which are essential for revising and clarifying certain provisions of the Law. | .
Measure 1.4.5: Development of methodological and analytical tools for monitoring LSGU services and citizens' satisfaction with their quality
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Survey on the availability and quality of LSGU priority services has been conducted (0 – No, 1 – Yes) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.
Survey on the users’ satisfaction with the services delivered by LSGUs has been conducted (0 – No, 1 – Yes) |  |  | 0 (2020) |  | - | - | Pursuant to the adopted AP for the Implementation of the Programme for the Reform of the Local Self-Government System in the Republic of Serbia 2021–2023, the target value for 2021 has not been planned.