## All activities export_1
Annual Report on the Implementation of the 2021 Action Plan for the: |  |  |  |  | ACTION PLAN 2021–2025 FOR THE IMPLEMENTATION OF STRATEGY FOR PUBLIC ADMINISTRATION REFORM IN THE REPUBLIC OF SERBIA FOR THE PERIOD 2021–2030
Institution responsible for coordination and reporting: |  |  |  |  | MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Public policy document elaborated by the Action Plan: |  |  |  |  | Strategy for Public Administration Reform in the Republic of Serbia 2021–2030
Overall objective 1: FURTHER IMPROVEMENT OF THE WORK OF PUBLIC ADMINISTRATION AND THE QUALITY OF PUBLIC POLICY DEVELOPMENT IN ACCORDANCE WITH THE EUROPEAN PRINCIPLES OF GOOD GOVERNANCE, ENSURING HIGH QUALITY SERVICES TO CITIZENS AND BUSINESS ENTITIES, AND A PROFESSIONAL PUBLIC ADMINISTRATION WHICH WILL SIGNIFICANTLY CONTRIBUTE TO THE ECONOMIC STABILITY AND THE IMPROVEMENT OF THE LIVING STANDARD
Document proponent: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Government Effectiveness (percentile ranking (from 1 to 100)) |  |  | 53.37 (2019) |  | 54–55 | 54.33
Satisfaction of citizens and businesses with services delivered by public administration (Number) |  |  | 4 (2020) |  | 4.5 | 5
Specific objective 1.1: IMPROVED QUALITY OF PUBLIC POLICY DOCUMENTS AND REGULATIONS
Institution in charge: PUBLIC POLICY SECRETARIAT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Regulatory quality indicator – World Bank ranking (Number) |  |  | 60.1 (2019) |  | 61 | 57.21
Indicator of alignment and quality of policy planning (Scale (1–5)) |  |  | 0 (2021) |  | - | - | Target value for 2021 has not been planned.
Measure 1.1.1: SPECIFIC OBJECTIVE 1 of the Public Policy Management and Regulatory Reform Programme — REGULATORY REFORM AIMED AT IMPROVING THE BUSINESS ENVIRONMENT AND REDUCING UNNECESSARY BURDEN ON CITIZENS AND BUSINESSES
Institution in charge: PUBLIC POLICY SECRETARIAT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
The share of adopted laws containing complete impact assessments in the total number of adopted laws requiring impact assessments, per calendar year (%) |  |  | 30.4 (2020) |  | 35 | 47.4
The share of adopted regulations containing complete impact assessments in the total number of adopted regulations requiring impact assessments, per calendar year (%) |  |  | 58.3 (2020) |  | 58 | 65.1
Measure 1.1.2: SPECIFIC OBJECTIVE 2 of the Public Policy Management and Regulatory Reform Programme —STRENGTHENING CAPACITIES AND IMPLEMENTING INSTRUMENTS FOR QUALITY DEVELOPMENT AND MANAGEMENT OF PUBLIC POLICIES AND REGULATIONS
Institution in charge: PUBLIC POLICY SECRETARIAT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
The share of adopted PPDs within a single calendar year, containing complete impact assessments, in the total number of adopted PPDs requiring impact assessments (%) |  |  | 50 (2020) |  | 60 | 43.8 | Of the total number of adopted public policy documents requiring an impact assessment during a calendar year, the total percentage of adopted public policy documents for which an impact assessment has been conducted, if partial impact assessments are counted in addition to the complete ones, reaches 100%.
Measure 1.1.3: SPECIFIC OBJECTIVE 3 of the Public Policy Management and Regulatory Reform Programme — EFFECTIVE PUBLIC POLICY COORDINATION
Institution in charge: PUBLIC POLICY SECRETARIAT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
The total number of planning areas with a revised and optimised planning framework (a clear hierarchical structure of PPDs established within planning areas) (Number) |  |  | 1 (2020) |  | 3 | 3 | The following areas had been optimised by the end of 2021: public information, public administration, and education.
Measure 1.1.4: SPECIFIC OBJECTIVE 4 of the Public Policy Management and Regulatory Reform Programme — INCREASED INVOLVEMENT OF CIVIL SOCIETY, BUSINESSES AND OTHER STAKEHOLDERS IN THE EARLY STAGES OF THE DEVELOPMENT OF PUBLIC POLICIES AND REGULATIONS AND IN MONITORING THEIR IMPACTS
Institution in charge: PUBLIC POLICY SECRETARIAT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
The share of adopted PPDs, during the preparation of which a consultative process took place in accordance with the LPS, in the total number of adopted PPDs in a calendar year (%) |  |  | 100 (2020) |  | 100 | 96.2
The share of adopted statutes, during the preparation of which a consultative process took place in accordance with the LPS, in the total number of adopted laws in a calendar year (%) |  |  | 35.71 (2020) |  | 38–40 | 44.4
The share of adopted regulations, during the preparation of which a consultative process took place in accordance with the LPS, in the total number of adopted regulations in a calendar year (%) |  |  | 11.46 (2020) |  | 14.25–15 | 21.4
Specific objective 1.2: AN IMPROVED RECRUITMENT PROCESS IN PUBLIC ADMINISTRATION
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Meritocracy and effectiveness of recruitment of civil servants (SIGMA principle) (Number) |  |  | 3 (2019) |  | 3 | 3
Measure 1.2.1: Improvement of personnel planning and promoting state administration as a desirable employer
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Recruitment based on stated personnel needs of bodies (%) |  |  | 0 (2019) |  | 20–25 | 14 | A deviation from the target value occurred due to the failure to adopt the 2021 Personnel Plan for ministries, special organisations, Government agencies and expert services of administrative districts, which would have allowed for all rulebooks on internal organisation and systematisation of job positions to be aligned with the adopted Personnel Plan/approved budgetary resources in 2021. Another reason for the deviation is the fact that the Committee for approvals of new recruitments and additional hirings by public funds beneficiaries was granting approvals for filling executive positions in accordance with the approved budgetary resources. The values used in the formula for calculating the percentage of persons who have been recruited for these job positions in relation to the total number of persons who are to be recruited, are based on the number of systematised positions in applicable rulebooks which have been approved by the Government of the Republic of Serbia, monthly records of the number and structure of employees in these bodies on 31 December 2020, and data on the influx of civil servants in 2021.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.1.1: Analysing the application of the existing personnel planning framework in state bodies and issuing recommendations for improvement, including a proposal to recruit personnel to work in priority-areas | Q3 2021 | MPALSG | completed | 100% | With the support of the GIZ Project “Support to Public Administration Reform in the EU Accession Process”, work began on innovating the methodology for personnel planning in state bodies. Thirteen meetings of MPALSG and HRMS representatives were held. Analysis of the application of the existing personnel planning framework in state bodies was conducted, Draft forms of the innovated personnel plan and Draft Decree on the Personnel Plan were prepared. . |  | . | .
Measure 1.2.2: Improvement of the selection process and the process of induction of new employees
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Degree to which the competency framework matches the public administration needs and core values (Number) |  |  | 1 (2020) |  | 2 | 2 | By adopting the Law on Civil Servants in 2018 and the Amendments to the Law on Employees in the Autonomous Provinces and Local Self-Government Units, the competency framework was established for civil servants and employees in the APs and LSGUs.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.2.6: Designing an introductory/induction training programme on state administration matters and operations for trainees, recruits on a probationary period and persons starting their employment in state administration and are not on probation | Q4 2021 | NAPA | completed | - | An introductory/induction training programme on state administration matters and operations for trainees, recruits on a probationary period and persons starting their employment in state administration who are not on probation, was prepared with the support of the French National School of Administration (ENA). Representatives of the Ministry of Public Administration and Local Self-Government (MPALSG) and Human Resource Management Service (HRMS) participated in the development of this programme. The programme is an integral whole which provides civil servants with an opportunity to prepare for taking the state professional examination, and build and reinforce behavioural and functional competencies defined in the Decree on Determining the Competencies for the Work of Civil Servants, with a focus on teamwork, cooperation, creativity and innovation. The introductory/induction programme contains the following segments: I. Preparation for taking the state professional examination; II. Developing your competencies step by step; III. Create, solve, innovate – group project. Upon a proposal of the National Academy for Public Administration, the Government of the Republic of Serbia, at its session held on 23 December 2021, by the Government Conclusion 05 No.151-11960/2021, adopted the 2022 General Training Programme for Civil Servants, with the introductory/induction Training Programme as its integral part. . |  | . | The introductory/induction training programme will be implemented in phases. Employees working in human resource management will be attending the Programme in its first phase.
1.2.2.8: Drafting a competency framework for employees in bodies of autonomous provinces and units of local self-government, to include a map to integration into the HRM | Q2 2021 | MPALSG | completed | 100% | With the support of the Programme “Human Resource Management in the Local Self-Government - Phase 2” (2018–2021), implemented by the Council of Europe in Serbia with its project partners, the Ministry of Public Administration and Local Self-Government and the Standing Conference of Towns and Municipalities, activities were implemented which primarily concerned the establishment of a competency system at the local government level, which resulted in the development of a final document - Competency Framework required for an effective work of employees in bodies of APs and LSGUs. These activities, which serve as a basis for establishing a competency system for employees, are established as starting points for regulatory activities of the Ministry which would incorporate the Competency Framework into the legal framework. In January 2021, the Minister of Public Administration and Local Self-Government created a Special Working Group (SWG) for drafting the Amendments to the Law on Employees in the Autonomous Provinces and Local Self-Government Units. The SWR drafted the text of the Amendments in accordance with the proposed Competency Framework. In view of the fact that establishing a competency system at local government level is a complex endeavour, the competency system for employees in bodies of APs and LSGUs will be integrated successively (in phases). The first phase will be adoption of the Law on Employees in the Autonomous Provinces and Local Self-Government Units, which will integrate competencies into acts on systematisation. The second phase consists of an introduction of competencies into the selection process, and the third phase consists of an introduction of competencies into the grading of employees. . |  | . | .
Measure 1.2.3: Improvement of the procedure for merit-based filling of senior civil service positions, and induction
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Percentage of senior civil service positions filled in accordance with the competency framework, compared to the total number of positions (%) |  |  | 34 (2020) |  | 38–40 | 42 | Of the total number of systematised job positions (408), unfilled job vacancies (41) were deducted. Of the total number of filled job positions (367) on 31 December 2021, 42% were filled after an open competition.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.3.3: Creating a mechanism of cooperation between institutions responsible for the senior civil servants management policy | Q2 2021 -> Q1 2023 | HRMS | In progress | - | . |  | The Special Working Group, with the support of SIGMA, started working on preparing the policy framework for the purpose of strategic orientation and further professionalisation of senior civil servants in the Republic of Serbia. The policy framework will determine the effects of the implementation of the existing regulatory framework and provide proposed measures for improvement concerning recruitment and selection, through induction and career management, to coordination and communication of all relevant participants in the management of the said category of employees. In September 2021, PRD and SIGMA coordinated a roadmap for development of a strategic document which is to be adopted in the second half of 2022, thus establishing a strategic basis for taking next steps for further professionalisation of senior civil servants, including coordination and communication of all relevant participants in the management of the said category of employees. | .
Specific objective 1.3: AN EFFICIENT CAREER MANAGEMENT SYSTEM APPLIED IN PRACTICE
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Degree to which the career management system for the civil service is developed (Number) |  |  | 1 (2020) |  | 1 | 1 | The Career Management Centre uses various civil servant career management tools (more than 3), such as analysis of individual development potentials, 360-degree feedback, career counselling and couching.
Measure 1.3.1: Creating an environment to have efficient, innovative and motivated civil servants
Institution in charge: HUMAN RESOURCE MANAGEMENT SERVICE
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Giving performance appraisal ratings according to HRM standards (%) |  |  | 75 (2020) |  | 70–73.5 | 58.4 | Percentage of civil servants employed in state administration bodies who received the highest rating exceeds expectations for their work performance in 2020.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.1.4: Preparing a study about remote employment models (working remotely or from home), with a proposal on how such models could be incorporated into the way in which state administration bodies in the Republic of Serbia operate | Q2 2021 | MPALSG | completed | - | In 2020, in view of the COVID-19 pandemic, an analysis was conducted, reviewing how state administration bodies organised their activity in circumstances caused by the pandemic, with a focus on the ministries most affected by the crisis and institutions in charge of providing services to citizens. An analysis of remote employee engagement models and possibilities of introducing this work method in state administration bodies in the Republic of Serbia was conducted with the help of SIGMA, under the Learning from the COVID-19 crisis: More flexible working arrangements for civil servants Project. The analysis showed that a large number of state administration bodies introduced remote work in 2020 (60%), that civil servants had a positive attitude to remote work and that they would love to continue working in this manner, but it also showed that managers, although they had successfully managed their team remotely, had no additional support mechanisms for managing remote teams. It was also demonstrated that the fundamental IT preconditions for introducing remote work were met, but that insufficient digitalisation of work processes was a problem. In this regard, recommendations were made for introducing a legal framework and practice in order for managements to successfully face similar situations in the future. These recommendations will serve as the basis for introducing more flexible working conditions for civil servants as an integral part of human resource management policy in state administration (e.g., possibility of remote work for a limited number of days per week or month, establishment of better communication and reporting templates, support to managers in remote team management, training in remote team management, development of digital skills, etc.). |  | . | .
Measure 1.3.2: Development of institutional and administrative capacities for human resource management
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Degree to which the organisation of personnel affairs in state administration bodies is standardised, and quality of personnel affairs (Number) |  |  | 0 (2020) |  | 1 | 1 | All state administration bodies which employ over 100 people have established HR units or systematised the job position of the Human Resources Officer.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.2.2: Preparing an action plan for building the capacities of HR units in state administration bodies, and implementing activities defined in that action plan | Q4 2021 | MPALSG | completed | 100% | In 2020, with the support of the project “Support to Public Administration Reform in the EU Accession Process”, implemented by GIZ (Deutsche Gesellschaft für Internationale Zusammenarbeit GmbH), the Ministry of Public Administration and Local Self-Government developed the “Action Plan for building the capacities of HR units in state administration bodies of the Republic of Serbia”. In order to develop the Action Plan, the Ministry created a Special Working Group for developing the programme and plan of development and improvement of HR units, by its Decision No. 119-01-28/2020-20 of 28 May 2020. In late 2020, the SWR adopted this Action Plan. In the next 3 years, this Action Plan will help establish a completely new role of HR managers and units in public administration bodies, which entails abandoning the traditional role of personnel units and a transformation into modern HR units, which would constitute systemic changes of the system. The Action Plan contains a description of the existing institutional framework for human resource management in state administration bodies of the Republic of Serbia, a description of the desired and an analysis of the current state, role and capacities of the HR units in SABs, and a draft triennial action plan for enhancement of capacities by the end of 2023. In 2021, the Ministry of Public Administration and Local Self-Government implemented activities stipulated in the adopted Action Plan. Activities concerning innovation of personnel planning in state bodies are currently underway. Thirteen meetings of MPALSG and HRMS representatives were held. At the meetings, draft forms of the innovated personnel plan and Draft Decree on the Personnel Plan were prepared. The AP, inter alia, establishes an objective concerning improvement of coordination between personnel units and HRMS, NAPA, MPALSG, and the General Secretariat of the Government (for senior civil servants). In order to reach that goal, a series of activities were defined for improvement of communication between these bodies and personnel units. One of the first ones is the creation of a network of employees dealing with human resources, for the purpose of a faster exchange of ideas and resolving problems in practice. The Human Resource Management Service was designated as the implementer of this activity. This activity was implemented at the beginning of this year. So far, 8 meetings of the network were held, where current HR activities in the state administration were presented. An IT platform was also developed, which would support the activities of the network and enable continuous communication with employees in personnel units. With a view to improving the role of personnel units in state administration bodies, with the support of ReSPA, the document “How to achieve strategically oriented personnel units” was developed. It will serve as the basis for involving employees dealing with HR affairs into the strategic management of bodies, i.e., for strengthening their role as a strategic partner and agent of change. |  | . | .
1.3.2.3: Development of competence-based training for managers and HR units | Q4 2021 | NAPA | completed | - | In the 2022 General Training Programme for Civil Servants, the thematic area Human Resource Management was developed, for the primary purpose of reinforcing knowledge and skills of civil servants for competency-based human resource management. This thematic area was developed with the support of the Ministry of Public Administration and Local Self-Government and the Human Resource Management Service. In addition, the same principle was applied to the development of the 2022 General Training Programme for Civil Servants. A new programme concept was developed, whose structure clearly indicates a connection between the programme and the development of competencies. For that purpose, 21 more thematic areas were developed which directly develop behavioural, general functional and special functional competencies of civil servants. Under the 2022 Training Programme for Managers in State Bodies, the Senior Civil Servants Training Programme and the Training Programme for Civil Servants who are Preparing for or are in Management Positions were developed. The Senior Civil Servants Training Programme was developed with the support of the organisation SIGMA, the Ministry of Public Administration and Local Self-Government and the Human Resource Management Service. The Training Programme for Civil Servants who are Preparing for or are in Management Positions was developed with the support of the Ministry of Public Administration and Local Self-Government and the Human Resource Management Service. These programmes develop necessary management knowledge and skills and behavioural competencies required by managers. Upon a proposal of the National Academy for Public Administration, the Government of the Republic of Serbia, at its session held on 23 December 2021, by the Government Conclusion 05 No.151-11960/2021, adopted the 2022 General Training Programme for Civil Servants and the 2022 Training Programme for Managers in State Bodies. . |  | . | The 2022 General Training Programme for Civil Servants and the Training Programme for Civil Servants who are Preparing for or are in Management Positions are expected to be executed in 2022, with resources and capacities of the National Academy for Public Administration. Support by the project “Strengthening professional capacities of Senior Civil Servants in Serbia” is ensured for the execution of the Senior Civil Servants Training Programme, which is implemented by the National Academy for Public Administration, with the financial support of the European Union.
Measure 1.3.3: Strengthening the professionalisation of the senior civil servants/managers
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Degree to which legal protection of senior civil servants/managers is ensured (based on five SIGMA sub-indicators) (Number) |  |  | 9 (2019) |  | 11 | 11 | On the basis of the 2020 SIGMA Report, the total number of points was established for each of the five sub-indicators, namely: 1.2/2, 2.2/3, 3.4/4, 4.1/2, 5.2/4, which makes a total of 11 points.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.3.3: Setting indicators of senior civil servants' performance in meeting annual work goals as part of the performance appraisal procedure | Q4 2021 | MPALSG | completed | - | Amendments to the Decree on Evaluation of the Performance of Civil Servants were adopted by Government at a session held on 14 February 2022. By these Amendments to the Decree, the performance evaluation procedure was complemented by organisational goals indicators in order to measure and guide the organisational units performance management process. In the performance appraisal process, performance indicators in meeting the annual targets for persons in the positions have been established. |  |  | .
Specific objective 1.4: A FUNCTIONAL AND INNOVATIVE SYSTEM OF PROFESSIONAL DEVELOPMENT AND PROFESSIONAL EXAMS IN PUBLIC ADMINISTRATION BASED ON THE ANALYSIS OF NEEDS FOR THE IMPROVEMENT OF EMPLOYEES' COMPETENCIES, KNOWLEDGE, SKILLS AND ABILITIES DEVELOPED AND IMPLEMENTED
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Degree to which the system of professional development and professional exams in public administration is normatively and practically based on the analysis of needs for the improvement of employees' knowledge, skills or competencies (Number) |  |  | 1 (2019) |  | 3 | 3
Measure 1.4.1: Improvement of the uniform system of professional development in state and LSGU bodies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Degree of implementation of the quality system in the elements of professional development in public administration (Number) |  |  | 1 (2020) |  | 2 | 2
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.1.1: Improving the accreditation system, the way in which training programme facilitators are hired, and the development of trainers’ skills and competencies | Q4 2021 | NAPA | completed | 100% | In 2021, with the support of the project “Human Resources Management in Local Self-Government – Phase 2”, jointly funded by the European Union and the Council of Europe, and implemented by the Council of Europe in Serbia, the existing Competency Framework of trainers was improved, a methodology was developed for monitoring the work and stimulating the professional development of NAPA trainers, using accompanying evaluation tools, and training of NAPA employees was implemented for the purpose of improving the process of monitoring and development of trainer competencies. . |  | . | Implementation of a pilot programme of evaluating trainer competencies, both by improving the internal competition procedure and by organising the first group evaluation of trainer competencies.
1.4.1.2: Improving the system of evaluation of training programmes in state bodies and units of local self-government, and increasing the knowledge and improving the skills of those participating in the evaluation process which are necessary for the implementation of the evaluation system | Q4 2021 | NAPA | completed | 100% | In 2021, under the project “Human Resources Management in Local Self-Government – Phase 2”, jointly funded by the European Union and the Council of Europe, and implemented by the Council of Europe in Serbia, a methodology was developed for evaluating the training programme after an evaluation of a training, and a report was compiled. . |  | . | .
1.4.1.3: Developing a methodology for training programme budget analysis and planning, as well as increasing the knowledge and the skills of civil servants and LSGU employees necessary for their application | Q4 2021 | NAPA | completed | 100% | The Methodology of training programme cost assessment and planning was developed as a comprehensive document, with the primary purpose of supporting civil servants in planning, organising, implementation and control of professional development programmes, and/or assessment of costs of their implementation and effects on the overall budget. This document may be downloaded from https://www.napa.gov.rs/tekst/1978/razvoj-programa-obuka.php In 2021, a webinar for 21 trainees was held. The topic of the webinar was Development of special programmes, and it was aimed at the NAPA contact persons, civil servants who participate in the development of special programmes in NAPA. In accordance with the Civil Servants Law and the Law on Employees in the Autonomous Provinces and Local Self-Government Units, training costs are a mandatory part of the training programme. Thus, the webinar covered the development of this element. . |  | . | A[nother] webinar on the development of special programmes is to be held in 2022, as a continuous activity.
Measure 1.4.2: Improvement of professional development programmes in state and LSGU bodies and of the manner of their organisation and delivery
Institution in charge: NATIONAL ACADEMY FOR PUBLIC ADMINISTRATION
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Fulfilment of participants’ expectations from training sessions where innovative forms and methods of professional development were applied (%) |  |  | 0 (2020) |  | 70 | 81
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.2.4: Supporting units of local self-government in a) the process of analysing their professional training needs, b) developing, designing and conducting special training programmes and the consolidated annual plan for professional development of their employees | Q4 2021 | NAPA | completed | - | With a view to providing expert assistance to bodies in the process of assessment of the needs for professional development, the following model acts were drawn up: Data Collection Techniques, Content Analysis Protocol (with the analysed elements), Guidebook for conversation with the manager of a state body, Conclusions from the meeting with the manager of a state body, Focus groups, Template for the individual development plan, Guidebook for conversation with managers of major organisational units, Structure of the Needs Assessment Report, and the Structure of the Report for NAPA. In addition, an infographic called “Calendar of professional development activities for employees of state bodies” was also prepared. On 16 June 2021, a webinar was held, for 21 trainees, on the subject “Development of special programmes”, aimed at NAPA contact persons, civil servants who participate in the development of special programmes in NAPA. Upon a request of the state body, expert assistance was provided to state bodies for the purpose of conducting an assessment of employee needs, by consultations with respect to the assessment of needs for professional development, developing and uploading online questionnaires for identifying individual needs of the employees, and data processing. Support was provided: to the Municipality of Tutin, City of Pančevo, and the City of Jagodina. In addition, expert assistance was provided to state bodies for the preparation of the draft Special Professional Development Programme. Support was provided: to the Expert Service of the Assembly of the Autonomous Province of Vojvodina and the Municipality of Medvedja. . |  | . | In 2022, support to state bodies will be continuously provided according to their needs.
Measure 1.4.3: Improvement of the normative framework governing professional development in public administration
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Quality of new regulations in the area of professional development (%) |  |  | 0 (2020) |  | 45–50 | - | The process of evaluation of all regulations concerning professional development has not been completed. The value of the indicators will be subsequently determined.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.3.1: Assessing the impact of and revisiting the laws regulating the area of professional development in state bodies (ex-post impact assessment of those laws) | Q4 2022 | MPALSG | completed | 100% | Public policy performance was measured on the basis of defined qualitative and quantitative indicators, and an ex-post assessment of the Law on the National Academy for Public Administration and the Civil Servants Law was conducted with respect to its part governing professional development, i.e., assessment of public policy relevance, efficiency and effectiveness and sustainability in professional development in state bodies for the purpose of its review and improvement, i.e. its revision and further planning. |  | . | Conducting an ex-ante assessment of the law governing professional development in state bodies and consultations with stakeholders and target groups with a view to proposing optimal improvement of the law (in 2023).
1.4.3.2: Assessing the impact of and revisiting the laws regulating the area of professional development in bodies of local self-government units (ex-post impact assessment of those laws) | Q1 2022 | MPALSG | In progress | 100% | Activities which have been completed are activities preceding the preparation of the implementation of an ex-post assessment and public policy performance evaluation concerning professional development as defined in the Law on Employees in the Autonomous Provinces and Local Self-government Units. An ex-post assessment of this law is in progress. |  | A delay in the execution of the task was due to a delay in the selection of the consultant who was recruited through the project “Human Resources Management in Local Self-Government – Phase 2”. The activity will be completed by the end of January 2022. | Conducting an ex-ante assessment of the law governing professional development in local self-government and consultations with stakeholders and target groups, with a view to proposing optimal improvement of the law (in 2023).
1.4.3.3: Assessing the impact of and revisiting by-laws adopted on the basis of statutes regulating the area of professional development in public administration (ex-post impact assessment of those by-laws) | Q4 2021 | NAPA | completed | 100% | With the support of the GIZ project, the recruited experts conducted an ex-post assessment of the Decree on Accreditation, Method of Engagement and Compensation of Executors and Implementers of Professional Development Programmes in Public Administration. A detailed report with recommendations was submitted to the National Academy in Q4 2021. . |  | . | Results of the report will be used to formulate and propose amendments to the said Decree.
Measure 1.4.4: Standardisation and establishment of a quality system in the area of professional development in public administration, with full application of ICT
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Number of business processes conducted with the use of information technologies (Number) |  |  | 1 (2020) |  | 1 | 6 | All business processes in the NAPA are digitalised
Measure 1.4.5: Establishment of a system for planning and managing the process of lifelong professional development in public administration (lifelong professional development master plan)
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Degree of development a system for planning and managing the process of lifelong professional development (Number) |  |  | 0 (2019) |  | 0 | 0
Measure 1.4.6: Establishment of instruments for cooperation between institutions responsible for professional development of employees in state and other bodies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Extent of development of the framework for cooperation between institutions in charge of the professional development of employees (Number) |  |  | 0 (2019) |  | 0 | 1
Measure 1.4.7: Introduction of uniform criteria, benchmarks and standards in the field of professional exams in the state administration system
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Extent of establishment of uniform standards concerning professional examinations in the public administration system (Number) |  |  | 0 (2019) |  | 3 | 3
Measure 1.4.8: Development of cooperation with higher education institutions to support schooling and/or additional education of staff for/in public administration
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Percentage of state administration bodies and units of local self-government participating in the student internship programme (%) |  |  | 0 (2020) |  | 9–10 | 10
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.8.1: Establishing an instrument to support the implementation of the public administration training and education system, equally focused on theory and practice | Q4 2024 | MPALSG | completed | - | This activity was completed ahead of schedule. A cooperation agreement was signed between 18 state and other bodies and 5 state universities. Before signing the agreement/programme, documents were prepared which were reviewed by the Government, which gave its consent to the Ministry of Public Administration and Local Self-Government, the Ministry of Education, Science and Technological Development, the Ministry of Foreign Affairs, the Ministry of Justice, the Ministry of Labour, Employment, Veteran and Social Affairs, the National Academy for Public Administration, the Public Policy Secretariat of the Republic of Serbia, the Human Resource Management Service, the Office for Information Technology and e-Government, the National Assembly of the Republic of Serbia, the Protector of Citizens, the Commissioner for Information of Public Importance and Personal Data Protection, the Commissioner for Protection of Equality, the City of Belgrade, the City of Niš, the City of Kragujevac, the City Administration of the City of Novi Pazar, and the City Administration of the City of Subotica, to conclude a Cooperation Agreement with the University of Belgrade, the University of Niš, and the State University of Novi Pazar concerning public administration's support to tertiary education institutions in the education process, as well as a Cooperation Programme concerning public administration's support to tertiary education institutions in the education process in 2021/2022. |  | . | Continuing to establish a framework for sustainable and dynamic cooperation in accordance with tertiary education objectives and PAR strategic objectives.
1.4.8.3: Organising an annual gathering Student Internships in Public Administration to promote professional training and development in public administration | Q4 2025 | MPALSG | completed | 100% | The first annual gathering “Student Internships in Public Administration” was organised and held with a view to promoting professional training and development in public administration. The first Student Internships Fair was held as a two-days gathering, through an online platform that was designed specifically for this purpose and was visualised by the Palace of Serbia. Thirteen state bodies, 5 local self-governments, 5 state universities and over 2,000 students took part in the Fair. During the 2021/2022 school year, over 400 state university students will have an opportunity to do an internship in SABs and LSGUs. |  | . | This activity will also be implemented in 2022.
Specific objective 1.5: PUBLIC ADMINISTRATION PROVIDES SERVICES IN AN EFFICIENT AND INNOVATIVE MANNER MATCHING THE NEEDS OF END USERS AND ENHANCES THEIR USER EXPERIENCE
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
SIGMA’s average score for service delivery for all four pillars (Grade 0–5) |  |  | 3 (2019) |  | 3,5–4 | 3.5 | http://www.sigmaweb.org/publications/Monitoring-Report-2021-Serbia.pdf
The GDP share of the administrative burden of citizens and businesses (%) |  |  | 3.11 (2018) |  | 3–3 | 3.01
Measure 1.5.1: Promoted development of new and optimisation of existing services tailored for end users
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Number of streamlined administrative procedures of citizens and businesses (Number) |  |  | 125 (2020) |  | 225–250 | 329
Number of one-stop shops set up in LSGUs (Number) |  |  | 14 (2020) |  | 17.1–19 | 19
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.5.1.1: Designing a methodology for the development of new and the optimisation of existing services based on a systematic involvement of end users in all the phases of the development through the use of advanced and innovative tools | Q3 2022 | PPS | In progress | - | Draft Decree on the Methodology for Regulation of Administrative Procedures |  | No deviation | Review of the document at the meeting of the Working Group, obtaining opinions, adoption by the Government.
1.5.1.2: Preparing the Programme for the Simplification of Administrative Procedures and Regulations for the next period (the e-Paper Programme from 2021 onwards) | Q2 2022 | PPS | In progress | - | Development of the e-PAPER Programme was initiated. Start of the development of the eConsultations Portal was announced, and starting points established in order to collect comments, suggestions and proposals. |  | No deviation | Draft Programme for the Simplification of Administrative Procedures and Regulations - “e-Paper” 2022–2025 was developed and adopted
1.5.1.3: Popularising the use of digital services, and increasing the availability of electronic certified signature issued by the certification body of the Ministry of Interior | Q4 2025 | MoI | In progress | - | On 2 February 2021, the e-Government Portal introduced the electronic service for citizens “Replacement of the driving licence”, which allows applications for replacement of a driving licence to be digitally signed with a certified electronic signature of the applicant. At all big ICT events in which the Ministry of Interior participates, a mobile team at the Ministry's stall issues certified electronic certificates. Over the last year, 900,000 promotional flyers were distributed to citizens through a counter for issuance of documents, for the purpose of a popularisation of identity cards with a chip and a certified electronic certificate for access to e-Government electronic services. |  | . | In collaboration with the Office for Information Technology and e-Government of the Government of the Republic of Serbia, services within the purview of the Ministry of Interior will be expanded at the e-Government Portal, which will allow citizens to sign applications/approvals with a certified electronic certificate. Activities on the popularisation of identity cards with a chip and certified electronic certificates for access to eGovernment electronic services will continue in the upcoming period, through promotional posters, distribution of flyers to citizens, etc.
1.5.1.4: Drafting the Guidelines for the choice of Priority Administrative Services to be digitalised (creating priority contactless services) | Q4 2021 | PPS | completed | - | Document has been prepared, and positive opinions of MPALSG and Office for IT and eGovernment obtained |  | No deviation | The document will be available at the PPS Portal and the Registry of Administrative Procedures Portal.
Measure 1.5.2: Raising human and technical-technological capacities of public administration for service delivery to end users
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Percentage of civil servants and local self-government employees in service delivery jobs who successfully completed a training in the area of service delivery quality improvement (%) |  |  | 0 (2020) |  | 9–10 | - | Not possible to calculate (National Academy for Public Administration)
EU Benchmark for e-Government – key prerequisites put in place (Index 0–100) |  |  | 35 (2020) |  | 31.5–35 | 43 | https://digital-strategy.ec.europa.eu/en/library/egovernment-benchmark-2021
Measure 1.5.3: Improved system of service quality control and quality assurance
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Number of SABs which have already implemented the CAF or any other quality management tool in the course of one calendar year, on the basis of the corresponding legal framework (Number) |  |  | 0 (2020) |  | 2 | 2
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.5.3.1: Creating a legal framework which prescribes the establishment of a comprehensive and updated electronic records of administrative procedures/a service in a form of a public registry | Q2 2021 | PPS | completed | - | Law on the Registry of Administrative Procedures was adopted (The Official Gazette of the Republic of Serbia, No. 44/21); |  | . | .
1.5.3.2: Translation of the CAF 2020 into the Serbian language | Q4 2021 | MPALSG | completed | 100% | https://caf.mduls.gov.rs/upload/media/0/0/0/11074/CAF-Smernice-2020.doc . |  | . | .
Specific objective 1.6: INCREASED LEVEL OF ACCOUNTABILITY AND TRANSPARENCY AT ALL LEVELS OF THE GOVERNMENT
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
EC's annual assessment of progress in the area of accountability (0 – No, 1 – Yes) |  |  | 0 (2020) |  | 0 | 0 | https://ec.europa.eu/neighbourhood-enlargement/document/download/fbe0f0b7-d8ff-4b89-a4ed-af5ccd289470_en
SIGMA indicator: accessibility of public information (Point/30) |  |  | 21 (2017) |  | 20–22 | 21.5 | http://www.sigmaweb.org/publications/Monitoring-Report-2021-Serbia.pdf
Measure 1.6.1: Establishment of systemic solutions for managerial accountability in public administration bodies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Percentage of state administration bodies with officials authorised to conduct administrative proceedings and decide in administrative matters (%) |  |  | 23 (2020) |  | 23.75–25 | 79.45 | Out of 73 state administration bodies, 58 SABs appointed officials authorised for conducting administrative proceedings and decision-making therein and implementing administrative actions.
Percentage of state administration bodies, independent bodies and LSGU bodies with officials who attended training on managerial accountability (%) |  |  | 0 (2020) |  | 0 | 0 | Implementation of the training has not started.
Measure 1.6.2: Improvement of the vertical and horizontal system of supervision and monitoring of work in public administration (established mechanism for performance management of public administration bodies)
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Percentage of priority objectives from the Action Plan for the Implementation of Government Programmes related to state administration bodies, which were taken into account in preparation of own (mandatory) medium-term plans (%) |  |  | 0 (2019) |  | 23.75–25 | 23.8 | The achieved value (23.8%) is considered an achievement of the target value, since a tolerance value of 5% was envisaged. A new APIGP is to be adopted by the new Government. The number of medium-term plans of institutions included in the APIGP is to be increased. No risks are expected with respect to the fulfilment of this indicator in the upcoming period.
Percentage of state administration bodies, independent state bodies and LSGUs with managers have attended a training on a single performance management methodology (%) |  |  | 0 (2020) |  | 0 | 0 | Implementation of the training has not started.
Measure 1.6.3: Strengthening integrity and ethical standards in public administration
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Percentage of state administration bodies and independent state bodies which organise and implement training in ethics and integrity for their managers and employees (%) |  |  | 0 (2020) |  | 23.75–25 | 81.8 | The Law on Prevention of Corruption prescribes criminal responsibility of a head of state body which fails to implement training in ethics and integrity for their managers and employees, and does not report to the Anti-Corruption Agency on the implementation of the training within the prescribed deadline. Due to this fact, a number of state bodies organised remote training in ethics and integrity for their employees and managers in 2021.
Measure 1.6.4: Promoting proactive disclosure of data held by public administration bodies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Number of public administration bodies and other holders of state bodies which/who publish open data on the Open Data Portal (Number) |  |  | 45 (2019) |  | 57–60 | 83
Percentage of state administration bodies and LSGU bodies whose employees attended training in open data standards and the Open Data Portal (%) |  |  | 0 (2020) |  | 4.75–5 | 8.57 | Employees of 61 SABs and LSGUs, out of 712 which are included in the NAPA database
Measure 1.6.5: Improving reactive transparency, acting according to regulations within the purview of independent state bodies, i.e. according to the recommendations of independent state bodies
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Percentage of execution of proposed, i.e. instructed measures of inspectoral supervision over the application of the statute on free access to public information (%) |  |  | 75 (2019) |  | 78.4–80 | 99
Percentage of execution acts of the Commissioner for information of Public Importance and Personal Data Protection (%) |  |  | 65 (2019) |  | 63.7–65 | 75.09
Percentage of executed documents by the Protector of Citizens (%) |  |  | 81.43 (2019) |  | 80.33–81.97 | 77,52
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.6.5.1: Amendments to the Law on Free Access to Information of Public Importance in order to increase accountability and transparency in the work of state bodies | Q4 2021 | MPALSG | completed | - | The Amendments to the Law on Free Access to Information of Public Importance have improved the independence of the Commissioner for Information of Public Importance and Personal Data Protection. They prescribe that the Speaker of the National Assembly will announce a public call to all stakeholders who meet the legally prescribed requirements, to apply for the status of a candidate. Parliamentary groups, as authorised proponents, may propose, as a candidate for the position of the Commissioner, only a person who is included on the list of candidates previously defined by the relevant committee of the National Assembly. Furthermore, the relevant committee is obliged, with a view to drawing up the list of candidates, to conduct an interview with all persons who had applied and who meet the legally prescribed requirements, and to allow them to present their views on the role and method of exercising the powers of these very important SABs. The Law explicitly prescribes that an interview which members of a relevant committee of NAPA conduct with a candidate must be public, guaranteeing greater transparency of the selection procedure, and ensuring a high level of public control. An eight-year mandate without a possibility of re-election is stipulated, which is to create conditions for a higher degree of functional independence of this body. In addition, the range of entities which are given the status of a state body and which are thus obliged to act in accordance with this law has been expanded, including public notaries and public enforcement officers, as holders of public powers, public enterprises, institutions, organisations and other legal persons which are incorporated by a legislative act or a decision of a body of the Republic of Serbia, an autonomous province or a local self-government unit, including urban municipalities, state-owned companies, companies owned or managed by such companies, and other state bodies. In addition, the Commissioner has been authorised to impose fines of up to 30,000 RSD on any person responsible for failing to act upon a request. This was done in order to prevent state bodies from ignoring requests for access to information of public importance, which is the most common reason for complaints submitted to the Commissioner. This new development considerably reduces the burden on misdemeanour courts, in view of the fact that persons requesting information will not be able to immediately initiate misdemeanour proceedings when a state body completely fails to respond to their request, but will have to first address the Commissioner and state their complaint. State bodies are obliged to publish all important data about their activity on their websites. Finally, the Law also increases the scope of the mandatory content of the Information Booklet. A compilation of information booklets in an electronic and machine-readable format is mandatory, in order to make it possible to search for needed information easily. A Unified Information System, used for publishing all information booklets, will be administered and maintained by the Commissioner. |  | . | .
1.6.5.2: Preparing new Instructions for Drafting and Publishing an Information Booklet | Q4 2022 | CIPIPDP | completed | - | Completed and sent to The Official Gazette for publication. A new instruction affirms the principle of proactive transparency, as a way to exercise the right to access information (Article 1 of the Law). The Information Booklet shall be published through the unified information system of the Information Booklet, administered and maintained by the Commissioner, in an electronic, machine-readable format. The Information Booklet shall be updated every 30 days. The range of information published has been expanded, together with the range of authorities which are obliged to compile an information booklet; failure to compile or update the Information Booklet shall be a misdemeanour, and the head of that body will be held responsible. |  | . | .
1.6.5.6: Amendments to the Law on the Protector of Citizens in order to increase accountability and transparency in the work of state bodies | Q4 2021 | MPALSG | completed | - | The new Law on the Protector of Citizens improves the independence of the Protector of Citizens, and creates conditions and a foundation for them to work more efficiently and effectively. The new Law prescribes that the Speaker of the National Assembly shall announce a public call to all stakeholders who meet the legally prescribed requirements, to apply for the status of a candidate. Parliamentary groups, as authorised proponents, may put forward, as a candidate for the position of the Protector of Citizens, only a person who is included on the list of candidates previously defined by the relevant committee of the National Assembly. Furthermore, the relevant committee is obliged, with a view to drawing up the list of candidates, to conduct an interview with all persons who had previously applied and who meet the legally prescribed requirements, and to allow them to present their views on the role and method of exercising the powers of these very important SABs. The Law explicitly prescribes that an interview which members of a relevant committee of NAPA conduct with a candidate must be public, guaranteeing greater transparency of the selection procedure, and ensuring a high level of public control. The stipulated mandate is considerably longer than eight years. A mandate of the Protector of Citizens is considerably longer than the mandates of other state bodies, especially the National Assembly and the Government, without a possibility of re-election, creates conditions for a greater degree of functional independence of the Protector of Citizens. Furthermore, without the authorisation to approve general acts on the organisation and systematisation of tasks of an expert service, the competent committee of the National Assembly is unable to obstruct the adoption of theses exceptionally important general acts. The budgetary and financial independence of the Protector of Citizens was improved by prescribing that annual operational funds of the Protector of Citizens should be sufficient to allow them to effectively and efficiently exercise their mandate, and that they may not be reduced, unless the reduction of operational funds also applies to other beneficiaries of budgetary resources. The Protector of Citizens is designated by the new Law to exercise the powers of an independent national mechanism for monitoring the implementation of two international conventions, namely: the Convention on the Rights of Persons with Disabilities, and the Council of Europe Convention on Action against Trafficking in Human Beings. The Protector of Citizens is authorised to submit an initiative to a state administration body/state body whose activity is under the control of the Protector of Citizens, for amending statutes, regulations, administrative actions or general acts, if the Protector of Citizens believes that citizens’ rights have been violated due to any flaw in the legislation, and to initiate adoption of new statutes, regulations, administrative actions or general acts, if the Protector of Citizens believes that it is important for exercise and protection of citizens’ rights. In addition, the Protector of Citizens is authorised to give their opinion to the state administration body/state body whose activity is under the control of the Protector of Citizens, about draft laws, regulations and administrative actions, if they regulate matters of importance for the protection of citizens’ rights. The Protector of Citizens is expressly authorised by the new Law to implement the procedure of controlling the state administration body before initiating proceedings before the competent court. Finally, new rules of procedure have created conditions for the Protector of Citizens to control the administration more efficiently and effectively. Procedural interventions, such as introductions of the shortened procedure and the investigation procedure, as well as prescribing deadlines for actions, ensure greater procedural predictability of the actions by the Protector of Citizens in individual cases and ensure conditions for greater procedural predictability for citizens when they submit their appeals to the Protector of Citizens. |  | . | .
Specific objective 1.7: EXECUTION OF A SUSTAINABLE BUDGET WITH A STABLE PUBLIC DEBT-TO-GDP RATIO, HELPED BY BETTER FINANCIAL MANAGEMENT AND CONTROL, AUDIT PROCESS AND CONNECTING BUDGET PLANNING WITH THE GOVERNMENT POLICIES
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Real growth of the Gross Domestic Product (GDP) (%) |  |  | 0 (2020) |  | 5–6 | 7.5
General government debt-to-GDP (%) |  |  | 59 (2020) |  | 58.7–59.87 | 57.5
Measure 1.7.1: SPECIFIC OBJECTIVE 1 of the Public Financial Management Reform Programme — IMPROVED CAPACITIES FOR BUDGET PLANNING AND PUBLIC INVESTMENT MANAGEMENT
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Public service delivery performance data (PEFA: 4 – А, 3.5 – B+, 3 – B, 2.5 – C+, 2 – C, 1.5 – D+, 1 – D, 1 – D*) |  |  | 2.5 (2020) |  | 2.5 | 2.5
Measure 1.7.2: SPECIFIC OBJECTIVE 2 of the Public Financial Management Reform Programme — EFFICIENT COLLECTION AND MANAGEMENT OF PUBLIC FUNDS
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Actual revenues and expenditures of the general government budget at annual level are within the range of 5% of those projected in the fiscal strategy (%) (%) |  |  | 5 (2019) |  | 5 | 5 | Actual revenues and expenditures are in the 5% range compared to the projections in the Fiscal Strategy.
Average duration of an open procedure (Number) |  |  | 52 (2020) |  | 50 | 48
Annual cost of public debt servicing (interest payment – net amount) as % of the GDP (%) |  |  | 1.9 (2020) |  | 1.9 | 1.6
Measure 1.7.3: SPECIFIC OBJECTIVE 3 of the Public Financial Management Reform Programme — IMPROVED BUDGETARY DISCIPLINE AND MORE TRANSPARENT USE OF PUBLIC FUNDS
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Average number of illegalities and irregularities per control in relation to the total number of controls (Number) |  |  | 2 (2020) |  | 2–2.2 | 3
Percentage of accepted and implemented recommendations which an audit body issues to subjects of indirect EU funds management (%) |  |  | 0 (2020) |  | 45–50 | 91
Measure 1.7.4: SPECIFIC OBJECTIVE 4 of the Public Financial Management Reform Programme — IMPROVEMENT OF THE INTERNAL FINANCIAL CONTROL IN PUBLIC SECTOR
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
PIFC-related progress identified in the EC progress report on the Republic of Serbia for a specific year (EC's assessment following the General Assessment of Preparedness value scale: 1 – Early stage of preparedness, 2 – Some level of preparedness, 3 – Moderate preparedness, 4 – Good level of preparedness) |  |  | 3 (2020) |  | 3 | 3 | Moderate preparedness – good progress achieved EC recommendations from 2020 have mostly been implemented
Measure 1.7.5: SPECIFIC OBJECTIVE 5 of the Public Financial Management Reform Programme — IMPROVED ACCOUNTING IN THE PUBLIC SECTOR WITH THE APPLICATION OF INTERNATIONAL PUBLIC SECTOR ACCOUNTING STANDARDS (IPSAS)
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Financial report prepared and presented to the Ministry of Finance of the Republic of Serbia in accordance with Cash Basis IPSAS (Number) |  |  | 0 (2020) |  | 0 | 0
Measure 1.7.6: SPECIFIC OBJECTIVE 6 of the Public Financial Management Reform Programme — STRENGTHENING OF EXTERNAL SUPERVISION OF PUBLIC FINANCES
Institution in charge: MINISTRY OF FINANCE
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Number of reviewed audit reports (Number) |  |  | 194 (2020) |  | 194.75–205 | 205
Specific objective 1.8: ESTABLISHED SYSTEM OF LOCAL SELF-GOVERNMENT THAT ENABLES EFFECTIVE AND SUSTAINABLE EXERCISE OF CITIZENS' RIGHTS TO LOCAL SELF-GOVERNMENT
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Compliance of the local self-government system with the key principles of the European Charter of Local Self-Government (Composite scale (1–5)) |  |  | 3 (2020) |  | 3 | 3
Share of LSG expenditures and consolidated public expenditures in the Republic of Serbia (%) |  |  | 14.75 (2019) |  | 15–12 | 12
The capacity of LSGUs to implement the principles of good governance (%) |  |  | 39 (2018) |  | 40–43 | 47 | The achieved value was entered as the measure of achievement of the Standing Conference of Towns and Municipalities (SCTM) Index.
Availability and quality of implementation of priority public services by LSG (Composite scale (1–10)) |  |  | 0 |  | - | - | In accordance with the adopted AP of the Program for the Reform of the Local Self-Government System in the Republic of Serbia 2021−2023, the target value was not envisaged for 2021.
Measure 1.8.1: SPECIFIC OBJECTIVE 1 of the Local Self-Government System Reform Programme — IMPROVING THE POSITION AND ACCOUNTABILITY OF LOCAL SELF-GOVERNMENT
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Level of ratification of the European Charter of Local Self-Government (Composite scale (1–5)) |  |  | 3 (2020) |  | 3 | 3
Average index value in selected areas: 1) accountability; 2) transparency, openness and participation (%) |  |  | 43 (2018) |  | 42.75–45 | 53 | The achieved value was entered as the measure of achievement of the Standing Conference of Towns and Municipalities (SCTM) Index in 2021.
The share of adopted laws in the total number of adopted laws which concern local self-government to a larger degree, which were prepared with the participation of LSGUs Scale (1–5)) |  |  | 3 (2020) |  | 3 | 3 | The achieved value was entered on the basis of data submitted by the SCTM.
Measure 1.8.2: SPECIFIC OBJECTIVE 2 of the Local Self-Government System Reform Programme — IMPROVEMENT OF THE LOCAL SELF-GOVERNMENT FINANCING SYSTEM
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Share of LSG tax revenues in total tax revenues in the Republic of Serbia (%) |  |  | 10.12 (2020) |  | 10.35–10.4 | 10.1
Share of capital expenditures in total expenditures of local self-government (%) |  |  | 15.54 (2019) |  | 15.92–16 | 17.3 | The share of realised capital expenditures also includes the respective transfers to other government levels
Share of LSGUs which have adopted medium-term plans (%) |  |  | 0 (2020) |  | 0 | 0 | In accordance with the adopted AP of the Program for the Reform of the Local Self-Government System in the Republic of Serbia 2021−2023, the target value was not envisaged for 2021.
Measure 1.8.3: SPECIFIC OBJECTIVE 3 of the Local Self-Government System Reform Programme — IMPROVING THE ORGANISATION AND CAPACITY OF LOCAL SELF-GOVERNMENT
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
LSGU capacity for HRM in local administration (%) |  |  | 51 (2020) |  | 53.2–56 | 59.3 | The last survey was conducted in Q2 2021 using a SCTM questionnaire about human resource management. The survey was conducted on a sample of 70 LSGUs.
Share of LSGUs which have established inter-municipal cooperation in the total number of LSGUs (%) |  |  | 27 (2020) |  | 31 | 36
Measure 1.8.4: SPECIFIC OBJECTIVE 4 of the Local Self-Government System Reform Programme — IMPROVING QUALITY AND ACCESSIBILITY OF SERVICES DELIVERED BY LOCAL ADMINISTRATION, UTILITY COMPANIES AND PUBLIC INSTITUTIONS
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Index to measure availability and quality of services delivered by LSGUs developed (0 – no, 1 – yes) |  |  | 0 (2020) |  | - | - | In accordance with the adopted Public Administration Reform Strategy, target value was not set for 2021.
Index to measure user satisfaction with services delivered by local self-government developed (0 – no, 1 – yes) |  |  | 0 (2020) |  | - | - | In accordance with the adopted Public Administration Reform Strategy, target value was not set for 2021.
Specific objective 1.9: COORDINATION AND COMMUNICATION
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Measure 1.9.1: Ensure efficient coordination and monitoring of PAR Action Plan measures and activities
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Number of public policy documents pertaining to PAR, the monitoring results of which are available through the OMT (Number) |  |  | 1 (2020) |  | 3 | 4
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.9.1.7: Developing a new mid-term PAR expenditure framework | Q4 2021 | MPALSG | In progress | 15% | The medium-term framework is harmonized with the Action Plan of the PAR Strategy 2021-2025. |  | Delays in the adoption of the Program for Improving Public Policy Management and Regulatory Reform, the Public Financial Management Program and the Local Government Reform Program. | Integration of the adopted three new programs in the medium-term expenditure framework.
Measure 1.9.2: Ensure efficient coordination of donor support to PAR
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Number of active and trained non-managerial staff working in the sector for European integration and international cooperation (Number) |  |  | 6 (2020) |  | 6 | 10 | Three employees attended the training “Using the UIS for planning, monitoring of implementation, public policy coordination and reporting”. Two employees attended the training “Exemption from taxes and customs duties in the Decentralised System”. Three employees attended the training “Workload analysis”. One employee attended the training “Regional Conference on IPA III” and “Regional Conference on Policy Co-ordination with the Inauguration of the Network of Policy co-ordinators in Western Balkans”. All above training sessions correspond to the indicator description.
Measure 1.9.3: Establishing a functional coordination mechanism for planning, implementation and monitoring of PAR communication at the national level
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Annual operational plan for PAR communication by the Coordination body in place (Number) |  |  | 0 (2020) |  | 1 | 1 | Since a mechanism for coordinating PAR communication was not created in 2021, the 2021 Communications Operational Plan was prepared under the EU project “Visibility and Communication of Support for the Public Administration Reform” on the basis of 2021 activities stipulated in the Action Plan 2021–2025 for the Implementation of the Public Administration Reform Strategy in the Republic of Serbia.
Level of fulfilment of annual operational plans for PAR communication (%) |  |  | 0 (2020) |  | 80 | 80 | The percentage of achievement of the 2021 Annual Operational Plan for PAR Communication is below the target value because the implementation of some activities was postponed.
Measure 1.9.4: Harmonisation, standardisation and continuous PAR communication in public administration
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Proportion of SABs and LSGUs that publish PAR-related information in a standardised manner on the e-Notice Board (%) |  |  | 25 (2020) |  | 50 | 0 | By a decision of MPALSG, the implementation of the activity was postponed for 2023.
Total number of trained public relations and human resources management staff in SABs and LSGUs (Number) |  |  | 0 (2020) |  | 200 | 0 | Due to the ongoing COVID-19 pandemic, it was not possible to organise in-person training in 2021. In 2021, in agreement with the National Academy for Public Administration, activities were oriented towards preparing a special set of online training which would be delivered through the online training platform of the National Academy for Public Administration. Thus, the range of potential users and the possibilities to implement training sessions has been expanded. Training developed in such a manner will be accessible to users at any time and from any location, greatly facilitating the learning process. For that reason, the implementation of training has been postponed for 2022.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.9.4.3: Improving technical capacity and functionality of the e-Notice Board for use (user access and content management) by all public administration bodies | 3Q 2021 -> 3Q 2023 | MPALSG | Has not commenced | - | This activity was not implemented in 2021. . |  | MPALSG was not able to implement this activity in 2021, and it was consequently postponed. | By a decision of MPALSG, the implementation of the activity was postponed for 2023..
Measure 1.9.5: Increasing visibility and communication of the PAR process and results
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Explanation
Number of affirmative and neutral posts (feature stories) about the public (Number) |  |  | 1,178 (2020) |  | 1296 | 1681 | The resulting value was obtained by analysing media features collected from reports developed by the agency NINAMEDIA for MPALSG.
Presence of PAR topics on institutions' websites and social media pages / profiles (Number) |  |  | 146 (2020) |  | 161 | 290 | The resulting value was obtained by analysing posts on websites and social network accounts of 21 institutions. A total of 21 websites and 35 social network accounts of these institutions were analysed.
Proportion of citizens who are informed about the results of the public administration reform (%) |  |  | 0 (2020) |  | 28 | 29 | The resulting value was obtained through an annual public opinion survey on citizens’ awareness on the public administration reform, which was implemented by the EU project “Visibility and Communication of Support for the Public Administration Reform” in collaboration with MPALSG in November and December 2021.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.9.5.1: SAB and LSGU capacity mapping for PAR communication (organisation of public relations activities, communication channels, technical capacities, level of training, etc.). Survey and two focus groups. | Q2 2021 | MPALSG | completed | 100% | This activity was implemented in collaboration with the EU project “Visibility and Communication of Support for the Public Administration Reform”, MPALSG, NAPA and the Office of the Prime Minister of the Republic of Serbia. . |  | . | .
1.9.5.2: Development of PAR Communication Standards with guidelines for the application of unique visual solutions, targeted messages and slogans ensuring that SABs and LSGUs coherently inform the public about PAR | Q3 2021 | MPALSG | completed | 100% | Experts from the EU project “Visibility and Communication of Support for the Public Administration Reform”, in consultations with MPALSG and the Office of the Prime Minister of the Republic of Serbia, prepared a draft document, which was subsequently transmitted to public administration bodies for approval. After the approval, the document was finalised and designed. . |  | . | .
1.9.5.3: Distribution of PAR communication standards to all SABs and LSGUs | Q2 2021 | MPALSG | completed | - | The document was distributed to representatives for communication of PAR, CSOs and LSGUs at the meetings held on 12 October and 15 October. |  | . | .
1.9.5.5: Workshops for SAB managers (state secretaries and assistant ministers) and PR officers on the importance of communicating the PAR process and results achieved. | Q4 2021 | NAPA | In progress | 41.77% | Due to the aggravated epidemic situation, it was decided to develop online training sessions, instead of in-person workshops, on the following 6 subjects in this field: Modern customer-oriented service to citizens and businesses, Communicator, Key terms and definitions in social media – learn & check your knowledge, PAR visibility & communication on social media, Effective crisis communication, and Public speech, whose development requires more time and resources to be allocated for this activity. . |  | Due to the ongoing COVID-19 pandemic, it was not possible to implement this action in 2021. | Its implementation was postponed for 2022.
1.9.5.11: Raising citizens' awareness of their rights before public administration bodies when it comes to eZUP services through posts on social media, media publications in national and local media, posters in SABs and LSGUs | Q2 2021 | MPALSG | completed | 100% | This activity was implemented through a video recorded in December 2021 and posted to the MPALSG’s social media accounts, with a paid promotional campaign, which lasted from 28 December 2021 to 31 January 2022. The video was made and promoted with the financial support of the EU project “Visibility and Communication of Support for the Public Administration Reform”. |  | . | .
1.9.5.20: Promotion of the Registry of Administrative Procedures (organisation of a presentation event, conducting media promotion on national and local media and social networks) | Q3 2021 -> Q3 2022 | PPS | completed | 100% | The Registry has been established, and data on administrative procedures entered in it have been publicly available since June 2021. In the previous period, the Registry was promoted through all kinds of media and social networks. |  | . | .
1.9.5.21: Promotion of the e-Paper Programme (visual and technical improvement and promotion of the e-Paper website) | Q4 2021 | PPS | completed | 20% | A new and improved website has been launched at www.epapir.gov.rs . |  | . | .