## Sve aktivnosti export_1
Annual Report on the Implementation of the 2021 Action Plan for the: |  |  |  |  | Implementation of the e-Government Development Programme of the Republic of Serbia 2020−2022
Institution responsible for coordination and reporting: |  |  |  |  | MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Public policy document elaborated by the Action Plan: |  |  |  |  | e-Government Development Programme of the Republic of Serbia 2020−2022
Overall objective 1: Development of an efficient and user-centric administration in a digital environment
Document proponent: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT (MPALSG)
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
EU benchmark for e-Government (%) |  |  | 37 (2019) |  | 49.16−51.75 | 50 | The latest e-Government Benchmark Report for 2021 (available at: https://digital-strategy.ec.europa.eu/en/library/egovernment-benchmark-2021) suggests that the Republic of Serbia has made a moderate progress in the area of electronic government development, i.e. that progress was noted in three out of the four measuring or evaluation dimensions of e-government development (user centricity, transparency, key enablers, cross-border mobility). With the overall maturity score of 50%, the Republic of Serbia is ahead of Albania, Romania, the Republic of North Macedonia, and Montenegro. The Report states that the COVID-19 pandemic has brought great turbulence in all countries around the world, but that it has also accelerated changes, boosted digital development, and stimulated governments to innovate and to upgrade their electronic tools and services. According to the Report, the Republic of Serbia is one of the countries which has managed to accelerate its digitalisation efforts, developing new online services for users. Looking at the overall score, this year's leaders in the area of e-Government on the Old continent are Malta (96%), Estonia (92%), Germany and Finland (85%). The Report noted that digital transformation remains the focus of all EU countries. Since 2012, the European Commission has been applying the e-Government Benchmark methodology to track development and delivery of electronic services to end users in 36 European countries. This methodology also serves to assess the need for information and communication technologies of public administration bodies in EU Member States. This methodology further covers other countries such as: Island, Norway, Switzerland, Great Britain, Albania, Montenegro, the Republic of North Macedonia, Serbia, and Turkey. For the purpose of drafting a detailed report on the progress in the area of electronic government, during August–September of last year, 7,872 websites of public administration bodies were reviewed, tested, and evaluated, and users responded to 48 [survey] questions about 8 key life events.
Specific objective 1: Development of e-Government infrastructure and ensuring interoperability
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT (ITE OFFICE)
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of public authorities using centres for storing and managing data in production and/or in operational use (Number) |  |  | 37 (2019) |  | 95−100 | 97
Number of LSGUs using centres for storing and managing data in production, i.e. in operational use (Number) |  |  | 0 (2019) |  | 20 | 170
Number of services downloading data from the Central Population Register (Number) |  |  | 0 (2019) |  | 5 | 4
Measure 1.1.1: Establishing State Data Management and Storage Centre in Kragujevac − Data Centre Kragujevac and Improvement of the State Data Management and Storage Centre in Belgrade − Data Centre Belgrade
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of registers migrated to data centres (Number) |  |  | 0 (2019) |  | 35 | 83
Number of software solutions migrated to data centres (Number) |  |  | 0 (2019) |  | 25 | 144
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.1.1: Adoption of by-laws to regulate the data management and storage infrastructure; | Q1 2020 -> Q4 2021 | MPALSG | Completed | - | The adoption of the Decree on the Maintenance and Improvement of the State Data Management and Storage Centre signifies the completion of the legal framework for the operability of e-Government in Serbia. The RS Government adopted the proposal of the said Decree on 10 February 2022. The adoption of the Decree was only possible after the construction of a suitable complex physical and virtual infrastructure of the Data Centre, and once it was determined which innovative technologies would be used in Data Centre. The risk of adopting the Decree sooner was that the Decree would not reflect the progress of implementation nor the implemented technical and technological solutions. Practice had shown that it was better to hold the adoption of the bylaw than to risk it not being aligned with the modern information and communication technologies, standards of protection, and infrastructural demands... |  | .
1.1.1.3: Drafting the initial plan of migration and assessment of the readiness of applications to be migrated to the cloud; Improvement of the migration plan and assessment of the readiness of applications to be migrated to the cloud; | Q4 2020 -> Q4 2021 | ITE Office | Completed | - | Processes have been established, and pre-conditions addressed. The activity is being implemented continuously. |  | . | System migration according to system owner's capabilities and plans. The activity is being implemented continuously.
1.1.1.5: Initial furnishing of facility 1 of Data Centre Kragujevac with ICT equipment; | Q3 2020.-> Q4 2021 -> Q4 2022 | ITE Office | In progress | - | The initial furnishing of the Data Centre has been completed, and the Data Centre is ready for Telehousing. |  | . | A new deadline for the completion of this activity has been set: until the end of the Programme validity. However, this activity will be extended beyond that, until Q1 2023. The public procurement call announcement is expected by the end of January 2022. The expected timeline for signing the contract: early May 2022.
Measure 1.1.2: Improving the Unified Information-Communication Network of e-Government
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Percentage of LSGUs connected to the UIC network (%) |  |  | 0 (2019) |  | 60 | 95 | Out of the total of 179 LSGUs, 170 LSGUs have been connected to the UIC network, which is 95%.
Number of established redundant nodes in Belgrade (Number) |  |  | 0 (2019) |  | 3 | 40
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.2.2: Establishing a NOC (Network Operation Centre); | Q4 2021. -> Q3 2022 | ITE Office | In progress | - | Phase 1 has been completed, i.e. NOC (Network Operation Centre) has been set-up in the Kragujevac Data Centre. For phase 2, it is necessary to establish NOCs for the entire network. |  | . | A new deadline for completing phase 2 has been set: Q3 2022.
1.1.2.3: Establishing redundant nodes in Belgrade; | Q 4 2020 -> Q 4 2021 -> Q 4 2022 | ITE Office | In progress | - | A procurement evaluation report has been completed. The deadline has been extended until the validity of the e-Government Development Programme, but this activity will be implemented in Q1 2023. |  | Extended processes of approving the specifications.. | A new deadline for the implementation of the activity has been set: Q1 2023.
Measure 1.1.3: Establishing a unified Register Office, e-Archive and integration with existing systems
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of institutions using the Register Office as a primary tool (%) |  |  | 0 (2019) |  | 30 | 0 | According to the Decree, the Register Office is to open on 1 February 2022. The Decree on Office Operations of State Administration Bodies, No. 21/2020-41
Number of institutions which have integrated the existing software solutions into the e-Register Office and e-Archive (%) |  |  | 0 (2019) |  | 50 | 0 | According to the Decree, the Register Office is to open on 1 February 2022. The Decree on Office Operations of State Administration Bodies, No. 21/2020-41
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.3.2: Establishment of a unified Register with e-Storage and integration with the e-Delivery and e-Archive systems and other systems; | Q4 2021 -> Q4 2022 | ITE Office | In progress | 100% | The deadline has been extended until the end of e-Government Development Programme validity, but this activity will be implemented in Q2 2024 (integration with the e-Archive will follow after the e-Archive software solution has been developed) . |  | According to the Decree, the Register Office is to open on 1 February 2022. | A new deadline for the completion of this activity has been set: until the end of the e-Government Development Programme validity. However, this activity will be extended beyond that, until Q2 2024. The activity will be proposed in the revised Programme and its AP 2023–25.
Measure 1.1.4: Development of other joint (shared) IT services for public administration purposes
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of state bodies integrated into the collaboration system (%) |  |  | 5 (2019) |  | 25 | 35 | The plan is to integrate another 50 LSGUs into the Unified Information System during 2022.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.4.2: Implementation of the mandatory use of gov.rs and упр.срб domains for all public administration bodies; | Q4 2020 -> Q4 2021 | ITE Office | Completed | - | Implemented. The activity is a continuous one. There are currently 415 .gov.rs domains, and 88 упр.срб domains. |  | . | .
1.1.4.3: Improvement of the service for the use of e-mail accounts for authorised officials (technological improvement). | Q3 2020 -> Q4 2021 | ITE Office | Completed | - | Implemented. The activity is a continuous one. There are currently 12,352 active e-mail accounts. |  | . | .
1.1.4.4: Improvement of the use of collaboration systems in public administration (joint work on documents, provision of opinions, common calendar, joint projects, etc.); | Q1 2021 | ITE Office | Completed | - | The e-Consultation Portal has been launched. The activity has been completed. |  | . | The plan is to integrate another 50 LSGUs into the Unified Information-Communication System during 2022.
Measure 1.1.5: Development of architecture and implementation of a Platform supporting the development and use of e-Government services
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of implemented e-Government services (Number) |  |  | 5 (2019) |  | 130 | 196
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.5.1: Establishing the Metaregister; Ensuring interoperability in e-Government; | Q2 2021 -> Q4 2022 | ITE Office | In progress | - | Consolidation of the required technical specifications. |  | Extended processes of approving the specifications.. | A new deadline for the completion of this activity has been set: until the end of the e-Government Development Programme validity. However, this activity will be extended beyond that, until Q2 2024. The activity will be proposed in the revised Programme and its AP 2023–25.
Measure 1.1.6: Establishing new and improving existing registers and records in electronic form to support the development of e-Government services
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Percentage of established registers compared to the total number of registers covered under this measure (%) |  |  | 10 (2019) |  | 60 | 60 | This measure covers the following registers: 1. Central Population Register; – activity completed: the Central Population Register was launched on 1 September 2020. 2. Address Register – the Republic Geodetic Authority has stated in the Annual Report on the Implementation of the e-Government Development Programme that activity 1.1.6.2: Establishment of an up-to-date Address register (improvement of the software solution and entry of missing data) and Register of Spatial Units has been completed. 3. Social Welfare IS; – SOZIS has been established. The system has been launched into production (Ministry of Labour, Employment, Veteran, and Social Affairs); 4. Unified IS Social Card; – In February 2021, the Law on Social Card (The Official Gazette of the Republic of Serbia, No. 14/2021) was passed, which was a necessary requirement to connect external databases, i.e. records of other bodies and institutions. A by-law – the Rulebook on Detailed Technical Requirements for Establishing and Managing the Social Card Register was adopted within 6 months of the Law adoption, i.e. on 2 July 2021 (The Official Gazette of the Republic of Serbia, No. 67/2021). Following the adoption of the Law, on 13 April 2021 a public procurement for the Social Card Register–phase 2 was initiated. The procurement exercise was completed, and the resulting contract with the winning bidder was concluded on 9 June 2021, with the product delivery deadline of 15 February 2022. The practical implementation of the contract is on-going, and it comprises six phases: project launch, analysis and design, development of the application software, integration with external and internal data sources, migrating the system to a production environment which includes a final test run, training and the start of production, launching into production, and utilisation by data users. Most recently, activities related to the phase of integration with source records have been successfully implemented, whereby records of five bodies of public administration (MPALSG, PDIF, MoI, NEB, RGA) were connected in a test run. This phase was very complex in terms of implementation, in both the procedural and technical sense. This phase conditions the success of data collection in the Social Card Register, i.e. the success of its very operability. To date, the first four phases have been implemented, and the phase relating to creating a production environment is underway. The following phase will concern the practical application of the [designed] solutions. The Tax Authority has stated that because fiscalisation was a priority, integration with their records would be completed this month. Integration of the Social Card with the electronic identification system of the Office for IT and eGovernment, with a re-direction to the Social Card, has been successful. This enables user authentication with a method of high reliability in accordance with the requirements for e-Government development in the Republic of Serbia. The conclusion is that there are no problems with the implementation of activity 1.1.6.4. The original deadline (Q4 2020) defined in the Action Plan for the Implementation of the e-Government Development Programme 2020–2022 was moved because the Law on Social Card was not adopted in 2019 as planned. The Law was in fact adopted in February 2021 when legal basis for the adoption was established. The legal deadline for the Register launch is 1 March 2022. 5. Improvement of the Property Register – Real-Estate Cadastre; – Improvements to the real-estate cadastre system in the Republic Geodetic Authority are being done as part of the Improving Real-Estate Management Project, with the support of the World Bank. The Project commenced in late 2015 and will last through 2022. Status update on the following: - Project phase 1 has been completed – document management system and business process management system have been implemented in all organisational units of the RGA - Project phase 2 has been completed – the information systems of the Address Register and the Register of Spatial Units have been developed and implemented - the information system of the Central Digital Cadastre Plan has been developed and implemented - the phase of improving data quality and integrating digital cadastre plans into the Central Information System of the Digital Cadastre Plan is on-going. 50 services out of the total 164 planned have been covered. Deadline for completion: December 2022. - currently in progress: Address Register update, developing a study of the street system. To date, 126 municipalities out of 164 have been covered. Planned date of completion: by the end of June 2022. - certified electronic seal introduced on all outgoing documents of the Republic Geodetic Authority - web services for the real-estate cadastre and all other data of the Republic Geodetic Authority have been developed and made available to all public sector institutions through the service bus (eZUP) of state bodies and the Internet, within the distribution geospatial platform GeoSerbia - Real-estate Price Register has been launched. A draft model of mass real-estate valuation for parts of buildings has been prepared. - Project phase 3 implementation has commenced – information system has been developed, testing has been completed, and implementation has commenced. System implementation and integration of alphanumerical and graphical data have been completed in Savski venac Municipality, and only initiated in Sopot Municipality. Completion is planned for the entire City of Belgrade, Novi Sad, Niš, and Kragujevac by the end of 2022. Completion of the system implementation for the whole territory of the Republic of Serbia is planned for the end of 2023. - satellite imagery of very high resolution acquired in 2016 and 2021. Register of Buildings has been developed – a record of objects not in the real-estate cadastre. - digital geospatial platform GeoSerbia has been developed. Over 330 data of over 32 public sector institutions in Serbia have been integrated. - the legal framework for the real-estate cadastre registration procedure has been amended. - the average timeline for case processing has reduced from 49 days to 4 when it comes to first-instance decisions, and to 60 days when it comes to second-instance decisions, in accordance with the law. - introducing ERP and BI has commenced. 6. Improvement of the Register of Businesses; – In 2019, a project for analysing and designing a new information system for managing the Register of Businesses was completed. On the basis of that project's results and the need for continued upgrading of the business registration system, in 2021 a public procurement of services for the development of a new e-registration system was conducted. The development of the new software solution should be finalised in 2022, and it is to enable submission of all kinds of applications for registration and improve existing operating procedures of the Register of Businesses by supporting a full electronic registration of all data changes which are legally defined as subjects of registration. Aside submitting applications for registration, the new system is meant to enable electronic submissions of requests which initiate the provision of other services by the Serbian Business Registers Agency (SBRA), primarily the issuance of database excerpts, confirmation of legal succession, etc. For the e-registration procedures to be conducted successfully, it is necessary to simultaneously upgrade the existing Register of Businesses management software. The development of the Register management software was planned for 2022, which would be the second step in building the SBRA's new information system that would allow for other status registers (and not only the Register of Businesses) to operate at a higher business level and, thus, support the entire e-registration idea. This would conclude the processes initiated in 2021, and the new system should facilitate better communication between state bodies, between state bodies and business, and among businesses themselves. When it comes to integration with other e-Government systems, the Register of Bidders has proven to be specially important in terms of the need to elevate the legality and efficiency of public procurement procedures. As a results, the National Alliance for Local Economic Development (NALED) has budgeted for the Register software upgrade, as part of the Effective Public Procurement in the Service of Economic Growth Project. The software upgrading commenced in 2021, and the deadline for completion is August 2022. The software upgrade will entail, among other things, integration of the Register of Bidders with the records of competent state administration bodies, through the service bus (eZUP). It should be noted that on 1 November 2020, the SBRA integrated with the Address Register which is managed by the RGA. 7. Unified Public Register of Administrative Procedures; 8. Digitalisation of the Register of Agricultural Farms (e-Agrar) – not completed; 8. Improvement of the veteran-disability protection IS; – in progress; 9. Improvement of the child and family protection IS. – In 2020, the anticipated amendments to the Law on Financial Support to Families with Children, which would have been a reason to improve the system, did not happen. Thus, the deadline for completing this activity has been pushed to 2022.
Number of institutions using data from the Register (Number) |  |  | 300 (2019) |  | 3000 | 321 | Number of bodies which exchange data electronically via the service bus on a daily basis.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.6.3: Establishment of the Social Welfare IS (SOZIS) (setting up a hardware-software platform, designing a software solution, migrating data from the social welfare centres' and the MLEVSA's data bases, and putting it into operation). | Q4 2021 | MLEVSA | Completed | 100% | The activity Establishment of the Social Welfare IS (SOZIS) has been completed. The system was launched on 9 December 2021. Full application is expected once the integration with the central e-Register Office and the migration of all data from the social welfare centres are completed in 2022. |  | . | .
1.1.6.8: Improvement of the veteran-disability protection IS; | Q2 2021 -> Q4 2022 | MLEVSA | In progress | - | . |  | The activity Improvement of the veteran-disability protection IS has not been implemented due to the lack of necessary funding in 2021. | .
Measure 1.1.7: Establishing a unified Public Register of Procedures
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA (PPS)
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Public Register of Administrative Procedures up and running (1 – the Register set-up, 2 – Publicly available Register containing all administrative procedures concerning businesses, 3 – Publicly available Register containing all administrative procedures concerning citizens) |  |  | 0 (2019) |  | 2 | 2
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.7.2: Adoption of by-laws based on the Law that would regulate the establishment and functioning of the Register; | Q4 2020 -> Q3 2021 -> Q3 2022 | PPS | In progress | - | Decree on Management, Functioning and Verification of Data Entered into the Register of Administrative Procedures, Portal Content, Data Entry, Changes and Deletion has been in the consultative process since 16 December 2021, via the e-Consultation Portal. |  | The Public Administration Reform Strategy prescribes a new deadline for this activities which is being followed now. Activity 1.5.1.1. envisages Q3 2022 as the deadline. | In February 2022, the Working Group will hold a meeting to decide on the final text of the Decree on Management, Functioning and Verification of Data Entered into the Register of Administrative Procedures, Portal Content, Data Entry, Changes and Deletion. Afterwards, the public hearing will be announced...
1.1.7.7: A detailed list of all remaining administrative procedures concerning citizens at the central level | Q2 2021 -> Q4 2022 | PPS | In progress | - | 1,948 administrative procedures concerning citizens, conducted by 111 bodies of public administration, have been mapped. The listing of the first 150 procedures, identified as priority in accordance with the set methodology, has commenced. By the end of 2021, 101 administrative procedure was entered into the Register of Administrative Procedures. . |  | In accordance with Article 17(3) of the Law on Administrative Procedures (The Official Gazette of the Republic of Serbia, No. 44/21), 1 January 2023 has been prescribed as the deadline for completing the list of administrative procedures concerning citizens. | Administrative procedures concerning citizens will be listed by the end of 2022..
Measure 1.1.8: Improving public administration human resources to establish and apply information technologies in e-Government
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of public administration employees certified for ITIL (Number) |  |  | 0 (2019) |  | 60 | 0 | Data not available.
Number of systematised and filled jobs for IT officers in state administration (0–1 out of 100, 1–1 out of 75, 2–1 out of 50, 3–1 out of 25) |  |  | 0 (2019) |  | 2 | 866 | Verification source: Human Resource Management Service. Note: 1,362 systematised posts, as well as 866 filled posts, excluding MoI's civil servants, with possible minor deviations owing to the on-going systematisation.
Number of systematised and filled jobs for IT officers in LSGUs (Number) |  |  | 0 |  | 2 | 210 | Data for this indicator are collected every two years. According to 2020 data, there are 210 systematised posts for IT officers in 98 LSGUs, and the majority of those posts has been filled. Thirteen of those 98 LSGUs has no systematised IT posts (Aranđelovac, Golubac, Bela Crkva, Titel, Ljig, Knić, Gadžin Han, Sremski Karlovci, Ada, Arilje, Kuršumlija, Veliko Gradište, and Beočin), whereas certain local self-governments are ahead in terms of the number of IT experts: Belgrade (22), Zrenjanin (13), Subotica (8), Inđija (7), Novi Pazar (6), and Kruševac (5). Certain LSGUs have signed ICT-service agreements with private companies.
Number of civil servants trained to work in a digital environment compared to the total number of civil servants employed by the public administration authority, i.e. LSGUs (Number) |  |  | 50 (2019) |  | 75 | 1161 | In 2021, 48 training sessions in electronic government and digitalisation were held as part of the National Academy for Public Administration [programme]. These sessions were attended by 1,161 employees/participants.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.8.1: Drafting an analysis of the needs of the public administration for IT profiles and staff to manage IT projects and a proposal for a sustainable scheme of managing such staff within public administration; | Q2 2021 -> Q4 2022 | MPALSG | It has not commenced | - | . |  | This activity has not been implemented because donor support could not be secured. | Given the importance of implementing this activity, this activity will be proposed in the revised e-Government Development Programme and its AP 2023–25..
1.1.8.5: Implementing training for staff in bodies working on prescribing procedures and their implementation through software in line with the methodology defined by the law regulating entry into the Register of Administrative Procedures; | Q3 2021 | ITE Office | Completed | - | 1 training in how to list administrative procedures was held as a webinar with 48 attendees. The initial report has been consolidated. The operational framework is being drafted. The training was held by the National Academy for Public Administration as part of its training programme. |  | . | New training will take place, as needed.
1.1.8.8: Drafting an analysis for improving LSGU capacities for the introduction of e-Government to form ICT service/coordination centres for support to the establishment and improvement of e-Government for groups of LSGs; | Q4 2021. -> Q4 2022 | MPALSG | It has not commenced | - | . |  | This activity has not been implemented because donor support could not be secured. | Given the importance of implementing this activity, this activity will be proposed in the revised e-Government Development Programme and its AP 2023–25..
Measure 1.1.9: Improving information security and standards
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Share of institutions which have an established and functional information security system and which meet information security standards (adopted Regulation on information security and adopted disaster recovery plan) compared to the implemented regular and extraordinary inspections on annual level (Number) |  |  | 10 (2019) |  | 85 | 85 | МТТТ submitted the report
Number of implemented information security tests for ICT in public administration and local self-government (Number) |  |  | 15 (2019) |  | 60 | 0 | Bearing in the mind that the competence of the national CERT is prescribed under the Law on Information Security (The Official Gazette of the Republic of Serbia, Nos. 6/2016, 94/2017, and 77/2019) but the competence of testing information security of ICT in state administration and local self-government is not, no testing was performed. The national CERT did not receive any report on information security of ICT systems in state administration or local self-government. RATEL submitted the report.
Number of civil servants that have completed cyber exercises (Number) |  |  | 50 (2019) |  | 150 | 112 | RATEL provided the report, i.e. data
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.1.9.1: Issuing expert recommendations for the protection of ICT systems of public administration bodies, which include the application of standards for disaster recovery and business continuity. | Q4 2020 -> Q4 2021 | ITE Office | Completed | - | ITE Office has adopted a Rulebook on the manner and measures of personal data protection. This document encompasses in part business continuity. The ITE Office has also adopted a Directive on the procedure of restoring a service following an interruption. |  | . | .
1.1.9.2: In line with the expert recommendations referred to in activity 1.9.1, proposing amendments to the Decree on the further regulation of measures for the protection of ICT systems pertaining to public authorities | Q4 2021 | ITE Office | Completed | - | Considering that the ITE Office has adopted two documents which cover this area sufficiently (namely, the Rulebook on the manner and measures of personal data protection, and the Directive on the procedure of restoring a service following an interruption), there is no need to produce another document. |  | . | .
1.1.9.5: Establishing a Security Operation Centre (SOC) and a Computer Emergency Response Team (CERT); | Q4 2021 -> Q4 2022 | ITE Office | In progress | - | The technical specifications are being drafted |  | Consolidation of the required technical specifications. | A new deadline for the completion of this activity has been set: until the end of the e-Government Development Programme validity. However, this activity will be extended beyond that, until Q2 2023. The activity will be proposed in the revised Programme and its AP 2023–25.
Specific objective 1.2: Improvement of legal certainty in the use of e-Government
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of court acts and documents concerning or stemming from proceedings before judicial organs which have been delivered to businesses and natural persons through the unique electronic mailbox (Number) |  |  | 0 (2019) |  | 10000 | 4148
Number of regulations by inspection authorities sent to the unique electronic mailbox of businesses and natural persons (Number) |  |  | 0 (2019) |  | 2000 | 15879
Measure 1.2.1: Harmonising the legal framework with the regulations governing e-Government and e-Commerce
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Percentage of the legislation harmonised with general regulations on e-Government and e-Commerce compared to the previously identified number of regulations that need to be harmonised (%) |  |  | 0 (2019) |  | 50 | 64 | This concerns the number of regulations (general acts regulating electronic government) on which the Unified E-Government Unit gave opinions in 2021
Measure 1.2.2: Establishing inspection control of the electronic service delivery quality
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of implemented supervision controls by competent inspections through the use of e-tools (AI and ISI) (Number) |  |  | 0 (2019) |  | 50 | 736 | For the purpose of conducting inspection supervision over the application of regulations on the single and the special electoral rolls and citizens registers, the Administrative Inspection is allowed access to three special softwares used by the Ministry of Public Administration and Local Self-Government, the Ministry of Human and Minority Rights and Social Dialogue, and all units of local self-government when updating the Single Electoral Roll, the Special Electoral Roll, and Citizens Registers.
Number of state administration, APs, and LSG bodies implementing electronic administrative procedures whose electronic systems are open for supervision by the Administrative Inspection (Number) |  |  | 0 (2019) |  | 1000 | 525
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.2.1: Drafting checklists for control over the implementation of regulations in e-Government (AI and ISI); | Q2 2020-> Q4 2021 | MPALSG | Completed | - | Checklist for the domain of the Law on e-Government has been completed |  | . | .
1.2.2.2: Ensuring access to information systems of state bodies to inspections competent for supervision through the use of the e-Inspector software tool. | Q4 2020 -> Q4 2021 | ITE Office | Completed | - | Connecting to the Central Register of Mandatory Social Insurance (CROSO) |  | . | All functionalities have been developed. The production URL and the certificate are pending.
Measure 1.2.3: Establishing a mechanism for correcting and updating data entered into the registers and monitoring the use of personal data
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of official records available in electronic form on the service bus for citizens to be able to check whether their personal data is current and accurate (Number) |  |  | 0 (2020) |  | 70 | 19
Number of requests for the correction of data kept in the official records which are available electronically, submitted through the e-Government Portal (Number) |  |  | 0 (2020) |  | 150 | 1097
Number of requests for the correction of data kept in the official records which are available electronically, submitted to the authorities (Number) |  |  | 0 (2020) |  | 20 | 1097 | Requests submitted electronically through the e-Government Portal
Number of requests for reports on the use of electronically available personal data by authorities in their regular course of business (Number) |  |  | 0 (2020) |  | 50 | 0 | Activity Ensure the functionality of the e-Government Portal for monitoring the processing of personal data has been abandoned because funding was not secured. Therefore, no progress with respect to this indicator has been achieved.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.3.2: Establish a mechanism for automatic notification of the body competent for maintaining the original data to initiate the procedure for changes in case of a request for the correction of an incorrect item of data | Q3 2021 | ITE Office | Completed | - | А mechanism for automatic notification of the body competent for maintaining the original data to initiate the procedure for changes in case of a request for the correction of an incorrect item of data is established |  | . | .
1.2.3.3: Ensure the functionality of the e-Government Portal for monitoring the processing of personal data | Q1 2021 | ITE Office | Aborted | - | . |  | The activity has been abandoned since no funding was secured and the activity itself was conditional. | The activity has been abandoned.
Measure 1.2.4: Ensuring effective protection of the rights of e-Government users in court proceedings
Institution in charge: MINISTRY OF JUSTICE (MoJ)
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of court proceedings which can be initiated electronically (Number) |  |  | 4 (2019) |  | 15 | 4
Percentage of courts which accept writs and evidence submitted electronically compared to the total number of courts (Number) |  |  | 2.6 (2019) |  | 40 | 2.6
Percentage of courts which access, ex officio, data in electronic records required for conducting the proceedings and issuing decisions compared to the total number of courts (%) |  |  | 90 (2019) |  | 100 | 100
Number of judges trained to work in a digital environment compared to the total number of judges (Number) |  |  | 0 |  | 180 | 0
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.4.1: Make training for holders of judicial functions in digital skills in the domain of e-Government and e-Commerce, a mandatory part of the training programme at the Judicial Academy; | Q2 2021 | MoJ | Completed | - | Digital skills are an integral part of the Judicial Academy's annual training programme which the Programme Council adopts. |  | . | .
1.2.4.2: Conducting training for staff in the justice sector to work with electronic documents and data in electronic records, as well as with systems used to implement electronic procedures; | Q2 2021 -> Q4 2022 | JA | It has not commenced | - | . |  | The activity could not be implemented because funding had not been secured. The COVID-19 pandemic presented additional challenges. | .
1.2.4.3: Drafting an analysis of the needs to harmonise the court rules of procedure and process laws with the LES and LEG, including the need to prescribe the obligation of holders of judicial functions and court forensic experts to retrieve data, and/or review data on electronic records and registers kept by public administration bodies under the evidence proceedings; | Q2 2021 | MoJ | Completed | - | The conducted analysis served as the foundation for the working groups to draft the court Rules of Procedure and the Civil Procedure Law. The basic idea was to adjust the provisions on procedure to the process of digital transformation. |  | . | .
1.2.4.4: Harmonising regulations in accordance with the analysis under activity 2.4.3. | Q2 2021 -> Q4 2022 | MoJ | In progress | - | Proposals of amendments to the court Rules of Procedure as well as amendments to the Civil Procedure Law have been made, in order to align those documents with the Law on e-Government and the Law on Electronic Signature. |  | . | The adoption of the proposed amendments is expected.
1.2.4.7: Conducting training in accordance with the adopted programme | Q4 2021 -> Q4 2022. | JA | It has not commenced | - | . |  | The activity could not be implemented because funding had not been secured. The COVID-19 pandemic presented additional challenges. | .
Measure 1.2.5: Improving the legal framework and practice of using e-Signatures and e-Seals within public administration
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of issued qualified electronic seals (target 10,000), first year 10%, second year 30%, third year 60%) (Number) |  |  | 0 (2019) |  | 3000 | 60 | МТТ has delivered the report.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.5.2: Use of e-Signatures and e-Seals in e-Government [made possible]; | Q2 2021 | ITE Office | Completed | - | The [ITE] Office has become certified to issue signatures in the cloud. The use of electronic seal and signature has been made possible as part of electronic services in electronic government. |  | . | .
Measure 1.2.6: Improving delivery in e-Government
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of activated electronic mailboxes for companies and legal persons (Number) |  |  | 0 (2019) |  | 40000 | 19261
Number of activated electronic mailboxes for natural persons (Number) |  |  | 0 (2019) |  | 320000 | 787110
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.2.6.1: Drafting an analysis of process laws and other special regulations on delivery with recommendations for harmonisation with the provisions on electronic delivery in the Law on e-Government, with recommendations for amendments and a proposal for a Government Conclusion for harmonisation in accordance with the recommendations | Q2 2021 | MPALSG | Completed | - | The National Alliance for Local Economic Development (NALED) has prepared an analysis of the regulatory framework for e-Delivery, it has given recommendations for improving the regulatory framework and concrete proposals for amending 15 regulations. All three documents were prepared within the e-Delivery Improvement Project funded by the EBRD and implemented by NALED. As a result of this Project and the analysis, the Law on Businesses has been amended to the effect of introducing a mandatory registration of businesses through the e-Government Portal, which in turn stimulates further development of e-Delivery. Also, the Law on Registration with the Serbian Business Registers Agency has been amended to the effect that, among other things, written copies of registrar's decisions are delivered to the e-Mailboxes of registered users of the e-Government Portal, so that they may be duly informed. |  | . | .
1.2.6.3: Improving e-Delivery in e-Government − implementation of e-Delivery in procedures for registering the right of property, submission of tax decisions, inspection supervision procedures and other actions | Q4 2021 | ITE Office | Completed | - | A total of 12 users (9 bodies, and 3 information systems). 1. Local tax administration 2. Intellectual Property Office 3. Ministry of Public Administration and Local Self-Government 4. Directorate for Agrarian Payments 5. Ministry of Finance – Games of Chance Administration 6. RGA – Real-Estate Cadastre 7. National Academy for Public Administration 8. Ministry of Finance – Tax Administration 9. Ministry of Justice 10. e-Government Portal 11. Central Population Register IS 11. e-Inspector IS 12. e-Permit IS . |  | . | .
Specific objective 1.3: Increase of e-Government accessibility to citizens and businesses by improving client service
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
EU e-Government Benchmark – Key enablers (Index points) |  |  | 24 (2018) |  | 42−45 | 43
EU e-Government Benchmark – User centricity (Index points) |  |  | 68 (2018) |  | 76 | 78
Measure 1.3.1: Improving the e-Government Portal and other software solutions
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of services on the e-Government Portal (Number) |  |  | 20 (2019) |  | 100 | 196 | https://euprava.gov.rs/
Number of active e-Government Portal service-users (Number) |  |  | 300,000 (2019) |  | 1000000 | 1150576 | https://euprava.gov.rs/
Share of level-four sophistication services available on the Portal compared to the total number of electronic services on the e-Government Portal (%) |  |  | 0 (2019) |  | 40 | 26 | https://euprava.gov.rs/
Percentage of users with positive experience using services through the e-Government Portal (%) |  |  | 0 (2020) |  | 70 | 70 | https://euprava.gov.rs/
e-Government Portal’s functionality harmonised with accessibility standards (%) |  |  | 0 (2020) |  | 70 | 70 | a) Validation in terms of e-Accessibility 0 points, 46 HTML and 15 CSS errors; b) Navigation throughout the website is possible with the help of the <Tab> button, and visually partially visible, half a point, 3 out of 5 points; c) All files on the website available for downloading are in a readable format. There are no scanned files in an image format. Maximum number of points: 5 out of 5; d) Website content suitable for using tools such as text-to-speech or screen reader. Maximum number of points: 5 out of 5; e) Downloadable files are available in multiple formats: text (.pdf, .docx, .odt) and table (.xlsx, .ods) in a single format, half a point, 3 out of 5; f) Photos and images on the website contain alternative text. Maximum number of points: 5 out of 5; Accurate assessment: a total of 21 points out of the possible 30. Alignment is at 70%.
Number of services provided annually through the e-Government Portal (Number) |  |  | 0 (2019) |  | 2000000 | 2253547 | https://euprava.gov.rs/
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.1.1: Establishing a mechanism for measuring the user experience on the e-Government Portal (drafting a methodology for analysing the user experience on the e-Government Portal, drafting the analysis and establishing the mechanism); | Q2 2020 -> Q1 2021 -> Q4 2022 | ITE Office | In progress | 100% | The methodology was developed in April 2021. A new deadline for establishing the mechanism has been set: Q2 2023, and it will be funded from another source. |  | . | A new deadline for the completion of this activity has been set: until the end of the Programme validity. However, this activity will be extended beyond that: until Q2 2023..
1.3.1.4: Ensuring the accessibility of public administration electronic services on all platforms (mobile devices) | Q3 2021 -> Q2 2022 | ITE Office | In progress | - | Electronic services may be initiated on all platforms, using a web browser. The planned application for smart mobile phones/tablets, which in the first phase will enable certain functionalities of the e-Government Portal (My Data, e-Mailbox/e-Delivery, e-Kindergarten), will be developed by the end of Q2 2022. |  | COVID-19 pandemic. | New deadline has been set: Q3 2022. Until then, the given mobile application for E-Kindergarten and e-Delivery will be finished.
Measure 1.3.2: Standardisation and optimisation of electronic services to improve client services
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Percentage of standardised and optimised services among the 100 selected (%) |  |  | 0 (2019) |  | 50 | 29 | Through the e-Paper Programme, new electronic services for businesses are being added to the e-Government Portal. To date, 29 services have been fully digitalised, another 54 are ready for production, and the PPS has created another 10 with the Ministry of Mining and Energy (these services are available on the Ministry of Mining and Energy's Portal)
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.2.2: Digitalise 100 selected procedures for businesses at the national level and set them up on the e-Government Portal (creation of electronic services) | Q2 2021. -> Q4 2022. | ITE Office | In progress | - | In 2021, the configuration of remaining procedures was completed, training of relevant bodies was held, changes to the modules User Management and Service Configuration were made, registration of тенант professional users was completed, and the new system for stamping was configured. Integration with the NEB has been completed, and two of NEB's services have been published. Additionally, 20 services of the NBS Securities Commission have been configured and published. |  | Procurement of certified electronic seals by the authorities, obtaining MPALSG's approval to use the seal, and configuration of the new server for seals/stamp because of the increased number of ports. | The final preparations for publishing the services of the Plant Protection Directorate, the MEP, the MCTI, and the MoI on the e-Government Portal are underway. Procedures of the Veterinary Directorate are in preparation.
1.3.2.3: Optimise all procedures for businesses at the national level through the e-Paper project; | Q4 2021 -> Q4 2022 | PPS | In progress | - | By Q3 2021, 235 administrative procedures were optimised and 13 cancelled, which resulted in 33 million EUR in savings |  | The e-Paper Programme envisages a certain dynamic of the optimisation of administrative procedures for businesses. The Programme does not envisage that the optimisation will be completed in Q4 2021. Rather, the optimisation is considered to be a continuous process. | Drafting the final 2018–2021 report on the optimisation of administrative procedures for businesses, and drafting the new e-Paper Programme and its implementation Action Plan 2022–2025.
Measure 1.3.3: Providing support to e-Government users
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Percentage of services that provide support through a helpdesk (%) |  |  | 5 (2019) |  | 80 | 29 | 29 (only by e-mail, no telephone or helpdesk support). A contact centre has been set up. For [the] 29 services, the provided support will not be through a helpdesk but rather an e-mail.
Percentage of resolved help-desk user requests compared to the number of submitted requests (%) |  |  | 80 (2019) |  | 90 | 95 | A contact centre has been set up.
Percentage of services with data on user satisfaction (%) |  |  | 0 (2019) |  | 80 | 0
Percentage of services positively assessed by the users (%) |  |  | 0 (2019) |  | 70 | 0
Percentage of users who positively assessed the e-Government services (%) |  |  | 0 (2019) |  | 80 | 0 | A contact centre has been set up.
Percentage of services for which it is possible to follow case progress/status (%) |  |  | 0 (2019) |  | 80 | 0 | Activity related to this indicator has been abandoned.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.3.1: Establishing contact centres for support to citizens and businesses | Q4 2021 | ITE Office | Completed | 100% | A contact centre has been established. Phase 1 is complete. |  | Aligning the required technical specifications as well as the COVID-19 pandemic. | Phase 2 will be initiated this year, and completed by the end of 2023. The new deadline for phase 2 completion has been set for Q4 2023.
1.3.3.2: Drafting the methodology for measuring user satisfaction with public services; | Q4 2021 | ITE Office | Completed | - | The methodology for measuring user satisfaction with the e-Government Portal was developed in April 2021. |  | This activity entails measuring user satisfaction with public services, and not only electronic ones. Thus, the activity is also included in the new Public Administration Reform Strategy (PAR Strategy) 2021–2030, and the PAR Strategy Implementation Action Plan 2021–2025, https://www.pravno-informacioni-sistem.rs/SlGlasnikPortal/eli/rep/sgrs/vlada/strategija/2021/42/1/reg. | As per the PAR Strategy, this activity was to be completed by the end of 2022..
1.3.3.3: Establishing mechanisms for measuring user satisfaction with public services; | Q4 2021. -> Q4 2022 | ITE Office | In progress | - | The methodology for measuring user satisfaction with the e-Government Portal was developed in April 2021. Establishing the mechanism for measuring user satisfaction with the e-Government Portal is planned for Q2 2023. |  | This activity entails measuring user satisfaction with public services, and not only electronic ones. Thus, the activity is also included in the new Public Administration Reform Strategy (PAR Strategy) 2021–2030, and the PAR Strategy Implementation Action Plan 2021–2025, https://www.pravno-informacioni-sistem.rs/SlGlasnikPortal/eli/rep/sgrs/vlada/strategija/2021/42/1/reg. | As per the PAR Strategy, this activity was to be completed by the end of 2022..
1.3.3.4: Ensure the functionality of the e-Government Portal for monitoring the status of a case; | Q4 2021 | ITE Office | Aborted | - | . |  | Since funding was not secured, this activity (otherwise conditional) has been abandoned. | .
Measure 1.3.4: Affirmation of e-Government (raising awareness of civil servants and citizens about the importance of digitalisation and strengthening trust in electronic services)
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of civil servants using the e-Government infrastructure (Number) |  |  | 100 (2019) |  | 1000 | 10000 | It is difficult to identify the number of employees using the e-Government infrastructure because most of the employees are using e-Government. According to the previously published data, more than 10,000 employees were using the e-ZUP information system, https://www.ite.gov.rs/tekst/80/ezup.php.
Number of citizens using the unified mailboxes (Number) |  |  | 0 (2019) |  | 10000 | 787110
Number of video instructions compared to the number of new electronic services, and/or IS (Number) |  |  | 1 (2019) |  | 20 | 3
Number of businesses using the unique mailboxes compared to the total number of businesses (Number) |  |  | 0 (2019) |  | 1000 | 395
Number of announcements on social media accounts posted annually (Number) |  |  | 500 (2019) |  | 700 | 800
Number of announcements posted annually on the internet portals (Number) |  |  | 300 (2019) |  | 400 | 1844
Number of articles in the most popular daily newspapers and weekly magazines published annually (Number) |  |  | 200 (2019) |  | 240 | 449
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.4.2: Development of ITE Office communication strategy to promote electronic services; | Q3 2020 -> Q4 2021 | ITE Office | Aborted | - | . |  | The COVID-19 pandemic, as well as other priority activities of the ITE Office. | .
1.3.4.3: Implementation of ITE Office communication strategy to promote electronic services. | Q4 2020 -> Q4 2021 | ITE Office | Aborted | - | . |  | The COVID-19 pandemic, as well as other priority activities of the ITE Office. | .
Measure 1.3.5: Implementing a one-stop shop
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of services which have an established one-stop shop (Number) |  |  | 0 (2019) |  | 5 | 5 | The number of services varies because this is a pilot project. The most frequently provided services at one-stop shops concerned social welfare, property rights, and utility services.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.3.5.3: Adopting a by-law which will further regulated how one-stop shops will operate. | Q1 2021 -> Q4 2022 | MPALSG | In progress | - | A Working Group (WG) has been set up to draft a proposal of a decree, and thus far the WG has held two meetings during which it defined the basic postulates and elements of the future decree. |  | The reason for deviating from the original deadline had to do with the local self-governments being at different levels of development, and the fact that the future decree is meant to achieve uniformity and standardisation of the process. | Continuing to work on the decree proposal.
Specific objective 1.4: Opening data in public administration
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of data bases available on the Open Data Portal (Number) |  |  | 250 (2019) |  | 500 | 1643 | https://data.gov.rs/sr/
Number of users of the Open Data Portal (Number) |  |  | 500 (2019) |  | 1000 | 1498 | https://data.gov.rs/sr/
Measure 1.4.1: Securing the implementation of the open data legal framework
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of public administration bodies and other holders of public authority which share/publish open data on the Open Data Portal (Number) |  |  | 33 (2019) |  | 80 | 83 | https://data.gov.rs/sr/
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.1.1: Establishing a special organisational unit in ITE Office for open data and the Open Data Portal with the aim of providing support to institutions to open data in a machine-readable format, to ensure the sustainability of the open data initiative; | Q1 2020 -> Q4 2021 | ITE Office | Completed | - | A special organisational unit has been formed within the Sector for Digital Standardisation. It is called Section for Electronic Services Quality, Data, and Data Protection. This activity was completed in Q4 2021. |  | . | .
Measure 1.4.2: Improving the Open Data Portal
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of machine-readable datasets published on the Open Data Portal and regularly updated (Number) |  |  | 0 (2019) |  | 2800 | 5196 | https://data.gov.rs/sr/
Measure 1.4.3: Supporting the use of open data
Institution in charge: OFFICE FOR INFORMATION TECHNOLOGIES AND EGOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of organised hackathons, datathons and Open Data Weeks (Number) |  |  | 0 (2020) |  | 10 | 1 | Due to the pandemic, only 1 Open Data hackathon was organised.
Number of applications and software solutions launched owing to the use of open data (Number) |  |  | 8 (2019) |  | 15 | 35 | https://data.gov.rs/sr/
Measure 1.4.4: Introducing the concept of "smart city"/e-City
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator |  |  | Baseline value and year |  | Target value in 2021 | Achieved value in 2021 | Note
Number of cities that have piloted “e-City” projects (Number) |  |  | 0 (2019) |  | - | 0 | Owing to donor support of the Government of the Republic of Korea through a project run by the Korea Development Institute, a pilot project will be developed by the end of 2022 which will offer a conceptual design of how to apply the smart cities concept in Petrovac na Mlavi, Bečej, and Šid.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future steps for implementation
1.4.4.2: Drafting an analysis of methods to secure the infrastructure for establishing smart cities and their networking (cloud infrastructure) with a proposal for implementation, including an analysis on what services will be offered under the smart cities concept | Q1 2021 | MPALSG | Completed | - | The Analysis of methods to secure the infrastructure for establishing smart cities and their networking (cloud infrastructure) with a proposal for implementation, including an analysis on what services will be offered under the smart cities concept, has been conducted |  | . | .
1.4.4.3: Establishing a hardware and software environment for all smart city services along with the supporting monitoring infrastructure (metrics, auditing, user support system...); | Q2 2021 -> Q4 2022 | MPALSG | It has not commenced | - | . |  | The original deadline has been pushed forward because the Korean Government, which is supporting the implementation of this activity, has moved the deadline to 2022 due to the COVID-19 pandemic. | Once the Korea Development Institute has completed the analysis (currently on-going), company Samsung (which is the Institute's project implementation partner) will propose a software solution.
1.4.4.4: Implementation of at least two pilot projects for the application of the smart cities concept (regarding cultural, regional, and other specificities); | Q4 2021 -> Q4 2022 | MPALSG | In progress | - | The project is being implemented in cooperation with the Korea Development Institute and company Samsung, in Petrovac na Mlavi, Bečej, and Šid. The project will be finalised by the end of 2022. |  | The original deadline has been pushed forward because the Korean Government, which is supporting the implementation of this activity, has moved the deadline to 2022 due to the COVID-19 pandemic. | Continuing and expanding the cooperation with the Korea Development Institute on the smart cities projects.
1.4.4.5: Drafting a procedure for implementing e-Democracy with the aim of optimising resource utilisation and development of services. | Q4 2021 | MPALSG | Aborted | - | . |  | The activity has been abandoned since no funding was secured. | .