## All activities export_1
Annex 2: Table from the UIS system: Contribution of specific institutions on the implementation of the PAR AP 2018-2020. for the 2020
Annual Report on the Implementation of the 2020 Action Plan for: |  |  |  |  | AP for the Implementation of the Public Administration Reform Strategy 2018-2020
Institution responsible for coordination and reporting: |  |  |  |  | MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Public policy document elaborated by the Action Plan: |  |  |  |  | Public Administration Reform Strategy
Note: An overview of the implementation of all activities in the period of three years is currently not provided in one table from the Unified Information System for Planning, Monitoring Implementation, Policy Coordination and Reporting (JIS). It is possible to obtain reports from JIS for individual years, i.e. in this case for 2020.
Overall objective 1: Further improvement of work of public administration in accordance with principles of the European Administrative Space, provision of high quality services to citizens and business entities and creation of public administration which will significantly contribute to the economic stability and the improvement of the living standard
Document proponent: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Government effectiveness |  |  | 55.77 (2016) |  | 52−56 | 53.37
Specific objective 1.1: Improvement of organisational and functional public administration subsystems
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Clarity and comprehensiveness of the official typology of central government bodies |  |  | 4 (2017) |  | 5 | − | The value has not been measured since 2017.
Mechanisms ensuring managerial accountability laid down in the regulatory and legislative frameworks |  |  | 1 (2017) |  | 2 | − | The value has not been measured since 2017.
Measure 1.1.1: Organisational and functional restructuring of public administration by implementing, by 2020, evidence-based measures for optimisation of public administration with respect to work processes, organisational structures, the number of institutions and their fitness for purpose and the number of employees
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Optimised, coherent and rational structure of public administration – % of planned measures for 2018 under the HFR AP |  |  | 0 (2017) |  | − | 0
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.1.1.1: Amend the Law on State Administration in order to standardise and define typologies of organisational forms and administrative tasks (coherent fields of work in administration), and to delegate powers to lower-rank managers | Q4 2018 −> Q2 2019 | MPALSG | Abandoned | − | The activity was not implemented, i.e. the activity was abandoned. . |  | No agreement was reached in the reporting period at the meeting of the Special Working Group for Public Policies and Normative Affairs established at GENSEC. | Determine the official position of the GENSEC Special Working Group.
1.1.1.2: Establish the Register of Holders of Public Powers in order to create a single record of public administration bodies, types of powers and a clear vertical accountability among bodies, an inventory of public registers and bodies in charge of establishing and maintaining individual registers | Q4 2018 −> Q2 2019 −> Q4 2021 −> Q1 2025 | MPALSG | In progress | − | . |  | Delayed implementation of the activity. | According to the Proposal from the new Action Plan for the Implementation of the Public Administration Reform Strategy 2021−2030, the deadline is Q1 2025.
1.1.1.3: Amend the Decree on principles of internal organisation and job classification in ministries, special organisations and services of the Government, in order to establish units in charge of public policy planning, reporting, communications, harmonisation of capacities and obligations under the NPAA, and determining standards for the ratio of non-managerial staff to managers (1:5) | Q4 2018 −> Q4 2019 | MPALSG | In progress | − | . |  | . | The procedure for the adoption of amendments to the Decree is in progress, the Draft Decree has been prepared, and opinions of competent bodies and organisations are currently being obtained. The expected period for consideration by the Government is the first half of February 2021
Measure 1.1.2: Improved functioning of local self-government and decentralisation and deconcentration of state administration tasks by defining the strategic framework and strengthening the capacity of cities and municipalities to efficiently carry out public tasks and procedures, establish inter-municipal cooperation, and implement the principles of good governance
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
A strategic or programmatic document determining a decentralisation policy or local self-government reform adopted |  |  | 0 (2017) |  | − | − | The Draft Programme for the Local Self-Government Reform in the Republic of Serbia with the Action Plan was developed
The number of new inter-municipal cooperation arrangements in the joint execution of local self-government responsibilities |  |  | 0 (2017) |  | 8 | 6 | In 2020, two new agreements on inter-municipal cooperation were adopted, which together with those from previous years makes a total of 6. However, due to delays in the start of a new project providing funds in this area caused by the circumstances related to the KOVID-19 virus pandemic, public the call for support for new projects for 2020 was announced only at the end of the previous year. Accordingly, at the time of writing, final data on the number of supported new arrangements are not available, as an evaluation of the proposals received is ongoing. Link to the published public invitation: http://mduls.gov.rs/obavestenja/javni-poziv-za-podnosenje-predloga-projekata-za-uspostavljanje-i-unapredjenje-medjuopstinske-saradnje-2/.
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.1.2.1: Adopt amendments to the Law on Local Self-Government to align it with new regulations and to reform the legal framework for operation of LSGs bodies, community-level self-government and inter-municipal cooperation (create a single inventory of LSGs tasks, organise 8 instruction seminars, draft a model statute for LSGs, a model rules of procedure for municipal assemblies and a model decision on community-level self-government) | Q3 2018 −> Q2 2019 | MPALSG | Completed | − | . |  | . | .
1.1.2.2: Support the development of inter-municipal cooperation by reviewing the best mechanisms for the establishment of inter-municipal cooperation (IMC) in the implementation of the LSG scope, the preparation of model IMC agreements and advisory support for their implementation | Q4 2020 | MPALSG | Completed | 407.6% | The Fund for Inter-Municipal Cooperation was established in 2019 with the aim of supporting LSG in establishing new or improving existing inter-municipal cooperation. With the Fund for Inter-Municipal Cooperation, local self-government units were able to receive support through inter-municipal cooperation in establishing joint bodies, companies, institutions and other organisations, in accordance with the law and the statute in order to more efficiently organise work, improve services and the quality of life of the community. The establishment of 3 new inter-municipal cooperations, which included 24 LSG units (56 cities, 3 city municipalities and 15 municipalities), was financed in the following fields: Support to the establishment of the mobility and communication support service for people with disabilities (PWD), support to a better response to natural disasters and support to the establishment of a joint audit service and improvement of the existing one which included 8 LSG units (1 city and 7 municipalities) in the field of better response to natural disasters. In 2020, two new agreements on inter-municipal cooperation were adopted, and at the end of the year, a new Public Invitation was announced. The evaluation of project proposals is ongoing A comparative analysis of the international legal framework and practice in the field of inter-municipal cooperation of five EU countries was conducted, and a review was created of the existing legal and financial frameworks and practice of implementation of mechanisms encouraging the development of inter-municipal cooperation in the Republic of Serbia. A Methodological Instruction for drafting IMC agreements was developed in cooperation with the MPALSG and SCTM, which may be used for all other fields within the LSG scope, as well as for specific IMC agreements. Based on this Instruction, the SCTM developed models of IMC agreements in 15 fields within the LSG scope in 2019 and 2020, i.e. in 2019 in the following 11 fields: Attorney General's Office, local Ombudsman, cultural institution, energy manager, emergency situations, municipal inspection, road inspection, traffic inspection, education inspection, sports inspection and tourist inspection; and in 2020 in the following four fields: Free legal aid, social protection, budget inspection and municipal police. Depending on particularities of each field, models were developed on the basis of four IMC modalities: Inter-municipal service, inter-municipal institution, inter-municipal body and mutual assignment of tasks among LSG units. Models of IMC agreements were sent to all cities and municipalities, presented in a series of special workshops and published on the SCTM website. In addition to developing model agreements, the SCTM provides advisory support in the field of IMC to its members, at their request. . |  | .Due to the delay in starting a new project to provide funds in this area, caused by the circumstances related to the KOVID-19 virus pandemic, a public call for support for new projects for 2020 was announced only at the end of the previous year. Accordingly, data on the number of new arrangements are not yet available, as the evaluation of submitted project proposals is still ongoing. Link to the published public invitation: http://mduls.gov.rs/obavestenja/javni-poziv-za-podnosenje-predloga-projekata-za-uspostavljanje-i-unapredjenje-medjuopstinske-saradnje-2/. | Activities related to providing support to projects from the Fund for Inter-Municipal Cooperation continue to be conducted with support of donor Government of Switzerland until the end of 2022.
1.1.2.3: The Public Administration Reform Council to prepare and adopt a policy concept paper for decentralisation or improvement of the role of local self-government in carrying out public affairs | Q4 2019 −> Q1 2021 | MPALSG | Completed | − | The MPALSG prepared and consulted on the development of the Programme for the Local Self-Government Reform in the Republic of Serbia. This activity was initiated within the project: Support to the Implementation of the Action Plan of the Public Administration Reform Strategy - Local Self-Government Reform 2016-2019, funded by the SDC, which will continue in the new project “Local Self-Government for the 21st Century" also funded by the SDC. The Special Working Group for the development of the Programme for the Local Self-Government Reform in the Republic of Serbia was established with a Minister’s decision. Expert support to the Special Working Group is provided by the consultants hired for drafting the wording of the Programme for the Local Self-Government Reform in the RS. The first meeting of the Special Working Group was held on 23 December 2019, at which the Baseline for the Local Self-Government Reform was presented, as well as the plan and structure of the Programme for the Local Self-Government Reform in the RS. Two workshops were held: the first one in February 2020, which was attended by the consultants hired for the development of the Programme and which included practical work on individual parts of the wording, and the second one in October 2020, which was attended by the representatives of the Ministry and the Standing Conference of Towns and Municipalities who analysed all received comments and suggestions of the members of the Special Working Group on the draft version of the wording of the Draft Programme. In this regard, the Draft Programme for the Local Self-Government Reform in the Republic of Serbia with the Action Plan was prepared and submitted to the members of the Special Working Group for comments and suggestions. After consideration of submitted comments, the final Draft Programme and Action Plan will be developed and the formal process of a public debate will begin. . |  | The reasons for deviation occurred somewhat later than planned, due to the adoption of the Baseline for the preparation of the Programme for the Local Self-Government Reform in the Republic of Serbia. In addition to the above stated, there was a delay in the approval of the project: Support to the Implementation of the Action Plan of the Public Administration Reform Strategy - Local Self-Government Reform 2016-2019. Project implementation started in January 2019. | After consideration of submitted comments, the final Draft Programme and Action Plan will be developed and the formal process of a public debate will begin. Organise a public debate on the Draft Programme with the Action Plan. Obtain opinions of all competent bodies on the Draft Programme with the Action Plan and send it to the Government for consideration and adoption.
1.1.2.4: Develop functional reviews for 20 LSG units in order to support them in ensuring a more functional organisation of tasks | Q3 2019 | MPALSG | Completed | − | . |  | . | .
1.1.2.5: Prepare, conduct consultations and adopt a strategic/programmatic framework for the local self-government reform and improvement of the role of local self-government in carrying out public affairs (a strategy and action plan for decentralisation or a programmatic document for the reform of local self-government) | Q4 2019 −> Q3 2020 −> Q1 2021 | MPALSG | In progress | − | The MPALSG prepared and consulted on the development of the Programme for the Local Self-Government Reform in the Republic of Serbia. This activity was initiated within the project: Support to the Implementation of the Action Plan of the Public Administration Reform Strategy - Local Self-Government Reform 2016-2019, funded by the SDC, which will continue in the new project “Local Self-Government for the 21st Century" also funded by the SDC. The Special Working Group for the development of the Programme for the Local Self-Government Reform in the Republic of Serbia was established with a Minister’s decision. Expert support to the Special Working Group is provided by the consultants hired for drafting the wording of the Programme for the Local Self-Government Reform in the RS. The first meeting of the Special Working Group was held on 23 December 2019, at which the Baseline for the Local Self-Government Reform was presented, as well as the plan and structure of the Programme for the Local Self-Government Reform in the RS. Two workshops were held: the first one in February 2020, which was attended by the consultants hired for the development of the Programme and which included practical work on individual parts of the wording, and the second one in October 2020, which was attended by the representatives of the Ministry and the Standing Conference of Towns and Municipalities who analysed all received comments and suggestions of the members of the Special Working Group on the draft version of the wording of the Draft Programme. In this regard, the Draft Programme for the Local Self-Government Reform in the Republic of Serbia with the Action Plan was prepared and submitted to the members of the Special Working Group for comments and suggestions. After consideration of submitted comments, the final Draft Programme and Action Plan will be developed and the formal process of a public debate will begin. . |  | The reasons for deviation occurred somewhat later than planned, due to the adoption of the Baseline for the preparation of the Programme for the Local Self-Government Reform in the Republic of Serbia. In addition to the above stated, there was a delay in the approval of the project: Support to the Implementation of the Action Plan of the Public Administration Reform Strategy - Local Self-Government Reform 2016-2019. Project implementation started in January 2019. | After consideration of submitted comments, the final Draft Programme and Action Plan will be developed and the formal process of a public debate will begin. Organise and hold a public debate on the Draft Programme with the Action Plan. Obtain opinions of all competent bodies on the Draft Programme with the Action Plan and send it to the Government for consideration and adoption.
1.1.2.6: Reform of local administrative procedures in order to improve and standardise administrative procedures through continuous improvement and harmonisation of models of LSG administrative procedures and implementation of direct technical support packages to improve administrative efficiency for 20 LSG units. | Q4 2020 | MPALSG | Completed | 44.88% | In 2017, the SCTM, MPALSG, Office of the Prime Minister of Serbia and Public Administration Reform Team initiated the process of development of models of administrative procedures conducted by LSG units within entrusted and initial responsibilities. In 2017, a total of 189 procedures were identified and detailed models and application forms for all procedures were developed. Competent ministries were consulted during the development of entrusted procedures. All APs are published on the SCTM and MPALSG websites in 2017. In order to facilitate access of LSG units to the data exchange information system (eZUP), the SCTM, MPALSG and Office of the Prime Minister developed standard application forms for access to electronic databases maintained by the competent ministries and institutions. These application forms (application forms for access to official records) were based on entrusted models of procedures, data and a legal basis for each data that is necessary in the decision-making process. In this manner, LSG units have had more than 2 million data access so far (January 2021), which means that LSG units have obtained 2 million data contained in various documents on behalf of parties (e.g. birth certificates, real estate folio in the land register, tax administration data…). The SCTM and MPALSG continued updating procedures in 2018, 2019 and 2020, especially procedures within the entrusted responsibility, in cooperation with the competent ministries. In December 2019. The Government of the Republic of Serbia adopted a conclusion according to which the competent ministries undertake to update all the procedures within their competence conducted by LSG units. Having in mind legal changes, since the publication of the procedure, the procedures concerning civil statuses, i.e. registers, veterans' protection, child protection, local tax administration, traffic, property and legal relations, have been updated. In 2017 and 2018, the MPALSG and SCTM delivered regional training courses on the application of models of procedures, as well as training courses on the application of the data exchange information system. Considering that there is only direct support through municipal support packages for the improvement of administrative efficiency provided by the SCTM to LSG units, at least 20 LSG units harmonised and applies procedures within the entrusted responsibility and adjusted procedures within the initial responsibility based on proposed models of procedures. . |  | . | The activity is completed, and continues to be conducted. The SCTM and MPALSG will continue updating procedures within the initial responsibility of LSG units until the end of 2022, and supporting the competent ministries in updating procedures in accordance with amendments made to regulations. The Draft Law on the Register of Administrative Procedures, which passed a public debate, envisages that all entrusted procedures and initial LSG units will be in this Register from 2023. The plan in the following period is to provide direct support to 10 LSG units in order to improve administrative efficiency and apply models of administrative procedures.
1.1.2.7: Build capacities of cities and municipalities for the application of the principle of good governance in carrying out public tasks of local self-government | Q4 2020 −> Q2 2021 | MPALSG | In progress | 87.34% | Level, development or implementation of local anti-corruption action plans, and support to 4 additional LSG units began at the end of 2020. A total of 72 general acts and 126 specific acts were adopted and 143 thematic training courses/workshops were delivered to 1,559 participants through implemented support packages in these two fields in the stated LSG units. After a citizen satisfaction survey was conducted by CeSID, targeted support started to be provided in 31 LSG units, in 2020, in defining measures and recommendations for resolving issues resulting from the said survey. A total of 26 measures were developed and technical support provided by the end of the year, which should contribute to strengthening the participation and influence of citizens in the provision of public services. The National Annual Competition for Best Practices of LSG Units in the Application of the Principles of Good Governance (Annual Award for the Best City/Municipal Administration) was established in cooperation with the MPALSG and SCTM, which is awarded in 4 fields of good governance. A total of 2 cycles of national competition (for 2018 and 2019) were conducted, and preparation of the invitation for the best practices in 2020 is in progress. Funds for awards are provided from the MPALSG budget fund and the SwissPRO project implemented by the UNOPS and SCTM. . |  | . | Key steps in 2021: Develop, adopt and implement new or improve existing systems of control and management of citizens’ requests in LSG units in order to become more responsible, transparent, efficient and effective in responding to the needs of citizens and local users of public services.
Measure 1.1.3: Improvement of the Government’s public policy management (PPM) system by establishing, by the end of 2020, the legal and institutional frameworks for integrated strategic management and adoption of medium-term work plans for state administration bodies (SAB) aligned with Government’s strategic priorities and the programme budget
Institution in charge: PUBLIC POLICY SECRETARIAT OF THE REPUBLIC OF SERBIA
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
The share of proposed strategies and action plans harmonised with the PPM methodology in the total number of strategies and APs adopted by the Government per calendar year |  |  | 67.9 (2017) |  | 90 | 100
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.1.3.3: Improve inter-ministerial coordination by monitoring the achievement of priority objectives from the Government Programme through mechanisms of the Action Plan for the Implementation of the Government Programme | Q4 2020 | PPSRS | Completed | 100% | Implementation of the Action Plan for the Implementation of the Government Programme (hereinafter: APIGP), adopted on 9 November 2017, significantly improved inter-ministerial coordination at the national level, which contributed to better public policy management and improvement of the system for strategic management of priority objectives of the Government. The APIGP enabled the strengthening of top-down planning elements, as well as the implementation of mechanisms for the execution and monitoring of priority objectives based on defined results, which were achieved within the set deadline. The previous APIGP cycle finished in October 2020, where 54 out of 96 planned results were achieved, which contribute to the achievement of priority objectives, whereas 19 results are still in the process of implementation. During the reporting period, the PPSRS supported the organisational mechanism for coordination and monitoring of implementation and reporting on achieved results. In this regard, the PPSRS prepared quarterly synthesis reports on the achievement of priority objectives and reported to the Prime Minister and ministers on the degree of achievement of priority objectives (through summary assessments of the degree of achievement of priority objectives), and more often, at the request of the Prime Minister, if necessary. The PPSRS also provided professional support to state bodies in data collection and processing, as well as to their preparation for reporting. Successful implementation of the APIGP maintains the previously established efficient model for the implementation of Government's priority objectives, which further strengthens the mechanisms for central public policy management and coordination at the level of the Republic of Serbia. It also enables indicator-based monitoring, as well as decision-making by managers, in accordance with priorities and based on data and facts. . |  | The activity was conducted in accordance with the plan. In this regard, there were no deviations from the plan for the implementation of the activity during its implementation. | Based on the priorities from the Programme of the Government of the Republic of Serbia, which was established on 28 October 2020, the PPSRS prepared the APIGP proposal, in cooperation with other state bodies, which was submitted to state administration bodies on 5 January 2021 for obtaining an opinion. In the forthcoming period, after obtaining an opinion of the competent authorities, the APIGP proposal will be submitted to the General Secretariat for consideration and adoption by the Government.
1.1.3.4: Develop a single training course for the representatives of LSG units on the improvement of the PPM system and deliver two initial training cycles for all LSG units by the end of 2020 | Q4 2020 | PPSRS | In progress | 100% | Starting from the Training Course for 2019, the training system was also expanded to the local level in order to provide quality professional development of employed servants (employees, as well as decision makers) in LSG units on the adequate implementation of the planning system at the local level. The online training "Public Policies" began on 11 September 2020, in cooperation with the PPSRS and NAPA, in order to strengthen the capacity of participants to create public policies, implement them, monitor, coordinate and analyse public policy effects, report, link to the budget process through medium-term planning and determine costs of public policies, conduct consultations and public debates, including reporting on all elements of the process. Duration of the training is not limited and its delivery is in progress. Registered servants from four LSG units from Kragujevac, Novi Sad, Krupanj and Požega have been trained on the stated training so far. A total of 4 training courses were conducted in Q4 2929 as part of the webinar: "Development and Implementation of the Plan for Development of Local Self-Government Units". A total of 186 representatives from 75 LGS units participated in these webinars, 177 of whom are employees in LSG bodies, whereas other participants are employees in regional development agencies (RDAs). Also, a training dedicated to LSG units titled: "Public policies towards the development of LSG units” was delivered in 2020 for 16 servants. . |  | The activity is conducted online. The situation caused by the Covid-19 pandemic and the inability to be physically present and deliver training courses have led to a reduced number of registered LSG servants for participation in the said training. With its activities, the PPSRS points out to the participants in the planning system the need to comply with all the provisions resulting from the Law on the Planning System of the Republic of Serbia to improve the public policy management system at all levels, including the local self-government level. In this regard, the PPSRS submitted to all LGS units a letter, in September 2020, concerning a review of the obligations resulting from the Law on the Planning System of the RS, including the Guidelines for the Drafting of Plans for the Development of LSG Units and the Manual for Managers for the Application of the Law on the Planning System in the RS. | Online training activities for the remaining LSG units will continue in 2021.
Measure 1.1.4: Establishing solid coordination mechanisms enabling a harmonised development and functioning of e-Government, and finalising the legal framework and procedures for e-Government development
Institution in charge: MINISTRY OF INTERIOR
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Percentage of bodies electronically exchanging data from official records |  |  | 20 (2017) |  | 70 | 100
Percentage of bodies using data from the Central Population Register |  |  | 0 (2017) |  | 60 | 0
Percentage of data contained in the record of citizens of the Republic of Serbia converted into electronic form and transferred to the Central Data Processing and Storing System |  |  | 0 (2017) |  | 90 | 90
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.1.4.2: Establish a mechanism for electronic exchange of data from official records between bodies (through the e-ZUP system or web services established on the government service bus; data are updated through the Metaregister) | Q2 2019 −> Q2 2020 | ITE | Completed | 100% | The DECREE on the manner of keeping the Metaregister, manner of approving, suspending and revoking access to the service bus of bodies and manner of work on the e-Government Portal (The Official Gazette of the Republic of Serbia, No. 104 of 28 December 2018) was adopted. Statistics until the end of 2020: - 320 bodies electronically exchange data - 10,280,822.00 documents exchanged via the service bus - 35 web services on the service bus of bodies. |  | Involvement of bodies in the single data exchange bus, their training for work, granting privileges. | Increase the number of bodies that exchange data via the service bus.
1.1.4.3: Establish an application for keeping records on RS citizens within the Central System for e-processing and storing data, and then transfer of citizenship data in electronic form to the application from:  The Register of Yugoslav citizens kept by the MoI  The Book of Citizens kept by LSG units  The Birth Register, kept by the MPALSG | Q4 2018 | MoI | Completed | − | The application is set up and data transfer is in progress IV 90%. |  | . | .
1.1.4.4: Finalise the Bill and adopt by-laws regulating the establishment and keeping of the Central Register of Citizens | Q4 2018 −> Q2 2019 | MPALSG | Completed | − | The Law on the Central Population Register (The Official Gazette of the Republic of Serbia, No. 17/19) and the by-law regulating this area in more detail were adopted - the Decree on the manner of taking over, exchanging data, accessing and protecting data contained in the Central Population Register, as well as other technical issues of importance for keeping the Central Population Register (The Official Gazette of the Republic of Serbia, No. 68/19). |  | . | .
1.1.4.5: Establish the Central Register of Citizens (software development and data migration) | Q3 2019 −> Q1 2021 | ITE | In progress | 100% | The Central Register of Citizens started operating on 20 November 2020. The ITE conducted public procurement, a software solution was developed and data migration was completed. The office is in charge of storing and keeping citizens' data. The citizens' database is located in the State Data Centre and is kept according to the highest technical and security standards. According to the Law on the Central Population Register, the MPALSG approves access to the Central Population Register, and IT and data security tasks are the responsibility of the Office for IT and e-Government. . |  | Extension of Agreement implementation due to the Covid-19 pandemic. | None of the bodies have access to the CPR yet, except for the citizens who may verify their data with a certificate or 2FA. The MPALSG plans to start to allow access of CPR bodies from April 2021. According to the Law on the Central Population Register, the MPALSG approves access to the Central Population Register.
1.1.4.7: Improve the spatial units register and the address register and establish interoperability with other registers (finalise the Bill on the spatial units register and the address register and link the residence register and the business register on one hand with the spatial units register and the address register on the other) | Q4 2019 −> Q4 2020 | RGA | Completed | 100% | The Law on the Register of Spatial Units and the Address Register was passed on 4 February 2020. The Register of Residence established a connection with the Address Register, and with the Central Population Register through the Register of Residence. The business register kept by the BRA also established a connection with the RGA’s Address Register in Q4 2020. The RGA provided all bodies with a link to the data from the Address Register through the NSDI. . |  | . | .
1.1.4.8: Establish the National Spatial Data Infrastructure (NSDI) with the adoption of all by-laws in accordance with the Law on the NSDI and development of a national geoportal in accordance with the INSPIRE Directive | Q4 2020 −> Q4 2021 | RGA | In progress | − | The adoption of the Decree on the Implementation of Rules for NSDI Metadata and the Decree on Monitoring and Reporting on NSDI Activities regulates these NSDI fields in accordance with the existing INSPIRE implementing rules issued by the European Commission. The development of a national geoportal in accordance with the INSPIRE Directive resulted in the establishment of an information and communication framework for the efficient functioning of the data and information exchange service for the purpose of improving the national spatial data infrastructure. . |  | Insufficient personnel capacity of the employees in the Centre for Spatial Data Management, and the outbreak of the pandemic and the declaration of the state of emergency, significantly slowed down all activities that precede the adoption of acts. A consultant was hired for the development of the draft Decree on Implementing Rules for Interoperability. | The consultant continued working on the development of the draft Decree on Implementing Rules for Interoperability. Define the development of the draft Decree on Implementing Rules for Network Systems and a by-law - access to data clusters and data services for the priority work objectives of the Centre for 2021.
1.1.4.9: Conduct an assessment of the e-Government situation at the local level (on a sample of minimum 30 LSG units) and support the improvement of local capacities for its implementation (award of grants to maximum 40 LSG units for the development and implementation of the procedures relevant for the introduction of the e-Government and training and mentoring support for minimum 30 LSG units for the provision of e-Government services). | Q4 2020 −> Q2 2021 | MPALSG | In progress | 26.59% | Support for the improvement of the e-Government is provided to 65 LSG units through the Swiss PRO Programme. The results achieved so far in the implementation of the activity have been as follows: - An assessment of the e-Government situation was conducted on a representative sample of 60 LSG units, which defined further fields of support for the improvement of the e-Government and introduction of e-Services at the local level. -With the award of grants in the amount of RSD 30,930,718, a total of 35 LSG units were supported in the procurement of IT equipment and in the establishment and improvement of the e-Government and e-Services, through technical support, in order to increase accountability, transparency and efficiency in providing better access to services and rights of citizens and businesses at the local level . -The institutional framework was fully defined, models of documents prepared and forms for 45 e-Services developed, by the end of 2020, in the field of citizen status, local tax administration, social and veteran-disability protection, economy and agriculture. Introduction of these services in 35 LSG units is expected to take place in Q1 2021. -A design model for the website was prepared as part of the technical support, and 12 LSG units are expected to apply the model for the development of their official websites. -Also, additional 30 LSG units, through technical support, started working on the opening of data and LSG units’ budgets. Working groups were established within LSG units and individual meetings were held as part of mentoring support. -Also, two webinars on the topic of open data were organised in cooperation with the Office for IT and e-Services in order to provide an equal level of understanding of key concepts, definitions, the legal framework and data opening standards. -A total of 16 out of 30 LSG units opened an account on the Open Data Portal by the end of 2020, whereas 14 LSG units published their budgets in a machine-readable format. A total of 30 LSG units are expected to adopt the Rulebook on data opening by the end of Q2 2021 and to continue regular data uploading and updating on the Open Data Portal. . |  | Technical support for 65 LSG units for the improvement of the e-Government, introduction of e-Services, opening of data and LSG units’ budgets began to be provided in March 2020. Due to the introduction of the state of emergency caused by the Coronavirus pandemic in March, as well as due to the parliamentary and local elections held in June 2020, technical support activities were conducted at a slower pace than planned. During this period, despite many challenges and limited capacities of local administration, working groups in LSG units were established and first technical support activities started to be conducted through online mentoring and training. Activities have been further intensified since September 2020, after the establishment of local administration in these LSG units. Bearing in mind that the new circumstances slowed down the planned implementation of activities, technical support will continue to be provided in 2021. | Key steps in 2021: • Introduction of assistive technologies for persons with disabilities on the official website in 11 LSG units; • Introduction of the language of a national minority on the official website in 5 LSG units; • Introduction of an application for e-Participation/reporting of utility problems in 11 LSG units; • Mentoring and building employees’ capacities in 35 LSG units; • Adoption of a normative framework for data opening in 30 LSG units; • Preparation of machine-readable data sets and publication on the Open Data Portal for 30 LSG units.
Specific objective 1.2: Establishment of a coherent, merit-based public service and improvement of human resource management
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Extent to which the civil service, the local-level service and the public service systems are harmonised |  |  | 4 (2017) |  | 5 | 5
Adequacy of policy framework, legal framework and institutional setup for professional human resource management in public service |  |  | 2 (2017) |  | 3 | 0 | The activity was not measured in 2020.
Professional development and training of civil servants |  |  | 3 (2017) |  | 4 | 0 | The activity was not measured in 2020.
Measure 1.2.1: Establishing a coherent system of labour relations and salaries in the public administration based on transparency and fairness
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
The share of appointed positions filled through open competitions in the total number of filled appointed positions in state administration bodies and Government services |  |  | 31 (2017) |  | 50 | 41
The share of public administration employees to whom a fair and transparent salary system applies |  |  | 0 (2017) |  | 100 | 0
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.2.1.1: Draft and finalise the Bill governing the system of labour relations and salaries in order to establish a coherent, merit-based civil service system in public agencies and state bodies | Q4 2018 | MPALSG | Completed | − | . |  | . | .
1.2.1.2: Prepare and adopt the catalogue of titles and positions in state administration bodies, the catalogue of titles and positions in LSG bodies, the catalogue of titles, positions, functions and jobs in other parts of public administration, and continuously prepare and adopt amendments to the Catalogue of jobs in public services and others organisations (public services established by special laws) due to the need to optimise the work and establish an effective systematisation of institutions | Q4 2020 | HRMS | Abandoned | − | . |  | By redefining the deadlines for the commencement of the application of the systemic law on salaries of public sector employees, as well as accompanying laws, the deadlines for the adoption of the Catalogue of titles and positions in state administration bodies and the Catalogue of titles and positions in local government bodies have been moved. The previous period involved preparation of the catalogues, as well as amendments to the Catalogue of jobs in public services and other organisations in the public sector. | A special working group with representatives of state bodies, elected representatives of LSG units and line ministries was established for the development of a draft Decree on the catalogue of jobs in public services and other organisations in the public sector and jobs of civil servants in appointed positions in state bodies and bodies of the autonomous province and local self-government unit.
1.2.1.3: Prepare and determine a proposal for amendments to the Law on Civil Servants in order to improve the employment and depoliticisation process, evaluation of work results, integrity and strengthening of responsibilities and development of other labour law concepts, integrated HRM system based on competencies | Q4 2018 | MPALSG | Completed | − | . |  | . | .
1.2.1.4: Strengthen the capacity of the MPALSG, Administrative Inspection and HRMS by increasing the number of servants in these bodies and develop competencies of all the employees in HRM units in state administration bodies. | Q4 2020 | MPALSG | Completed | − | In accordance with the Rulebook on Internal Organisation and Job Systematisation in the Ministry of Public Administration and Local Self-Government Number No. 110-00-318/2019-02 of 23 September 2019, which was approved by the Government with Conclusion 05 No. 110-10230/2019 of 17 October 2019, which entered into force on 28 October 2019, the number of new employees increased by 11 in 2020. In accordance with the Law on Amendments to the Law on Civil Servants from December 2018, the Human Resource Management Service (HRMS) was approved to increase the number of employees by 10 new servants for the execution of the new competencies prescribed by the Law. After adoption of the Rulebook on Internal Organisation and Job Systematisation in the Human Resource Management Service on 24 June 2019, the existing number of jobs increased from 30 to 37 (i.e. from 35 to 45 servants). After obtaining approval, open competitions were carried out for filling 6 vacancies in the Service. Currently, 40 out of 45 servants envisaged by the Rulebook were employed at the end of 2020. With the support of the project "Support to the Public Administration Reform in Serbia" implemented by GIZ (Deutsche Gesellschaft für Internationale Zusammenarbeit GmbH), the Ministry of Public Administration and Local Self-Government developed the "Action Plan for Strengthening Capacities of Human Resource Units in Public Administration Bodies of the Republic of Serbia” in 2020. For the purpose of development of the Action Plan, the Ministry established a Special Working Group for the development of programmes and plans for the development and improvement of human resources management units with Decision No. 119-01-28/2020-20 of 28 May 2020, which adopted the said Action Plan at the end of 2020. This Action Plan will be used in the next three years for the establishment of a completely new role of managers and human resource management units in public administration bodies, which implies the abandonment of the traditional role of human resource units and transformation into modern human resource management units, which represents systemic changes in the system. The Action Plan contains a description of the existing institutional framework for human resource management in state administration bodies of the Republic of Serbia, a description of the desired status and an analysis of the current status of the role and capacities of human resource units in state administration bodies, a proposal of a three-year action plan for strengthening capacities until the end of 2023 and a communication plan for the proposed action plan. . |  | . | Strengthening capacities is a continuous process, which will continue in the following period.
Measure 1.2.2: Establishing the HRM function in public administration and improving the HRM function in state administration and local self-government by introducing new instruments and strengthening HRM capacity
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Extent to which the competency framework is used in state administration bodies and Government services |  |  | 0 (2017) |  | 3 | 3
Average capacity of LSG units to manage human resources according to the SCTM index |  |  | 54 (2017) |  | 70 | 50.94
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.2.2.1: Prepare and adopt documents for the adoption of the Competency Framework and introduction of competencies in the process of recruitment and selection, evaluation and promotion in state administration bodies | Q4 2018 | MPALSG | Completed | − | . |  | . | .
1.2.2.2: Draft and adopt by-laws regulating in detail the performance appraisal of public service employees | Q4 2019 | MPALSG | Abandoned | − | Activity was not carried out. |  | At its session held on 28 December 2020, the National Assembly adopted the Law on Amendments to the Law on Public Service Employees. This Law, published in The Official Gazette of the Republic of Serbia, No. 157/20, rescheduled the deadlines by specifying that the application would start on 1 January 2022. Consequently, the adoption of the aforementioned documents is delayed. | .
1.2.2.4: Develop and apply instruments (institutional and individual) for career management in state administration for civil servants and other measures for the strengthening of professionalisation of the administration in order to retain competent staff in state administration | Q4 2020 | HRMS | Completed | 111.7% | Since the beginning of the implementation of the innovated normative framework, which regulates the civil service system in terms of civil servant career development, the HRMS established a Career Management Centre with the aim of further improving and modernising the field of competence-based career management. For now, the work of the Centre is focused on an individual civil servant, because the roles of all factors in that process have not been institutionally determined. The services provided by the HRMS in this domain are an analysis of individual potentials, career counselling, development of an individual development plan and development support through individual work and work in small groups for all the civil servants applying on their own initiative or sent by managers. Also, the Centre checks competencies of those registered at the ITR and monitors the situation regarding the outflow of staff. With the support of the GIZ project "Support to the Public Administration Reform" in 2019 and 2020, two instruments for the assessment and development of competencies were developed: the Assessment Centre and Feedback − 360 Degree Assessment. Using the first instrument, 40 civil servants from different SABs were trained for assessors and a set of new individual and group exercises was developed. An online platform for the application of the second instrument 360 ​​Degrees Assessment was developed, employees of the Centre were trained for its application and a pilot project was implemented for 10 employees whose competencies were assessed. Human resource units were informed about the availability of this instrument, and its application at all management levels is particularly important. Also, the capacity of the HRMS internal team of coaches for the application of the coaching instrument for coaching teams and coaching senior managers has been continuously strengthened. The Centre carried out the following activities, in 2020, related to the application of the instruments for the needs of civil servants career development: - 75 civil servants were assessed in terms of individual development potentials for the purpose of promotion; - 22 employees underwent an assessment of general functional and behavioural competencies for the purpose of takeover through the internal labour market; - 10 civil servants applied for online assessment of competencies for development purposes; - 22 civil servants requested and received career counselling services; - 20 coaching sessions were held for 5 civil servants; - Feedback − 360 Degrees Assessment was conducted for 12 civil servants. In addition, two reports were prepared and submitted to the Government for review and consideration, the Annual Report on Results of Performance Evaluation for 2019 and the Annual Report on the Status of Outflow of Staff for the period April 2019−April 2020. |  | . | .
1.2.2.5: Conduct an analysis of the existing IT system of the Central Personnel Records (CPR), prepare recommendations, draft a technical specification for the replacement of existing IT systems with a new software solution and establish and develop HRM software that supports and automates tasks in a manner that integrates and covers the entire field of HRM operation | Q4 2020 −> Q2 2021 | HRMS | In progress | 100% | With the contracted expert IT consultant, the Human Resources Management Service begun to develop a technical specification, on 6 September 2018, for the project “Design and implementation of HRM IS for civil servants - Serbia”, for the needs of the Human Resource Management Service. In cooperation with civil servants from the Human Resource Management Service, the expert IT consultant prepared the final version of the IS technical specification on 10 December 2018, on the basis of which the process of using funds available in the European Commission umbrella agreement was initiated under the management of the EU Delegation to the Republic of Serbia: “FWC SIEA 2018 - LOT 2: Infrastructure, sustainable growth and jobs; EuropeAid / 138778/DH/SER/multi”. Based on the aforementioned technical specification, the technical consultant of the EU Delegation to Serbia prepared the final technical specification on the basis of which a public procurement procedure under reference No. Request for Services 2019/410480 Version 1 was conducted. Euronet Worldwide was selected according to PRAG procedures and a contract was concluded with the EU Delegation to the Republic of Serbia in December 2019. In accordance with the above stated, implementation of the project started with a kick-off meeting held on 20 January 2020. The plan is to create a new IS consisting of a total of 15 modules, 9 of which were developed by the end of 2020 (4 modules passed the testing phase on 26 October 2020 and may be found on the production server). The plan is to complete the testing of 5 more modules by 29 January 2021. . |  | . | The plan is to prepare a draft decree in Q1 2021 which enables implementation of the human resources management information system, public consultations on the decree and an analysis of the needs for amendments to the Law on Civil Servants in the part referring to the establishment of the human resources management information system.
1.2.2.6: Build capacities of cities and municipalities for implementation and improvement of human resource management function in local self-government (local administration) | Q4 2020 −> Q4 2021 | MPALSG | Completed | − | The Law on Employees in Autonomous Provinces and Local Self-Government Units, the full application of which began in 2017, for the first time comprehensively regulates the system of labour relations in autonomous provinces and local self-government units and establishes basic principles of the civil service system based on the standards accepted in modern comparative legal systems. The practice and mostly good results in the long-term application of the Law on Civil Servants indicated the view that the status of employees in the AP and LSG units should be regulated with the application of the same principles that regulate the status of civil servants. In this manner, the basic precondition for full professionalisation and depoliticisation of staff in the autonomous provinces and local self-government units is met, and work principles are introduced which enable professional and legal execution of tasks under the competence of AP and LGS units, whereas, during their work, employees are protected from political actions that could affect their position, career development, professional development and career advancement in the service. All the principles of the civil service system regulated by this law are systematically set in a manner that they leave autonomous provinces and local self-government units the freedom to decide in clearly defined areas such as: Adoption of the Human Resource Plan, tender procedures and appointment of the tender commission in the procedure of filling vacancies, work of the appeal commission that decides in the second instance on employees’ appeals against employment documents, and special professional development programmes for employees in local self-government units. For the purpose of the integrity of regulation, this law encompasses and regulates the position of officials in AP and LSG bodies, and thus completely terminates the application of the Law on Labour Relations in state bodies at the provincial and local level. Also, bearing in mind the autonomy in which the province and local self-government have the possibility to establish different organisational forms for the purpose of performing tasks within their competence, the law defines the scope of application to employees, with a positive or negative determination, in all the organisational forms that perform tasks within the scope of the province and local self-government and that are not expressly governed by other, special laws. In addition, adoption of the Strategy for Professional Development of Employees in Local Self-Government Units in the Republic of Serbia (The Official Gazette of the Republic of Serbia, No. 27/15, hereinafter: the Strategy) resulted in the determination of essential reform objectives on which the "establishment of a harmonised, permanent and sustainable system of professional development of employees in local self-government units" should be based. In accordance with the established objectives and the need to further harmonise labour and legal relations in state bodies, public services, AP and LSG bodies, amendments to the law from 2018 and adoption of appropriate by-laws normatively regulate all issues of importance for the professional development function at this level of government, as one of the preconditions for the introduction of the "new system of professional development of employees in local self-government units” defined by the Strategy. Also, additional regulation of conditions for the execution of tasks on a certain position was performed, provisions referring to officials’ position and work of the disciplinary commission were specified, the position of servants in case of amendments to the Rulebook and adoption of a new one was regulated, as well as the system for the assessment of servants and movements within the service. Simultaneously with the change of the normative framework, the provisions of the Special Collective Agreement for employees in local self-government units were harmonised and further specified. The Rulebook regulates employment rights and duties of employees in LSG bodies, city municipalities, special services and organisations. For the purpose of continuous developing of the human resources management function in local self-government units, the Council of Europe, together with the Ministry of Public Administration and Local Self-Government and the Standing Conference of Towns and Municipalities, initiated the Programme "Human Resources Management in Local Self-Government − Phase 2" (2018−2021), built on the implementation of the Public Administration Reform Strategy in the Republic of Serbia and the Action Plan for the Implementation of the Public Administration Reform Strategy in the Republic of Serbia and in accordance with the European Charter of Local Self-Government. The Programme is based on the achievements and challenges of the Programme "Human Resources Management in Local Self-Government − Phase 1" (2016−2017) and deals with the most relevant issues of human resources management and human resources development at the local government level in the Republic of Serbia. The second phase of the project is continued provision of the necessary support to cities and municipalities through further development and improvement of human resources management and professional development of local government employees, which started on 19 December 2018 and will be completed on 19 December 2021. As part of the expected result that refers to the strengthening of the human resources management function at the local government level, the Ministry of Public Administration and Local Self-Government, in cooperation with partners, in 2019 and 2020, carried out a series of activities aimed at improving the legal and procedural framework for human resource management, and include preparation of analyses and giving recommendations for the further public administration reform in the field of human resources management, and synchronisation of the local system with the principles of the civil service system. Primarily, they aim at determining the possibilities of introduction of a system of competencies and establishing a civil service system based on competencies in autonomous province and local self-government unit bodies. For this purpose, a Special Working Group for the development of the competence framework for the effective work of servants in autonomous provinces and local self-government units was established in 2020, which adopted the final document (the Competence Framework required for the effective work of servants in AP and LSG bodies), as well as the framework plan of activities and proposal for the schedule of integration of the competency framework for employees in AP and LSG bodies into the legislative framework. The competency framework for employees in AP and LSG bodies was presented as part of the SCTM Human Resources Management Network, which continued its work during the second phase of the project. With the adoption of the competency framework at the local level, employees in AP and LSG units obtain a modern tool for human resources management based on good practice established in the EU, but also in RS state administration. At the same time, introduction and application of the competency framework at the local level is a complex endeavour, given the number of local self-government units, their distribution, uneven number and training of employees in human resource management units who are the main responsible for the application of this concept. Accordingly, the establishment of the competency system at the local level is expected to take place in the next 2−4 years. In this regard, the normative framework (laws and by-laws) is expected to be changed in 2021, which will be followed successively (2022−2024) by the integration of the competency framework into the Regulations on job systematisation, tender procedure and assessment procedure, as well as strengthening capacities for the application of the competency framework (planning, implementation and delivery of training courses for employees). The Human Resources Management Sector also cooperates, in the Programme, in the implementation of the Support Package for local self-government units, which is implemented in fifty local self-governments in the Republic of Serbia and aims to provide comprehensive support to local self-governments in the HRM implementation process. Furthermore, an analysis of the quality of the selection of candidates with recommendations for improvement will be conducted in the aforementioned Programme, which should be carried out through the analysis of the tender procedure and application of the Decree on Internal Competition, and the goal is to determine the quality of knowledge testing and testing of abilities and skills expressed through case studies and through the application of regulations. The third segment of cooperation, which will also be established in the following period, is focused on the quality of implementation of the concept of evaluation of servants in AP and LSG bodies, as well as on determining effects of protection of employees' rights through efficient work of appeal commissions. 1. Advisory support was established by the SCTM on 4 September 2019. This is a continuous activity, and a total of 242 LSG questions have been processed so far, and adequate answers have been provided. 2. Models of documents are created in accordance with the needs of LSG units. This is also a continuous activity, and close to 80 different models of documents have been created so far and delivered to LSG through support packages and work of the SCTM team. 3. Since the beginning of the project, the SCTM team has organised 40 regional training courses. E-training was also organised in 2019 on the topic of professional development of employees in LSG units. A total of 4 webinars were held in 2020 on the topic of Harassment at Workplace − Mobbing. 4. A total of 50 LSG units, in which packages of direct technical support for the improvement of HRM are implemented, were selected in an open competition. The activity ends in Q1 2021. 5. The activity is in preparation, the organisational packages methodology has been developed, and implementation is expected to take place in 2021. |  | The activity was postponed due to the situation with Covid-19 because the priorities of the cities and municipalities were related to the health situation | In order to continuously develop the function of human resources management in local self-government units, the Council of Europe, together with the Ministry of Public Administration and Local Self-Government and the Standing Conference of Towns and Municipalities, will continue working on the Programme "Human Resources Management in Local Self-Government - Phase 2". The activity will be implemented as originally planned, with 15 LSGs as beneficiaries of organisational support packages, and 15 small grants.
Measure 1.2.3: Development of the professional development system in public administration
Institution in charge: NATIONAL ACADEMY OF PUBLIC ADMINISTRATION
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Percentage of delivered training courses done by the NAPA based on its annual work plan |  |  | 0 (2017) |  | 80 | 99
Percentage of public administration employees who successfully completed professional development programmes offered by the NAPA |  |  | 0 (2017) |  | 15−30 | 27
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.2.3.1: Adopt by-laws for the implementation of the Law on the National Academy of Public Administration and other specific laws governing professional development in certain parts of public administration | Q4 2018 | NAPA | Completed | − | The following regulations and other general acts were adopted: - Decree on accreditation, manner of engagement and fees for trainers and providers of professional development programmes in public administration (The Official Gazette of the Republic of Serbia, No. 90/18); - Decree on amendments to the Decree on accreditation, manner of engagement and fees for trainers and providers of professional development programmes in public administration (The Official Gazette of the Republic of Serbia, No. 71/19); - Rulebook on criteria and measures for evaluation of professional development programmes (The Official Gazette of the Republic of Serbia, No. 101/18); - Rulebook on central records of professional development programmes in public administration and issuance of programme participation certificates (The Official Gazette of the Republic of Serbia, No. 102/18); - Instruction on the methodology for determining needs for professional development in public administration bodies (The Official Gazette of the Republic of Serbia, No. 32/19); - General training courses for civil servants and General training course for employees in LSG units for 2019; - Training course for managers in state bodies and Training course for managers in LSG bodies for 2019; - General training courses for civil servants and General training course for employees in LSG units for 2020; - Training course of managers in state bodies and Training course for managers in LSG bodies for 2020. Also, certain elements of professional development were improved with the adoption of the Law on Amendments to the Law on Civil Servants (The Official Gazette of the Republic of Serbia, No. 95/18) and the Law on Employees in Autonomous Provinces and Local Self-Government Units (The Official Gazette of the Republic of Serbia, No. 95/18). Based on the adopted regulations, a unified system of professional development in public administration was established. The NAPA was able to exercise its responsibilities, and all employees in public administration have conditions for professional development in accordance with determined needs for professional development, as well as equal access to law and equal quality of professional development. . |  | . | .
1.2.3.2: Create Central Records of professional development programme in public administration | Q4 2018 | NAPA | Completed | − | . |  | . | .
1.2.3.3: Establish a system for accreditation of trainers and training providers in the area of professional development in public administration | Q1 2019 | NAPA | Completed | − | . |  | . | .
1.2.3.4: Adopt a general act on the programme for professional training of trainees (induction of trainees) | Q1 2019 | MPALSG | Completed | − | The Rulebook on the Introduction of Trainees in the Ministry of Public Administration and Local Self-Government No. 110-00-307/2019-13, was adopted on 9 October 2019. In addition, in 2020, the Model Rulebook on the Introduction of Trainees in State Bodies was prepared and published (in printed and electronic form) with the support of the German Agency for International Cooperation in Serbia (GIZ) project “Support to the Public Administration Reform 2018-2020”, and it was made publicly available as support to MPALSG bodies in the preparation of this by-law. . |  | . | .
1.2.3.5: Support further improvement of the system for the professional development of employees in LSG units by strengthening capacities of LSG units for carrying out professional development activities within their competence, and by developing, preparing and implementing professional development programmes | Q4 2020 | MPALSG | In progress | 7.301% | All planned project activities were implemented by providing support in the following manner: - The brochure "Planning the cycle of professional development for employees in local self-government units" was prepared and delivered to all local self-government units; - Guidelines for the development of a special professional development programme in the local self-government unit with a programme model were prepared as support to local self-government units in the preparation of special professional development programmes in local self-government units for 2021; - Determining the needs for the professional development of employees for 2021, for 92 local self-government units, in accordance with the Instruction on the methodology for determining the needs for professional development in public administration bodies, which started to be applied on 1 January 2020, and for these local self-government units, reports on the analysis of the needs for the professional development of employees were prepared, which were submitted to the NAPA in the prescribed format for the preparation of reports on the analysis of the needs for professional development in public administration for 2021; - Proposals for special professional development programmes for 2021 were prepared for 89 local self-government units; - The Draft Sectoral Programme for Continuing Professional Development for 2021 was prepared, which includes 17 areas of professional development and 101 thematic units. After considering and determining a proposal at a session of the Council for Professional Development of Employees in Local Self-Government Units, this draft programme was incorporated into the General Training Course for Employees in Local Self-Government Units for 2021. - Support was provided to the Ministry of Construction, Transport and Infrastructure, the Ministry of Education, Science and Technological Development, the Ministry of Trade, Tourism and Telecommunications and the Ministry of Youth and Sports in identifying professional development needs, preparing reports on identified needs and proposing sectoral special training courses for employees in local self-government units for 2021, which perform assigned tasks of inspection within the scope of these ministries; - A methodology for the evaluation of training courses was developed, which contains a proposal for measures for the improvement of the Rulebook on Criteria and Measures for the Evaluation of Professional Development Programmes. . |  | . | .
Specific objective 1.3: Improving public finance management and public procurement management
Institution in charge: MINISTRY OF FINANCE
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Percentage of implementation of the Public Finance Management Reform Programme |  |  | 0 (2017) |  | 100 | −
Measure 1.3.1: Improving the (framework for) sustainability of public finance by reforming and developing public property management
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Number of LSG units which established the register of public property, the database, and the framework for effective and transparent public property management |  |  | 30 (2017) |  | 85 | 81 | The number of LGUs stated here is based on the coverage of LGUs included in the current Exchange 5 Program (through the grant scheme and asset management support packages), increased by the number of LGUs that received support in the previous (fourth) phase of the Program, and eliminated user recurrences. JLS between these two phases. In that sense, it is a more conservatively expressed value of indicators based on program data, since due to the circumstances present during 2020, the mapping was not repeated using the SCTM questionnaire for self-assessment of local self-government in the field of asset management. For the sake of objectivity in the interpretation of the indicator, it should be pointed out that its target value was set for the last year of Exchange 5 implementation (which was actually moved to 2021 based on the Program Addendum), and that the indicator is still being met until the end of the Program. 20 LGUs that are beneficiaries of the technical support package for asset management, as explained in the report text for the related activity under measure 3.1.
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.3.1.1: Amendments to the Law on Public Property | Q4 2018 | MF | Completed | − | . |  | . | .
1.3.1.2: Development and delivery of 14 regional training courses for public property management at the local level | Q1 2020 −> Q2 2021 | MPALSG | In progress | 92.04% | The activity is implemented as planned, within the Exchange 5 Programme (the EU donation approved to the Republic of Serbia within the allocation of funds for IPA 2014 as part of the IPA II Action Programme implemented according to the indirect management regime). The activity has been partially implemented with the implementation of one cycle consisting of 7 training courses for public property management at the local level, from March to September 2020, whereas another cycle follows in 2021, as explained. The training courses in 2020 were delivered in the form of 6 live regional events, whereas the last, 7th event was organised online, in the form of a webinar, due to the circumstances caused by the COVID-19 pandemic. The training courses were conducted in accordance with the Sectoral Programme for Continuous Professional Development of LSG Employees for 2020, as accredited training courses. A total of 206 participants from 99 LSG units attended all regional training courses, including the webinar. The total number of participants who met the condition for obtaining a certificate in the field of managing public property of LSG units, after these training courses, amounts to 179 participants. The purpose of the training courses was to familiarise the employees engaged in property and legal affairs and property management affairs in LSG units with amendments to the Law on Public Property adopted in December 2018, and with other related regulations (the Law on Planning and Construction, the Law on Legalisation of Facilities, the Law on Housing and Building Maintenance, the Law on State Survey and Cadastre, the Law on Procedure for Registration in the Real Estate and Power Lines Cadastre, the Law on Roads, the Law on Public Utility Activities, the Law on Public Enterprises, the Law on Waters, the Law on Forests, the Law on Agricultural Land, the Law on Public-Private Partnerships and Concessions, etc.), as well as with accompanying by-laws, in order to adequately implement positive legal regulations in order to legally, efficiently and purposefully manage property, as well as with best practices in this area. With the implementation of this training cycle, all the participants who successfully passed the test strengthened their capacity to establish a purposeful and efficient system of managing public property in LSG units by raising the level of understanding of the legal framework and proper application of procedures in all the phases of this process; the awareness of the necessity to proactively act before competent cadastral services in terms of the obligation to register ex officio certain categories of real estate was raised; the level of knowledge of employees in LSG units, public companies, institutions, capital companies (whose LSG unit is the founder) was increased about the necessity of entering data into the register of public property. . |  | During the implementation of the Exchange 5 Programme, Addendum No. 1 of 24 September 2020, the extension of Programme duration was approved until April 2021, and the delivery of public property management training courses for LSG units was harmonised with the schedule. In that sense, one cycle of training courses consisting of 7 events was implemented in 2020, and another cycle of accredited training courses is planned to be implemented in Q1 2021. | Depending on epidemiological circumstances and accompanying prevention measures, the last cycle of training courses will be conducted in the form of 4 online events, in case the setup of 7 regional events (live) is not possible. The concept of training courses remains unchanged in the sense that the representatives of all LSG units will be able to participate and the training courses will be delivered as accredited training courses in accordance with the propositions of the NAPA and SCTM, as accredited training providers.
1.3.1.3: Implement LSG projects within the grant scheme for the improvement of public property management at the local level | Q2 2020 −> Q2 2021 | MPALSG | In progress | 93.7% | The activity is implemented as planned, within the Exchange 5 Programme (the EU donation approved to the Republic of Serbia within the allocation of funds for IPA 2014 as part of the IPA II Action Programme implemented according to the indirect management regime). With the conclusion of grant agreements (between the Contracting Authority in the MFIN/CFCU and LSG project coordinator) on 21 December 2018, the implementation of 18 projects was approved, within the programme grant scheme, in the field of property management at the local level. The projects covered 48 local self-government units (18 coordinators and 30 partners), and several other beneficiaries (PUCs, development agencies, CSOs). The total value of contracted projects exceeds EUR 3.5 million (3,528,954.72), out of which the European Union donation amounts to about EUR 3 million (2,973,371.54), and the remaining amount is co-financed by beneficiaries (EUR 555,582.19). An individual value of a donation per project, provided from EU funds, is envisaged to range between EUR 120,000-200,000. Initially envisaged duration of projects (12-18 months) was adjusted to the circumstances during the implementation, thus, duration of most projects was extended, which was one of the reasons for the conclusion of the Addendum for the extension of the total duration of Exchange 5 Programme until April 2021. Accordingly, and due to the fact that the state of emergency and the COVID-19 virus pandemic further slowed down the implementation, 4 grant scheme projects were completed by mid-2020, and the implementation of other projects continued in the second half of 2020 (and in the case of one project - the deadline was extended until February 2021). Considering that a total of 17 projects of this grant scheme were completed by the end of 2020, it may be stated, for reporting purposes, that all the LSG units participating in the grant scheme worked on the development of a public property register, database and general framework for effective and transparent public property management. Namely, certain mandatory activities were carried out in all projects, such as: 1 Establishment/improvement of the organisational structure of property management in local self-government; 2. Collection, verification and analysis of property data; 3. Filling in data on property owned/used by local governments in the Central Database managed by the Republic Directorate for the Property of the Republic of Serbia; 4. Determining the value of the property identified as a priority for valuation. In addition, grant beneficiaries carried out some of the optional activities such as: Building capacity of employees and local government officials in the field of property management (training courses, workshops, seminars); analysis and establishment of necessary ICT for property management in accordance with the requirements of applicable regulations (procurement of IT equipment/IT infrastructure and development/improvement of property management software); linking the property database to the accounting database; determining the actual condition of property, its beneficiaries or purpose and initiating changes in cadastral records; geodetic works necessary for exercising the right to register public property in the Republic Geodetic Authority (recording of surface and/or underground facilities and networks, conversion of condominiums of special parts of the building/apportioning, deleting buildings/facilities, developing a cadastre and topographic maps, etc.); preparing technical documentation necessary for the legalisation of buildings built without the building permit (e.g. preparing reports on property condition construction works projects). In this manner, public property management in LSG units, which are the beneficiaries of Exchange 5 Programme grant scheme, was improved. Specific results for each of the implemented projects are systematised within the final reports prepared within 3 months after completion of implementation, and submitted to the Contracting Authority in the MFIN. Monitoring and supporting the implementation of programme grant scheme projects is performed continuously through the system of monitoring and technical support coordinated by the SCTM, with the active participation of the MPALSG and MFIN. This included both daily communication with project beneficiaries and quarterly visits (or online meetings when live visits were not feasible) when the status of project documentation (technical and financial) and project implementation progress was reviewed, and project teams were given suggestions necessary for project reporting and for further work on the project. Reports created after the visits were regularly submitted to the CFCU and MPALSG. Training for the preparation of final financial statements for the projects completed in the period June - October 2020 was held in July 2020, on 15 July 2020, in coordination with the SCTM and in cooperation with the MPALSG and CFCU. In terms of the remaining projects completed at the end of 2020/beginning of 2021, the same training is organised at the end of January 2021. . |  | During the implementation of Exchange 5 Programme, Addendum No. 1 of 24 September 2020, the extension of Programme duration was approved until April 2021, and the delivery of public property management training courses for LSG units was harmonised with the schedule. | Since the Programme also envisages comprehensive support for the preparation of final narrative and financial statements on the project (within 3 months of completed implementation), as well as final verification visits to beneficiary LSG units, in the first half of 2021, the MPALSG, MFIN/CFCU and SCTM continue with the support activities, including the organisation of seminars/training for the preparation of final reports in January 2021.
1.3.1.4: Develop and deliver 20 packages of direct technical support to municipalities for the improvement of public property management at the local level | Q2 2020 −> Q2 2021 | MPALSG | In progress | 43.77% | The activity is implemented as planned, within the Exchange 5 Programme (the EU donation approved to the Republic of Serbia within the allocation of funds for IPA 2014 as part of the IPA II Action Programme implemented according to the indirect management regime). Thus, in addition to project donations for LSG units through the grant scheme, as explained in the previous activity, the Programme also provides support for the improvement of municipal property management services for 20 LSG units that mostly fall into the category of underdeveloped LSG units and/or include LSG units that were not support beneficiaries within Exchange Programme in this field. Support is provided in the form of expert technical assistance - the so-called support package. In terms of their scope, they are specifically adapted to the capacities of LSG units that are less developed or less advanced in the field of property management, since the intention is to make a step forward in the Programme, in case of such LSG units, in establishing at least basic preconditions for the property management system. The award of support packages is organised on a tender-based principle, with simpler procedural requirements. A call for/announcement of this type of support was initiated in March 2019, i.e. after the award of grants under the grant scheme, to ensure that there is no overlap of beneficiary LSG packages in grant scheme projects. Based on the Agreement on Cooperation with 20 selected LSG units, the planned technical support for property management has been implementing since mid-2019. Having in mind later activation of the support package in relation to the initial plan (synchronisation with the grant scheme), execution of this activity was extended for the period covered by the Programme Addendum, i.e. until April 2021. The circumstances caused by the COVID-19 pandemic, as well as the general state of emergency and individual emergencies in case of individual beneficiary LSG units, also affected the package implementation schedule throughout 2020. By their nature, these support packages include a number of standard activities carried out in each selected LSG unit. Their content is adapted and further aligned with the specific circumstances of a specific LSG unit in accordance with the needs listed in the application form and information collected during the initial analysis of LSG units. Therefore, there are 5 mandatory general activities for all beneficiary LSG unit: A1 - An analysis of the current property management situation in LSG units; A2 - Establishment of the public property right in LSG units, inventory, registration of property rights and keeping records on real estate in the public ownership of LSG units, public property management and utilisation of software application Register of Public Property of the Republic Directorate for the Property of the Republic of Serbia (RDPRS); A3 - Development and/or harmonisation of local documents on property management in LSG units; A4 - Improvement of the current situation with property accounting records and establishment of the basis for consolidated property management; A5 - Determining the factual state, i.e. physical identification of facilities (real estate/property units). An optional activity for which a total of 16 LSG units applied, i.e. O1 - refers to the support of LSG units in the introduction of an IT application for the consolidation of data obtained from property management services on the one hand and financial services/departments on the other. In the implementation of the activity so far, initial visits to all beneficiary LSG units were conducted by the end of October 2019, which served as a basis for conducting an analysis of the inventory and registration of the property rights, harmonisation of internal documents with relevant regulations, property accounting records, updating of the Register of Public Property, as well as the need for the improvement for each of supported LSG units. Analyses were prepared and, in addition to the findings obtained during visits, they include an analysis of internal documents and existing property records in order to identify the current situation and plan further activities within the package (support for the entrance of forms in the Register of Public Property in the RDPRS and support for the physical identification of public property in beneficiary LSG units). In cooperation with the RGA, electronic property records were obtained for 20 beneficiary LSG units, which directly support the improvement of property records and physical identification of property. Specifically, for the purpose of conducting these activities, a process was conducted for the engagement of persons - local associates for data entry in the Register of Public Property and for the physical identification of property. Having in mind the particularity of relevant job descriptions, especially in terms of the necessity to perform envisaged tasks on the territory of LSG units, the concept is designed in a manner that hired external associates must be from the territory of the beneficiary LSG unit, which is why the SCTM (through commission decision) hires these external associates on the basis of a proposed list of potential candidates obtained from the beneficiary LSG unit. All the material was prepared and submitted to the LSG unit. After submission of lists of candidates by LSG units, the commission in the SCTM made decision, which was followed by the selection of local expert service providers in June and July 2020 (one part for beneficiary LSG unit, i.e. about half for associate positions). Appropriate contracts were concluded with selected associates, and they have been effectively working in beneficiary LSG units since October 2020. The procedure for the selection of associates for the vacancies that were not filled in some LSG units after the first call was repeated in October and, due to specific situations in certain LSG units, a second call had to be prepared in November, whose completion is expected to result in the required number of associates in LSG units within the support package (who will start performing their tasks effectively from January 2021). In terms of other aspects of support within the relevant packages, the first set of workshops for all beneficiary LSG units was delivered by the end of September 2020 (regional grouping at 5 locations) on the topics of completion of the inventory and registration of public property of LSG units (for each beneficiary LSG unit, classified per type of property and status) and managing the register of public property (provision of specific technical instructions throughout the workshop). The second set of training courses with beneficiary LSG units was delivered in November in the online format, as a combination of workshops for the harmonisation of the legal documents governing LSG units and coordination of competent services (based on models recommended within the Programme and advisory support), and workshops on financial property management. In terms of the mentioned models of local documents, it is relevant to point out that the following models have been prepared: A Model Decision on acquisition, disposal, use and management of public items; Model Instruction/Decision (on the coordination of work of all LSG services in the field of property management; and Model of a local document/Decision on construction land. All prepared models were submitted to beneficiary LSG units as part of the support package, and to other LSG units, and they were additionally presented to all LSG units at the meeting of the SCTM Property Management Network, held in December 2020. Considering that a total of 17 projects of this grant scheme were completed by the end of 2020, it may be stated, for reporting purposes, that all the LSG units participating in the grant scheme worked on the development of a public property register, database and general framework for effective and transparent public property management. . |  | During the implementation of Exchange 5 Programme, Addendum No. 1 of 24 September 2020, the extension of Programme duration was approved until April 2021, and the delivery of public property management training courses for LSG units was harmonised with the schedule. | Implementation of activities in the first half of 2021 includes coordination and further execution of tasks in all beneficiary LSG units related to data entry in the Register of Public Property and the physical identification of property through the SCTM and locally engaged cooperation teams. With regard to planned training courses for all beneficiary LSG units, two more cycles of training courses on financial property management will be delivered. Work on the software algorithm for the establishment of separate property records continues, i.e. linking property and financial data in LSG units, and on the software algorithm for the functionality of the mass migration of units, and, in the final stage, for providing support through the relevant packages - and preparing final reports per beneficiary LSG unit.
Measure 1.3.2: Improvement of the budget planning and formulation process
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Percentage of LSGs the budgets of which are formulated according to the programme budgeting methodology, measured annually |  |  | 60 (2017) |  | 80 | 81
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.3.2.3: Build capacities of LSG units for the implementation of the programme budgeting process in accordance with the programme budgeting methodology through the development of instructional documents for the programme budget formulation, organise 24 regional training courses for all LSG units and direct technical support for 12 LSG units | Q2 2020 −> Q2 2021 | MPALSG | In progress | 62.98% | The activity is implemented as planned, within the Exchange 5 Programme (the EU donation approved to the Republic of Serbia within the allocation of funds for IPA 2014 as part of the IPA II Action Programme implemented according to the indirect management regime). The emphasis of support was, therefore, on the correct and comprehensive application of programme budgeting requirements as a relatively new modality in the development and implementation of financial plans of LSG units by presenting programmes, programme activities and projects (mandatory since 2015). In that sense, Exchange 5 involved support to LSG units in all the budget cycle phases in 3 years of Programme implementation (April 2017-April 2020), and, in a somewhat reduced volume, in accordance with the approved Programme Addendum, it continued in the fourth year of Programme implementation (April 2021). Support was provided on the basis of the methodologies prescribed by the Ministry of Finance, where the SCTM has special responsibilities in terms of coordination, improvement and support to cities and municipalities in Serbia. Mapping of the implementation of the programme budget in all 170 LSG units was conducted in the first half of each calendar year, which was followed by detailed sectoral reviews of the programme budget for 20 LSG units, which are monitored in 2018-2020 time frame, and a review of planned expenditures for programmes, programme activities and projects in the budgets of 20 LSG units. Statistics were prepared for the LSGs practising the development and publication of citizen guides through budget decisions, as well as for those LSGs that apply a gender perspective in budgeting. Based on mapping and comparative analytical data for 2020, a conclusion is that LSGs continued an upward trend in the application of programme budgeting and in the transparency of local finance - 81% of LSGs present programme information in their budgets (whereas these percentages in previous years were: 2015-45.56%; 2016-46.5%; 2017-61.53%; 2018-67.65%; 2019-78%). In terms of other aspects of LSGs actions related to 2020 Budget Decisions, it was stated that the Citizen Guide was created by a total of 63 LSG units through the budget decision, and the Plan for the gradual introduction of the gender based budgeting (GBB) for 2020 was adopted by 32 LSG units. In accordance with this mapping, it was concluded that a public debate on the 2020 Budget Decision was held in 85 LSG units. In preparation for the annual budget cycle in reporting years 2018-2019, on average 4 sectoral workshops for the improvement of objectives and indicators of the programme structure of the LSG budget were conducted and organised according to related budget programmes, in cooperation with competent national institutions and LSG representatives, and packages of supporting documents and models for drafting the LSG Budget Decision (including in 2021 budget cycle in 2020) were prepared. In addition, based on the conclusions from the workshops and the requirements set by the Law on Planning System (from 2018), in terms of drafting planning documents at the local level, proposals for amendments to the programme structure of the LSG budget were prepared and submitted to the MFIN. In the autumn part of the budget cycle, on an annual basis, all LSG units in Serbia were supported through regional training courses, including, in addition to programme budgeting, reporting topics, gender based budgeting, capital planning and promotion of citizen guides through the budget and public debates on the budget. In reporting years 2018-2019, annual series of 12 regional training courses (24) for all LSG units in Serbia were delivered, with an average participation of 600-700 representatives from over 70% of LSGs. Additionally, in the fourth year of Programme implementation, in accordance with the approved Programme Addendum, another cycle of these training courses was conducted in September 2020 (support in the preparation of budget for 2021). Although the training courses were initially planned to be delivered in the form of 7 regional in vivo one-day events, due to changing circumstances and measures of the limited number of participants on public gatherings, due to the COVID-19 pandemic, it was decided to implement this activity in the form of 4 one-day webinars. The webinars were held in accordance with the guidelines for conducting online training courses and included just over 200 participants from 93 LSG units. In all reporting years, the Programme has continuously ensured the provision of advisory support for specific issues requested by LSG units. A special page was set up on the SCTM website dedicated to programme budgeting where information is updated and model document (aligned with the MFIN) on related processes uploaded (models of citizen guide through the budget, instructions and models for plans for the gradual introduction of the GBB, reporting forms on LSG PB performance, model documents in the process of capital planning) - available to all LSG units, and they are also communicated through the SCTM Network for Local Finance. In addition to the described content of the support provided to all LSG units in Serbia, an important aspect of technical assistance within the Programme related to direct work with 12 LSG units (selected on the basis of competitions) in planning and programme budgeting. Namely, 2 competitions were conducted (in 2017 and 2019) on the basis of which 12 LSG units (8 + 4) were selected, which in the reporting years were provided with direct technical support in the processes of programme budgeting and capital planning, i.e. In all key steps and requirements, in terms of the budget calendar, thus, more advanced approaches in the application of these processes were tested. By mid-2020, final analyses of the process of programme, gender based and capital budgeting were conducted for all 12 beneficiary LSG units, with recommendations for further improvement of work. This completes provision of support under the Programme in this domain. (Until the end of Programme implementation, horizontal activities for all LSG units are treated - advisory support and development of general reviews of PB implementation at the local level). . |  | The activity was implemented as planned, in its entirety. However, it should be taken into consideration that, within the implementation of Exchange 5 Programme, Addendum No. 1 of 24 September 2020, the extension of Programme duration was approved until April 2021, and the delivery of public property management training courses for LSG units was harmonised with the schedule. | In further Programme implementation in the first half of 2021, the plan is to implement another cycle of mapping programme budget implementation for all 170 LSG units in adopted 2021 Budget Decisions, as well as continuous advisory support for all LSG units, especially in terms of reporting on programme performance and further implementation of gender based budgeting (whose introduction is limited with the latest amendments to the Law on the Budget System to year 2024).
Measure 1.3.3: Improvement of the financial management and control system of use of public resources and of internal audit
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Number of annual reports on the state of FMC and IA submitted by public funds beneficiaries to the Ministry of Finance (CHU) |  |  | 1,125 (2017) |  | 1200 |  | The activity of receiving annual reports is in progress. Legal deadline 31.03.2021. year, and we will enter the final data after the legal deadline.
Measure 1.3.4: Functional improvement of the budget inspection work
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Number of control operations by the budget inspectorate |  |  | 19 (2016) |  | 23 | 27
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.3.4.1: Filling budget inspectorate vacancies, 100% full capacity, in accordance with the Rulebook on Internal Organisation and Job Systematisation in order to increase the number of performed inspections, which contributes to the strengthening of the financial discipline. | Q4 2018 | MF | Completed | − | Filling budget inspectorate vacancies, 100% full capacity, in accordance with set objectives and systematisation from April 2018, according to which the number of systematised budget inspectorate jobs is 23. A new Rulebook on Internal Organisation and Job Systematisation in the Ministry of Finance was adopted in December 2018, according to which the Department for Budget Inspection, as an integral part of the Public Fund Control Sector, transformed into a special Sector for Budget Inspection. Out of a total of 40 systematised jobs, there were 26 employees in the Budget Inspection Sector of the Ministry of Finance in December 2020, 17 of whom are inspectors. The filling of budget inspectorate vacancies is in progress and in accordance with the three-year action plan for the employment of civil servants who perform inspection supervision under the competence of national inspectorates (7 in 2019, 7 in 2020 and 3 in 2021). A total of 9 new persons were employed in the Sector for Budget Inspection of the Ministry of Finance in 2020, 8 of whom are inspectors. . |  | . | .
1.3.4.2: Develop and adopt the Methodology for the Budget Inspection Work in line with the Law on the Budget System | Q2 2018 −> Q2 2019 | MF | Completed | − | . |  | . | .
Measure 1.3.5: Improvement of the public procurement system
Institution in charge: PUBLIC PROCUREMENT OFFICE
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
The total value of contracts signed on the basis of the framework agreement in one fiscal year |  |  | 42.7 (2016) |  | 35.5 | 0 | The data for 2020 will be available in the Report on public procurements, which the Public Procurement Office is, from 1 July 2020 and commencement of the application of the new Law on Public Procurement, obliged to submit by 31 March of the current year for the previous year.
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.3.5.1: Develop and adopt the by-laws arising from the new Law on Public Procurement harmonised with EU directives | Q4 2020 | PPO | Completed | 40.03% | All by-laws necessary for the full application of the Law on Public Procurement were developed and adopted. . |  | . | .
1.3.5.2: Standard forms for the publication of a public procurement announcement are created and published | Q4 2020 | PPO | Completed | 117.8% | Forms that enable performance of procedural activities on the Public Procurement Portal and application of the LPP were created and published. . |  | . | .
1.3.5.3: General models of tender documentation are created and published | Q4 2020 | PPO | Completed | 110.8% | Models of tender documentation were created. One set refers to the open public procurement procedure, and the other one refers to the public procurement procedure for concluding the framework agreement. Both sets contain model contracts. Models of tender documentation are expected to enable ordering authorities and bidders to apply the LPP more easily. . |  | . | .
1.3.5.4: General models of tender documentation are created and published | Q4 2018 −> Q2 2019 −> Q3 2020 | PPO | Completed | − | Considering it to be more useful, instead of the originally planned "Model Framework Agreements", Guidelines for the application of framework agreements were developed and published within the project "Support to further improvement of the public procurement system in Serbia” at http://eupodrska.ujn.gov.rs/dokumenta/. It is expected that they will enable the ordering authorities and bidders to apply the LPP more easily. . |  | . | .
Specific objective 1.4: Increasing legal certainty and improvement of the business environment and quality of public services provision
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Citizen-oriented service delivery |  |  | 3 (2017) |  | 4 | − | The value has not been measured since 2017.
Fairness and efficiency of administrative procedures |  |  | 3 (2017) |  | 4 | − | The value has not been measured since 2017.
Measure 1.4.1: Improving administrative procedures and ensuring that procedures before state administration bodies and public administration bodies and organisations when deciding on rights, obligations and legal interests of citizens and other entities are in accordance with the principles of good administration
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Percentage of laws aligned with the GAP Law |  |  | 1.5 (2017) |  | 100 | 54.4
Activity | Deadline -> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.4.1.1: Draft and adopt the Decree on One-Stop Shop (Article 42 of the GAP Law) | Q2 2018 −> Q4 2019 −> Q2 2020 −> Q4 2021 | MPALSG | In progress | − | . |  | Implementation of pilot projects will continue in 2018, 2019 and 2020. | Preparation of an analysis of the implementation of pilot projects and drawing conclusions on the basis of which more detailed criteria, measures and conditions will be defined by a by-law, in accordance with the GAP Law.
1.4.1.2: Draft proposals for amendments to the laws governing special administrative procedures in order to align them with the GAP Law (about 270 laws) | Q4 2018 −> Q4 2020 | MPALSG | In progress | − | . |  | Three laws were passed in 2020, a total of 147 out of 240 planned. | .
1.4.1.3: Publish data on civil servants and other persons authorised to carry out administrative procedures in all SABs on official Internet portals | Q4 2020 −> Q3 2021 | MPALSG | In progress | − | Implementation of this activity is in progress. Some bodies only partially complied with this obligation. . |  | Failure of SABs to comply with this obligation. For the purpose of completing this activity, an invitation, i.e. a reminder will be sent to publish the stated data. | Repeat invitation to SABs to complete the activity, i.e. to act according to the determined obligation.
Measure 1.4.2: Reform of the inspection supervision and ensuring better protection of public interest, while reducing administrative costs of inspection supervision and increasing legal certainty of inspected entities
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Percentage of separate laws aligned with the Law on Inspection Supervision |  |  | 0 (2017) |  | 95 | 44
Percentage of reviewed inspection checklists and joint inspection plans (full predictability of the work of inspection services) |  |  | 9.6 (2017) |  | 95 | 100
Number of inspection services using the unified inspection supervision system (e-Inspector) |  |  | 0 (2017) |  | 29.7−33 | 36
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.4.2.1: Alignment of 78 separate laws with the Law on Inspection Supervision | Q4 2018 −> Q4 2019 −> Q4 2020 −> Q 2023 | MPALSG | In progress | − | A total of 44 laws out of the 78 envisaged were aligned in 2020. |  | Deviation from the plan of alignment of separate laws with the LIS is primarily a result of waiting of the competent ministries, proponents of amendments, to collect more proposals for amendments, so that the law would not be amended only in the part referring to the alignment with the LIS. Urgent requests were sent for alignment of separate laws with the LIS. | Continue with urgent requests in order to speed up the alignment process.
Measure 1.4.3: Introduction and promotion of mechanisms which ensure quality of public services
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Number of reports drawn up on the basis of surveys of citizens’ satisfaction with the services received from state bodies and bodies of LSG units |  |  | 0 (2017) |  | 173 | −
Average ranking of the quality of training courses and seminars provided at the SKIP Centre |  |  | 0 (2017) |  | 4.5 | 4.5
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.4.3.1: Development of a feasibility study on the use of blockchain technology in the public administration of the RS and implementation of a pilot project, in accordance with the recommendations referred to in the study | Q4 2019 −> Q4 2020 | MPALSG | In progress | − | As part of the feasibility study on the use of blockchain technology in the Republic of Serbia, the Government of the Republic of Korea developed a feasibility study in the Republic of Serbia. The study was published on the website of the Ministry of Public Administration and Local Self-Government: http://mduls.gov.rs/publikacije/?script=lat . |  | . | .
1.4.3.2: Survey of citizens’ satisfaction, requirements and expectations in terms of the quality of public services (key stakeholders: citizens, civil society, economy, public administration employees) through the implementation of an internationally recognized citizens’ satisfaction methodology which includes mechanisms for continuous feedback between citizens and public administration as a sustainable mechanism of citizens’ influence on the work of public administration | Q4 2019 −> Q1 2021 | MPALSG | In progress | − | Implementation of the UNDP project is in progress as part of the survey of citizens’ satisfaction, requirements and expectations in terms of the quality of public services, whose main objective is to gain deeper insight into the citizens’ experience of public administration at the local and national level, by identifying good practice in public services and accelerating the public administration reform, as well as horizontal and vertical transfer of knowledge in the public administration system. The survey was conducted in four cycles within the project, in 10 LSG units selected using the representative sample system. The survey was divided into: a) Quantitative survey: A total of 10 LSG units were covered (Kuršumlija, Lebane, Bela Palanka, Prokuplje, Aleksinac, Bujanovac, Vranje, Pirot, Niš and Leskovac) on the territory of Jablanica, Pčinja, Toplica, Nišava and Pirot districts and b) Qualitative survey: includes 32 focus groups in 4 cycles, case studies and a roundtable discussion. In addition to the survey, the project envisages the development of a Methodology and guidelines for an independent analysis of the quality of services provided or financed by LSG units (by the end of March 2021), a manual based on examples of good practice, and 10 training courses in 10 LSG units on the application of the Methodology. . |  | . | .
1.4.3.3: Establish and achieve full operability of the Serbian-Korean Information Access Centre (SKIP), which enables all state bodies, civil society and citizens to improve their knowledge in IT and provision of e-services through various seminars and training courses | Q4 2020 | MPALSG | In progress | − | The Serbian-Korean Information and Access Centre (SKIP Centre), which opened on 20 December 2017, in the previous three years of work, in cooperation with numerous bodies, institutions and organisations, conducted more than 1,000 different free training courses, in which participated more than 35,000 citizens and servants. . |  | . | .
1.4.3.4: Gradual introduction of the public services quality management system through the implementation of a pilot project in a selected state administration body | Q4 2020 | MPALSG | In progress | − | The Department for Strategic Planning and MPALSG started in 2019 with the application of the European quality management instrument (CAF), after mapping all quality management instruments used in public administration bodies. The objective of CAF implementation is to improve efficiency, effectiveness, economic and social responsibility, and the Ministry of Public Administration and Local Self-Government is the first to implement this instrument. The CAF was implemented in the MPALSG in the period 2019-2020. However, the drafted Action Plan for improvement was not adopted due to the announcement of elections. A member of the Department is the CAF Correspondent for Serbia in the CAF Group of the EUPAN Forum of Assistants in charge of the public administration reform (https://www.eupan.eu/). Although Serbia is not a EU member, it was admitted as an observer during the mandate period both in the EUPAN and EUPAN quality management subgroup. . |  | . | .
Specific objective 1.5: Increasing citizens’ participation and transparency, improving ethical standards and accountability in performing public administration tasks
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Effectiveness of control by independent oversight bodies over authorities |  |  | 3 (2017) |  | 4 | − | The value has not been measured since 2017.
Availability of information of public interest |  |  | 4 (2017) |  | 5 | − | The value has not been measured since 2017.
Measure 1.5.1: Improving conditions for participation of the interested public in the work of public administration while increasing access to information on the work of public administration and on public finance
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Percentage of information bulletins published through the unified information system for access to, processing and presenting information bulletins, by 2020 |  |  | 0 (2017) |  | 50 | 0
Percentage of laws which during the preparation stage were subject to consultations under the Law on Amendments to the Law on State Administration |  |  | 0 (2017) |  | 70 | 0
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.5.1.1: Improve proactive transparency – information bulletins – by developing a user manual for the software application (unified information system for access to, processing and presenting information bulletins); deliver up to 15 training courses for authorised persons in state bodies and LSG units; adopt a new instruction for developing and publishing information bulletins; promote the application among the public, civil society, businesses and the media | Q4 2019 −> Q3 2020 −> Q1 2021 | MPALSG | In progress | − | Implementation of these activities is based on the previous adoption of amendments to the Law on Free Access to Information of Public Importance, which is in progress. After a public debate, the Ministry did not receive any comment or proposal for the amendment to the article proposing a reform of the information bulletins, which inevitably indicates the quality of the envisaged legal provisions that will improve this area of ​​access to information. It is also necessary to mention that the activities of development and piloting a unified information system for access, processing and presenting information bulletins were successfully carried out by the Commissioner’s Office. . |  | After a public debate and gathering opinions of competent bodies according to the rules of procedure, the Draft Law was in the final phase of drafting before it was sent to the Government in September 2019. Considering that the mandate of the former Commissioner was expiring, the Ministry considered it justified to leave room for the new Commissioner to make a statement about the Draft Law. Since it was necessary that proposals for additional amendments to the Law, submitted by the Commissioner to the Ministry in September 2019, be the subject of further consideration, before the final text of the Draft Law is sent to the Government for consideration and decision, considering that a lot of time has passed since the public debate (April-May 2018), when the Draft Law was the last time published, the Ministry of Public Administration and Local Self-Government published an Overview of the provisions amended in the Law on the official website in November 2019, and thus continued the trend of transparent and inclusive action in the process of drafting regulations. Since 2020 was an election year, a decision was made to continue working on amendments to the law after the establishment of the new Government. After the establishment of the new Government, a working meeting was held, in December 2020, between Minister of Public Administration and Local Self-Government Marija Obradović and Commissioner for Information of Public Importance and Personal Data Protection Milan Marinović, where cooperation and intensive work on creating the draft text of amendments to the Law on Free Access to Information of Public Importance was agreed upon. Calls were made to the competent bodies to designate representatives of their institutions who will participate in the work of the special working group. According to the Government's Work Plan, the deadline for the adoption of the Law on Amendments to the Law on Free Access to Information of Public Importance is Q1 2021. | Establish a new working group that will work on amendments to the law is planned for the first half of January 2021. The first meeting of the working group is planned for the second half of January, which will be followed by work on the preparation of the final version of the text of the Draft Law and actions taken according to the rules of procedure, so that the Draft Law could be submitted to the Government for consideration and decision, at the beginning of March 2021.
1.5.1.2: Establish the Council for Cooperation with Civil Society | Q2 2019 −> Q4 2020 | MPALSG | In progress | − | The Office for Cooperation with Civil Society carried out preparatory activities in 2019 for the establishment of the Council for Cooperation with Civil Society, within the scope entrusted to it by the Decree on the Office for Cooperation with Civil Society. With the technical support of the GIZ project "Support to the Public Administration Reforms in Serbia", an analysis of similar bodies in EU member states and countries in the region was prepared with recommendations for the establishment of such a body in Serbia. On the basis of the analysis, the Office prepared a concept for the establishment of this body which addressed key issues such as the composition and competencies of the Council, which was followed by a focus group (consultative meeting) with the representatives of civil society organisations to discuss the prepared concept. . |  | One of the reasons for the delay in the implementation of the relevant activity is due to the fact that there was a delay with the very beginning of work, which automatically made it impossible to meet the initially set deadline. Further, in an effort to offer a concept that would be acceptable to both civil society and the Government, the Office considered it necessary (although there was no such obligation) to conduct consultations with civil society organisations, which required additional time. A special challenge was the fact that similar mechanisms, established in the region, proved to be mostly ineffective, and it was necessary to consider in detail the reasons for such practices and offer potential solutions that would prevent similar practices in our country. Also, it should be borne in mind that in 2019, in parallel with this activity, the Office worked on the preparation of the Guidelines for the inclusion of civil society organisations in working groups for creating draft public policy documents, i.e. draft regulations (activity 5.3), which was significant burden for the Office’ already insufficient human resources. Finally, an additional difficulty was the absence of a strategic document (public policy document) that would determine priority directions of the development of cooperation between state administration bodies and civil society, whose implementation should be monitored by the Council. Implementation of this activity in 2020 was further slowed down by the fact that, in Q1 2020, due to the outbreak of the Covid-19 pandemic, the state of emergency was declared, which led to the postponement of numerous activities and activities related to the establishment of the Council. In addition, parliamentary elections were scheduled for the first half of 2020, which slowed down normative activities. When the Law on Ministries was passed on 26 October 2020, i.e. in Q3 2020, the Office for Cooperation with Civil Society ceased to exist, and the newly established Ministry of Human and Minority Rights and Social Dialogue assumed Office competencies. These reasons caused a delay in the establishment of the Council for Cooperation with Civil Society. | Given that the development of a strategic framework for cooperation with civil society is planned for 2021, and that one of the roles of the Council is to monitor implementation of the strategic document, which sets out priority directions for cooperation between state administration and civil society, plans for further activities will be considered and an advisory body of the Government will be established.
1.5.1.3: Improve citizens’ participation by developing the Guidelines for the composition of working groups for drafting public policy proposals and regulations and preparing and adopting by-laws regulating consultations with the interested public in the process of drafting regulations and private policy documents, following the adoption of the Law on the Planning System and the Law on Amendments to the Law on State Administration | Q4 2019 | MPALSG | Completed | − | At the proposal of the Public Policy Secretariat of the Republic of Serbia, the Government of the Republic of Serbia adopted the Decree on the methodology of public policy management, policy and regulatory impact assessment, and content of individual public policy documents (The Official Gazette of the Republic of Serbia, No. 8/19), on 31 January 2019, which regulates in more detail specific provisions of the Law on the Planning System (The Official Gazette of the Republic of Serbia, No. 30/18), including those that regulate public participation (of stakeholders and target groups) in the process of drafting public policy documents and regulations. In accordance with the provisions of Article 77 of the Law on State Administration (The Official Gazette of the Republic of Serbia, Nos. 79/05, 101/07, 95/10, 99/14, 47/18 and 30/18−state law), and after establishing cooperation with the Public Policy Secretariat of the Republic of Serbia, the Minister of Public Administration and Local Self-Government adopted the Rulebook on good practice guidelines for exercising public participation in the drafting of laws and other regulations and acts (The Official Gazette of the Republic of Serbia, No. 51/19), on 12 July 2019, a by-law that regulates in detail consultations on the preparation of regulations. Adoption of the abovementioned by-laws complements the new legal framework governing public participation in decision-making processes, whose foundations are set by the Law on the Planning System and Amendments to the Law on State Administration and the Law on Local Self-Government. These legal solutions have significantly improved conditions for citizens participation by "opening" processes of preparation of regulations and public policies for public participation from the earliest stage of their preparation through consultations, unlike in case of previous regulations and practice, which involved only public debates, as a rule, in the late stages of the decision-making process. The Office for Cooperation with Civil Society first prepared the Draft Conclusion, in 2019, on the adoption of the Guidelines for the inclusion of civil society organisations in working groups for drafting proposals for public policy documents and regulation drafts i.e. proposals, including stakeholders and target groups in this process by organising two focus groups, and then, the revised Draft Conclusion would be the subject of consultations with the general public using the round table method and collecting written comments. The Conclusion on the adoption of the Guidelines for the inclusion of civil society organisations in working groups for drafting proposals for public policy documents and regulation drafts, i.e. proposals (The Official Gazette of the Republic of Serbia, No. 8/20) was adopted on 30 January 2020. NOTE: During the drafting process, the title of the document was changed from the Guidelines for the composition of working groups for drafting public policy proposals and regulations, as stated in the text of the Action Plan, to the existing one, i.e. the Guidelines for the inclusion of civil society organisations in working groups for drafting proposals for public policy documents and regulation drafts, i.e. proposals. |  | . | .
1.5.1.4: Improve the open data initiative in the Republic of Serbia by: adopting the legal framework for open data and reuse of information in line with the EU Directive on the reuse of public sector information; acceding to the Open Data Charter; organising activities to promote the open data concept; and supporting the development of applications based on open data | Q4 2019 −> Q4 2020 | MPALSG | Completed | − | The project "Open Data−Open Opportunities" was completed in Q1 2020 with significant results. The Open Data Portal publishes over 2,000 data sets from 78 bodies and organisations. Five cities opened public transport data in the GTFS format and, consequently, lines, stops and routes are visible both on Google Maps and OpenStreet maps. Over 80 local self-government units opened data on the planned budget, revenues and expenditures, and a visualisation application was created. Data on air quality are published on the basis of measuring conducted by the Environmental Protection Agency, and read from devices which citizens use for measuring air quality. Visualisation was created of open data on the number of people infected with the COVID-19 virus on the territory of the Republic of Serbia, as well as on self-isolation. The Office for IT and e-Government received four ReSPA Awards in the Pandemic Response Competition, in the context of the e-Government, one of which refers to the use of open data. The name of the project is Spread Control and Infection Monitoring Mechanisms. Training courses and workshops were held on the topic of open data ecosystems, open data standards and examples of good practice for local governments were presented. Training on open data processing tools at the technical level was held for selected candidates. The concept of open data was also promoted through the Open Government Partnership initiative. A commitment was proposed for the new Action Plan, which improves services for citizens by opening and standardising data, and improves communication between the central and local government. . |  | . | .
1.5.1.5: Produce a comparative study of e-civic engagement practices in order to ensure a more efficient expression of views by citizens | Q4 2019 | MPALSG | Completed | − | A Comparative Study of the legal framework for the referendum, civic initiative and petition was done, with an overview of standards and principles contained in key international documents regulating the above-mentioned forms of citizens’ participation in the decision-making process. In addition, a Methodology for the development of the comparative study of the legal framework for the referendum, civic initiative and petition was developed. The countries selected for the Study were: Montenegro, the Republic of Slovenia, the Republic of Croatia, the Republic of Bulgaria, the Swiss Confederation, the Republic of Austria, and the Republic of Estonia. The Study also includes recommendations for improving the working draft of the Law on Referendum and People’s Initiative and other relevant regulations governing forms of direct citizens’ participation in the decision-making process (referendum, civic initiative and petition). . |  | . | .
1.5.1.6: Draft and adopt the new Law on Referendum and People’s Initiative in order to improve mechanisms for expression of views by citizens | Q4 2019 −> Q1 2020 −> Q2 2021 | MPALSG | In progress | − | The Draft Law on Referendum and People’s Initiative was sent to state bodies for their opinion, in accordance with the Government’s Rules of Procedure. After the text was modified to mirror the comments provided, the Draft Law, the rationale and accompanying documentation were submitted to the Government to approve it as the Bill. . |  | The Government still have not decided on the Bill. | .
Measure 1.5.2: Strengthening integrity and ethical standards of public administration employees and reducing corruption through strengthening prevention mechanisms
Institution in charge: MINISTRY OF PUBLIC ADMINISTRATION AND LOCAL SELF-GOVERNMENT
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Percentage of implemented recommendations of the Anti-Corruption Agency for elimination of corruption risks from proposed laws by 2020 |  |  | 24 (2017) |  | 40 | − | There are no data for this indicator as no opinions were provided in 2020, or, consequently, recommendations for elimination of corruption risks from proposed laws. The reason for that is the fact that the new Law on Prevention of Corruption started to be applied in September 2020. Based on this Law, the Agency, with the help of the OSCE, developed, at the end of 2020, a new methodology of corruption risk assessment in regulations and held trainings on its application for Agency’s employees. It is expected that, in 2021, the Agency will start conducting corruption risk assessment in regulations in its full capacity, in accordance with the new Law on Prevention of Corruption and the new methodology of corruption risk assessment in regulations, based on which the degree of fulfilment of recommendations would be assessed.
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.5.2.3: Establish a mechanism for monitoring implementation of the recommendations of the Anti-Corruption Agency after introducing corruption risk assessment in the process of preparation of regulations − the General Secretariat submits to the Agency an explanation of accepted recommendations or reasons for non-acceptance, after its approval as the Bill | Q1 2020 | GENSEC | In progress | − | No progress has been made in this field |  | . | .
1.5.2.4: Preparation of the first Annual Report of the Anti-Corruption Agency on the degree of fulfilment of recommendations based on the opinion on corruption risk assessment in the provisions of the draft law in the fields particularly at risk of corruption | Q1 2020 −> Q1 2022 | ACA | The activity has not commenced. | − | A precondition for the implementation of this activity was the adoption of the Law on Prevention of Corruption, which would contain provisions on the introduction of corruption risk assessment in regulations in the process of preparation of regulations and adoption of the methodology of corruption risk assessment in regulations, adopted by the ACA (see activity 5.2.1.). Also, a precondition was to adopt the Law and started with its application in 2019. Although the mentioned Law was adopted in May 2019, its application was postponed until September 2020. Due to the fact that the Law started to be applied only in September 2020, the activity could not be executed in time and in the manner envisaged by the Action Plan. . |  | The reason for delay in the implementation of this activity was caused by the commencement of the application of the Law on Prevention of Corruption in September 2020. | Based on the new legal framework in this field, the Anti-Corruption Agency will start implementing the new methodology of corruption risk assessment in regulations in 2021. Based on the opinions containing recommendations for the elimination of corruption risks from regulation drafts, which the Agency will submit to public authorities, reports will be made on the degree of fulfilment of the recommendations, which will denote implementation of the planned activity.
Measure 1.5.3: Strengthening of mechanisms for external and internal public administration control
Institution in charge: OMBUDSMAN
Indicator: |  |  | Baseline value and year |  | Target value in 2020 | Achieved value in 2020 | Explanation
Percentage of Ombudsman’s recommendations accepted by administration bodies |  |  | 88.88 (2016) |  | 91.88 | 77.03
Percentage of implemented recommendations made by the State Audit Institution |  |  | 70.35 (2017) |  | 75 | −
Percentage of cases where legal and natural persons acted upon recommendations issued to them by the Commissioner for the Protection of Equality |  |  | 77.7 (2017) |  | 80.7 | 87.2
Activity | Deadline −> New deadline | Institution in charge | Implementation status | Execution of funds (%) | Explanation of progress |  | Reasons for the deviation from the plan and measures taken | Future (key) steps for implementation
1.5.3.1: Draft, hold public consultations and formulate the Bill on Amendments to the Law on Free Access to Information of Public Importance in order to strengthen the institution’s independence, extend the number of obliged entities, improve procedures, and enhance proactive transparency | Q2 2018 −> Q2 2019 −> Q3 2020 −> Q1 2021 | MPALSG | In progress | − | After a public debate and collected opinions of the competent authorities (26), the text of the Draft Law was prepared, which envisages the expansion of the number of obliged entities, exceptions related to the protection of certain rights were specified, the number of reasons for rejecting requests was reduced, the provisions concerning the election for and termination of the Commissioner’s function were specified, improvement of the procedure before the authority, execution of the administrative procedure, exclusion from the second instance procedure in actions on the basis of requests for free access of the National Bank of Serbia, mandatory provision of the Commissioner's opinion on the draft laws referring to his scope, Information Bulletins Reform - Proactive Transparency The envisaged amendments to the Law will increase the accountability and transparency of the work of public administration and increase the amount of information about the work of the public sector. . |  | After a public debate and gathering opinions of competent bodies according to rules of procedure, the Draft Law was in the final phase of development before it was sent to the Government in September 2019. Considering that the mandate of the former Commissioner was expiring, the Ministry considered it justified to leave room for the new Commissioner to make a statement about the Draft Law. Since it was necessary that proposals for additional amendments to the Law, submitted by the Commissioner to the Ministry in September 2019, be the subject of further consideration, before the final text of the Draft Law is sent to the Government for consideration and decision, considering that a lot of time has passed since the public debate (April-May 2018), when the Draft Law was the last time published, the Ministry of Public Administration and Local Self-Government published an Overview of the provisions amended in the Law on the official website in November 2019, and thus continued the trend of transparent and inclusive action in the process of drafting regulations. Since 2020 was an election year, a decision was made to continue working on amendments to the law after the establishment of the new Government. After the establishment of the new Government, a working meeting was held, in December 2020, between Minister of Public Administration and Local Self-Government Marija Obradović and Commissioner for Information of Public Importance and Personal Data Protection Milan Marinović, where cooperation and intensive work on creating the draft text of amendments to the Law on Free Access to Information of Public Importance was agreed upon. Calls were made to the competent bodies to designate representatives of their institutions who will participate in the work of the special working group. | Establish a new working group that will work on amendments to the law is planned for the first half of January 2021. The first meeting of the working group is planned for the second half of January, which will be followed by work on the preparation of the final version of the text of the Draft Law, and actions taken according to the rules of procedure, so that the Draft Law could be submitted to the Government for consideration and decision, at the beginning of March 2021.
1.5.3.2: Draft, hold public consultations and formulate the Draft Law on Amendments to the Law on the Ombudsman in order to strengthen the institution’s independence, improve its efficiency and ensure the protection of rights of citizens before state bodies | Q4 2018 −> Q4 2019 −> Q4 2020 −> Q3 2021 | MPALSG | In progress | − | The working group emphasised consideration of the Bill submitted by the Ombudsman which refers to the extension of the scope to justice, the mandate, the procedure and conditions for the election of the Ombudsman and termination of the Ombudsman’s mandate, reporting, the issue of jurisdiction to protect the rights of the child. . |  | After the Ombudsman submitted to the MPALSG his own proposal for the new Law (not amendments) in September 2019, three working group meetings were held from October 2019 to February 2020, to discuss the proposed provisions. The Ombudsman actively participated at the meetings of the working group. SIGMA submitted its opinion on this proposal in early October. After the joint work and cooperation of the working group and the Ombudsman, the Ministry made certain amendments to the text of the Draft Law and prepared a draft version of the Baselines for amendments to the Law on the Ombudsman, which includes some solutions from the Ombudsman’s proposal from 2019. A meeting with a SIGMA expert was held at the Ministry of Public Administration and Local Self-Government on 6 March 2020, after which SIGMA submitted its opinion to the Ministry on 27 March 2020 on the solutions proposed so far for the improvement of the legal framework governing competence, organisation and work of the Ombudsman in the Republic of Serbia. After the establishment of the new Government, two working meetings were held between Minister of Public Administration and Local Self-Government Marija Obradović, Ombudsman, Zoran Pašalić, MSc, at which it was agreed to continue consultations on amendments to the Law on the Ombudsman. The Ombudsman submitted a new draft version of the Law on the Ombudsman on 14 December 2020. A new working group was established on 28 December 2020 to work on amendments to the Law. | The first meeting of the WG is scheduled for 14 January 2021. After the WG determines the baselines, the plan is to conduct online consultations, formulate the text of the Draft Law and conduct a public debate. This should be followed by work on the preparation of the final version of the text of the Draft Law, taking actions according to the rules of procedure, so that the Draft Law could be submitted to the Government for consideration and decision at the beginning of September 2021.
1.5.3.3: Prepare, hold consultations and formulate the Bill on Amendments to the Law on the State Audit Institution in order to ensure full financial and operational independence, as well as to provide a mechanism that will contribute to the greater coverage of audit entities (by shortening deadlines for the completion of the audit procedure, new audit titles) | Q4 2018 −> Q1 2019 −> Q4 2020 −> Q4 2023 | SAI | The activity has not commenced. | − | The Proposal of the Action Plan for the implementation of strategic activities in the following period was developed at the end of 2020, which moved the deadline for the implementation of this activity to Q4 2023. In the meantime, the needs for this activity will be examined in more detail and relevant analyses will be conducted. . |  | . | In the meantime, the needs for this activity will be examined in more detail and relevant analyses will be conducted.
1.5.3.5: Amend the Law on Prohibition of Discrimination in order to achieve full alignment with the EU acquis, especially in terms of: - The number of exceptions to the principle of equal treatment; - Defining indirect discrimination. | Q4 2018 −> Q2 2019 | SAI | In progress | − | The MLEVSA did not make actions related to the adoption of amendments to the Law on Prohibition of Discrimination in 2020. Due to the pandemic, in Q1 2020 and later, after the elections and constitution of the new convocation of the National Assembly of the RS and, accordingly, actions of the caretaker government - the MLEVSA did not initiate the issue concerning the amendments. The new Law on Ministries was adopted at the end of October 2020 (The Official Gazette of the Republic of Serbia, No. 128/20), whose provisions in Article 12 assign anti-discrimination tasks of state administration to the Ministry of Human and Minority Rights and Social Dialogue. Therefore, a correction should be made in Table item 5.3.5, and in the column "institution in charge" Development and adoption of the Draft Law on Amendments to the Law on Prohibition of Discrimination is envisaged by the Government's Work Plan for 2021. |  | . | .
1.5.3.6: Strengthen SAI capacities and improve working conditions by increasing the number of employees and finding a permanent solution to work premises problems | Q4 2020 | SAI | In progress | − | The number of SAI employees increased by 20 in 2019 and 2020. As of 31 December 2020, the SAI has 331 employees. . |  | Due to the situation with the COVID-19 pandemic, no progress was made in 2020 concerning the implementation of activities related to finding a permanent solution to the problem with SAI work premises. | .
1.5.3.7: Strengthen capacities of the Commissioner for the Protection of Equality (CPE) and improve working conditions by increasing the number of employees and improving business premises (elevators, windows and toilets, with a special emphasis on the toilet adapted to PWDs), in order to increase the percentage of actions based on the recommendation of the Commissioner for the Protection of Equality | Q4 2020 | SAI | In progress | − | A total of 60 civil servants and civil servants in appointed positions are allocated to the Commissioner’s Administrative and Professional Service with the systematisation (without a person elected by the National Assembly - Commissioner). The Commissioner’s Human Resource Plan for 2020 envisages employment of a total of 50 civil servants and civil servants in appointed positions in the Administrative and Professional Service by the end of the year. However, due to limited funds, vacancies were not filled, i.e. there were no takeovers of civil servants in 2020, nor announcement of internal and open competitions. The occupancy of jobs in the Commissioner’s Administrative and Professional Service envisaged with the systematisation is 62%, and, in order to further strengthen human resource capacities, it is necessary to fill vacancies in a planned and continuous manner. The mandate of Commissioner Brankica Janković expired on 27 May 2020, and the National Assembly, at its session held on 26 November 2020, for the second time elected Brankica Janković as Commissioner for the Protection of Equality, for a period of five years. The Commissioner’s Administrative and Professional Service has 37 permanent employees as of 31 December 2020 (the Commissioner for the Protection of Equality is not included in that number), 2 temporary employees and one person hired on the basis of a service agreement. Replacement of elevators in the premises used by the Commissioner was done in 2020. The toilet in the building used by the Commissioner was adapted for PWDs in 2019 by the Administration for Joint Services of the Republic Bodies (AJSRB). . |  | . | .